## Web
Pegasus S/W Test Cases #1
| No. | Section | Test Scenario | How to test | Expected Result | Actual Result | Test Date | Dev OK | User OK | Remark
FALSE | 1 | SQL/Schedule | Create schedule from PO |  |  | Found problem - Section must be department ID - Unit_qty & Unit name - BOM relation
TRUE |  |  | BOM | [6 empty] | Get information from user
TRUE |  |  | Generate production jobs SO | [6 empty] | Waiting for BOM
TRUE
FALSE
FALSE
TRUE | 2 | Web
TRUE | 2.1 | Inbound schedule | Confirm job | [6 empty] | Will ask user to confirm or not?
FALSE |  |  | Search conditions |  |  |  |  | FAILED |  | Will copy and edit the acme again
TRUE |  |  | Data table | [6 empty] | Found problem - Sorting icons disappear - Remove Add records, CSV Import
TRUE |  |  | * Will combine the inbound/outbound to single page
FALSE | 2.2 | Tag label generator | Generate tag |  | Tag generated correctly | Some information should be fix - Add serial no - Change font size - Adjust qrcode by the new format |  | WAITING
TRUE
TRUE
FALSE
FALSE
TRUE
TRUE
FALSE
TRUE
TRUE
FALSE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
FALSE | 2
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
FALSE
FALSE
TRUE
TRUE
FALSE
TRUE
TRUE
FALSE | 3
TRUE
TRUE
TRUE
FALSE
FALSE
TRUE
TRUE
FALSE
TRUE
TRUE
FALSE
TRUE
TRUE
FALSE
FALSE
TRUE
TRUE
FALSE
TRUE
TRUE
FALSE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
FALSE | 4
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
FALSE
FALSE
TRUE
TRUE
FALSE
TRUE
TRUE
FALSE | 5
TRUE
TRUE
TRUE
TRUE
TRUE
FALSE
FALSE
TRUE
TRUE
FALSE
TRUE
TRUE
FALSE | 6
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
FALSE | 7
TRUE
TRUE
TRUE
TRUE
TRUE
FALSE
TRUE
TRUE
TRUE
FALSE | 8
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
FALSE | 9
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
FALSE
FALSE
TRUE
TRUE
FALSE
TRUE
TRUE
FALSE | 10
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
FALSE
FALSE
TRUE
TRUE
FALSE
TRUE
TRUE
FALSE | 11
TRUE
TRUE
TRUE
TRUE
FALSE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE | 12
TRUE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Handheld
Pegasus S/W Test Cases #1
| No. | Section | Test Scenario | How to test | Expected Result | Actual Result | Date | Dev OK | User OK | Remark
FALSE | 1 | Inbound
TRUE |  | SUPPLIER | 1st screen - Show all grouping tasks | Click inbound => show all schedule groups | show all schedule groups | Date format wrong display | 2023-11-04 | WAITING |  | Waiting for fix issues
TRUE |  |  | 2nd screen - Show all item in group | Click a group | show all items | show all items | 2023-11-04 | OK
TRUE |  |  | 3rd screen - Show all details | Click an item | Show schedule data | Change to uneditable for Qty | 2023-11-04 | OK
FALSE |  |  | Store section | Click an item | Location should be display only in store_section(department) |  | 2023-11-04 |  |  | Will test again p'Yut will add the dept_id to location master
FALSE |  |  | Scan with correct tag label |  |  |  | 2023-11-04 |  |  | Will test again
TRUE |  |  | Scan with incorrect tag label |  | Alert dialog display | Alert dialog display | 2023-11-04 |  |  | Will test again
TRUE |  |  | Scan with correct location tag |  |  |  | 2023-11-04 |  |  | Will test again
FALSE |  |  | Scan with incorrect location tag |  | Alert dialog display |  | 2023-11-04 |  |  | Will test again
TRUE |  |  | Scan the actual label | Generate the label from web |  |  | 2023-11-04 |  |  | Will test again
TRUE |  |  | Duplicate scan | Re-scan an old label immediately |  |  | 2023-11-04 |  |  | Will test again
FALSE |  |  | Scan an used label | Re-scan an old label in other job |  |  | 2023-11-04 |  |  | Will test again
TRUE |  |  | Support label format | Scan label from web |  |  | 2023-11-04 |  |  | Will modify to support the below format 2023-11-04¦2023-12-30¦23110400005¦FDK-00075¦GOZENSHU Nine 500 ml¦12BTL/1CT¦12.000000¦BTL¦22¦1
TRUE
FALSE |  |  | Inbound the completely qty | Scan the label of completely qty |  |  | 2023-11-04 | OK
FALSE |  |  | Inbound the incomplete qty | Scan the label of incomplete qty |  |  | 2023-11-04 | FAILED |  | Will add this function
TRUE
TRUE |  | CUSTOMER | 1st screen - Show all grouping tasks |  |  |  | 2023-11-04 | FAILED
FALSE |  |  | 2nd screen - Show all item in group |  |  |  | 2023-11-04 | FAILED
TRUE |  |  | 3rd screen - Show all details |  |  |  | 2023-11-04 | FAILED
TRUE
FALSE |  | PRODUCTION | 1st screen - Show all grouping tasks |  |  |  | 2023-11-04 | FAILED
TRUE |  |  | 2nd screen - Show all item in group |  |  |  | 2023-11-04 | FAILED
TRUE |  |  | 3rd screen - Show all details |  |  |  | 2023-11-04 | FAILED
TRUE
TRUE |  | TRANSFER | 1st screen - Show all grouping tasks |  |  |  | 2023-11-04 | FAILED
TRUE |  |  | 2nd screen - Show all item in group |  |  |  | 2023-11-04 | FAILED
TRUE |  |  | 3rd screen - Show all details |  |  |  | 2023-11-04 | FAILED
FALSE
FALSE | 2 | Outbound
TRUE |  | FROZEN | 1st screen - Show all grouping tasks |  |  |  | 2023-11-04 | FAILED |  | Cannot show the data
TRUE |  |  | 2nd screen - Show all item in group |  |  |  | 2023-11-04 | FAILED |  | Cannot show the data
TRUE |  |  | 3rd screen - Show all details |  |  |  | 2023-11-04 | FAILED |  | Cannot show the data
TRUE
TRUE |  | COLD | 1st screen - Show all grouping tasks |  |  |  | 2023-11-04 | FAILED
TRUE |  |  | 2nd screen - Show all item in group |  |  |  | 2023-11-04 | FAILED
FALSE |  |  | 3rd screen - Show all details |  |  |  | 2023-11-04 | FAILED
FALSE
TRUE
TRUE
FALSE
TRUE
TRUE
FALSE
TRUE
TRUE
TRUE
FALSE
FALSE
TRUE
TRUE
FALSE
TRUE
TRUE
FALSE
TRUE
TRUE
FALSE
FALSE
TRUE
TRUE
FALSE
TRUE
TRUE
FALSE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
FALSE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
FALSE
FALSE
TRUE
TRUE
FALSE
TRUE
TRUE
FALSE
TRUE
TRUE
TRUE
TRUE
TRUE
FALSE
FALSE
TRUE
TRUE
FALSE
TRUE
TRUE
FALSE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
FALSE
TRUE
TRUE
TRUE
TRUE
TRUE
FALSE
TRUE
TRUE
TRUE
FALSE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
FALSE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
FALSE
FALSE
TRUE
TRUE
FALSE
TRUE
TRUE
FALSE | 10 | Stock Maintenance Inquiry / Report
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE
FALSE
FALSE
TRUE
TRUE
FALSE
TRUE
TRUE
FALSE | 11 | Login / Logout
TRUE
TRUE
TRUE
TRUE
FALSE
TRUE
TRUE
TRUE
TRUE
TRUE
TRUE | 12 | Menu
TRUE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE