## Equipment and Estimate time
Estimate cost and Labore cost of Data machine monitoring system for FTS
Item | Model / Part Number | Discription | Suppier | Brand | Lead Time | Quote Rev. | Unit price | Quantity | Total (BATH) | Unit | Installation Point | Catagory | PO Status | PO Number | Delivery day | Date of use | Status | Remark
1 | KV-8000(SO) | PLC Module | KEYENCE | KEYENCE |  |  |  | 1 | 0 | Set | Machine 1
2 | KV-XD02 | Monitor module | KEYENCE | KEYENCE
3 | KV-XL402 | RS232 Module | KEYENCE | KEYENCE
4 | KV-PU1 | Power Supply 24VCD 3A | KEYENCE | KEYENCE
5 | KV-7500 | PLC Module | KEYENCE | KEYENCE |  |  |  | 1 |  |  | Machine 2
6 | KV-XL402 | RS232 Module | KEYENCE | KEYENCE
7 | KV-PU1 | Power Supply 24VCD 3A | KEYENCE | KEYENCE
8 | - | Labore cost in side 15 Day | TOMAS TECH | TOMAS TECH | - | - | 0 | 15 | 0 | Day |  | Labore cost
9 | - | Labore cost out side 7 Day | TOMAS TECH | TOMAS TECH | - | - | 0 | 7 | 0 | Day |  | Labore cost
10 | - | Sefety cost | - | - | - |  | 10000 | 1 | 10000
10000
Note on O2: Administrator: Status - Waiting Approve - Already Approved

## Labore cost
Data machine monitoring system for FTS |  |  | Location | Remark
Concept design | 5 | day | office
Program design and devoloper | 5 | day | office
Dashboard design | 5 | day | office
Install program | 2 | day | out site
Debug for find trigger bit | 1 | day | out site
Test system | 1 | day | out site
Support | 3 | day | out site
SUM | 22 | day