## TO-DO
TO DO List documents
A.N.I. LOGISTICS, LTD. - CKD System Phase3 | [7 empty] | Last updated | 2023-12-22
No. |  | Title | Description | Requested By | In-charge person | Issue/Request | Current status/Solution | Result | Expected Date | Actual Date
1 | 1.1 | Kickoff meeting | - Introduce the team members, system concept and scope of work. - Present about the Stock management system - Show the demo about the production planning with Microsoft Excel. | ANI | TOMAS | Request |  | OK | 2023-11-08 | 2023-11-08
| 1.2 | Meeting | Hold the next meeting about present the next release of Specification document and talk about the remaining topics. | TOMAS | TOMAS,ANI | Request |  | OK | 2023-12-13
| 1.2.1 | Meeting | Hold the meeting about present the master plan and re-demo the CCTV and define the position of CCTV installation at on site. | TOMAS | TOMAS,ANI | Request |  | OK | 2023-11-30 | 2023-11-30
| 1.3 | Print tag | User asks about the tag label print for INNER packing. Does it print the all tag or print 1 by 1? | ANI | TOMAS | Request | Print all tags. It is able to print all tags in 1 time coz there are confirmation process in the packing process. | OK | 2023-11-08 | 2023-11-08
| 1.4 | Inner method pdf file | It will use the BASIC_PART_NO as the file name. Can it use JPEG format? |  |  |  | It is only supported the PDF file format. | OK
|  |  | There are some parts that it has more than 1 file depending on PACKAGE_TYPE. How to solve it? | ANI | TOMAS | Request | Tomas preferred to use the pattern in the item master settings below. The 1st 2 digits of package type in NET files will be mapped to the file name in the packing process automatically. INNER_PACKING_METHOD : <BASIC_PART_NO>_<%PACKAGE_TYPE%>.pdf Example: <BASIC_PART_NO>_RT.pdf <BASIC_PART_NO>_CA.pdf <BASIC_PART_NO>_PB.pdf | OK | 2023-11-08 | 2023-11-08
| 1.5 | Detective instruction require | Honda requests us to provide the instructions to detect/correction the work. | HONDA | TOMAS | Request | Details Confirmed | OK | 2023-11-15
| 1.6 | Deep detail report for Outer schedule | Add the detail report for label scan tracking of specific outer packing work. | ANI | TOMAS | Request | Already designed | OK | 2023-11-22
| 1.7 | Result meeting | User requests the result report data. | ANI K.Timphaka | TOMAS | Request | Hold this request. Will do after project go live. | Hold | 2023-11-15
| 1.8 | BG color identity for finished shift work | Add the column to user master to identify the shift work A/B user. Keep the above shift data to schedule and display it in the dashboard. | ANI | TOMAS | Request | Details Confirmed | in progress | 2023-11-22
| 1.9 | Temporary tag | Able to print the additional tag by scan an original and enter the print amount. | ANI | TOMAS | Request | Details Confirmed | in progress | 2023-11-15
| 1.10 | Show an OUTER Packing sequence number | Show a sequece number on Tablet | ANI | TOMAS | Request | Do nothing | Rejected | 2023-11-15
| 1.11 | New concept of staging process | Will redesign an easier operation concept of staging process | ANI | TOMAS | Request | Details Confirmed | OK | 2023-11-15
| 1.12 | Contents part receive just in time | There are 2 types of receive tag depending on origin country/no-country | ANI | TOMAS | Request | Details Confirmed | OK | 2023-11-15
| 1.13 | CP LIST report | User requests to keep an error to CP LIST report | ANI | TOMAS | Request | Ask K.Timphaka about the details | Rejected | 2023-11-15
| 1.14 | Locked control usage for web console | Control concurrent access by the same user. | ANI | TOMAS | Request | Waiting for development | OK | 2023-01-02
| 1.15 | Dashboard design | There are 2 types below |  |  |  | It will show 3 days of work as yesterday, today and tomorrow
|  |  | Summary dashboard | ANI | TOMAS | Request | Details Confirmed | OK | 2023-11-15
|  |  | Progress dashboard | ANI | TOMAS | Request | Details Confirmed | OK | 2023-11-15
| 1.16 | Condition to print the separate type of contents label |  | TOMAS | ANI | Request | Details Confirmed | OK | 2023-11-15
| 1.17 | Label fields mapping confirmation
|  | Receive tag |  | TOMAS | ANI | Request | Details Confirmed | OK | 2023-11-15
|  | Contents label |  | TOMAS | ANI | Request | Details Confirmed | OK | 2023-11-15
2 | 2.1 | Label expense report | User requests the label summary report that it used to sending the price to Honda. | ANI | TOMAS | Request | Waiting for development | OK | 2023-11-22
| 2.2 | Advance print | User send the filter information | TOMAS | ANI | Request | Details Confirmed | OK | 2023-11-22
| 2.3 | Table ID map to work |  | ANI | TOMAS | Request | No need to do | Rejected | 2023-11-22
| 2.4 | Add the Letters R,L to contents label |  | ANI | TOMAS | Request | Waiting for development | OK | 2023-11-22
| 2.5 | INNER PACKING Error Report |  | ANI | TOMAS | Request | Details Confirmed | OK | 2023-11-22
3 | 3.1 | Add tag receive/temporary label print function to HT | Scan the delivery sheet to confirm the work | ANI | TOMAS | Request | Details Confirmed | OK | 2023-11-22
| 3.2 | DIST master data |  | TOMAS | ANI | Request | Cancel the request | Rejected | 2023-11-23
| 3.3 | Export csv by user requested |  | TOMAS | ANI | Request | Details Confirmed | OK | 2023-11-23
4 | 4.1 | Label print management | 1. Add new column about the print type (JIT/Manual) to NET fiile => J/M 2. Create new page for Label print JIT/Manual. 3. Able to print all contents of packing set (PPP). 4. Add [Print all manual] for manual items only except the reprint. 5. Able to filter data Packing_date, PC_NO, Control_No, Parts_no and part_color. 6. Show serial no column. | ANI | TOMAS,ANI | Request | Spec prepared | OK | 2023-12-06
| 4.2 | Summary dashboard | Modify the chart by adding the summary number of other production groups e.g. In-house, etc. | ANI | TOMAS | Request | Spec prepared | OK | 2023-12-06
5 | 5.1 | Print type management | Need to add new the print type master to manage the print type for tag receive and contents label * Default type => JIT Use keying by - Part no - Part color - Control no - Model no - Print type JIT/Manual (data) | ANI | TOMAS | Request | Spec prepared | Waiting for confirm | 2023-12-13
| 5.2 | Import schedule | Add an error column when import the schedule Example => "Item master not found!!" for print type validate real time | ANI | TOMAS | Request | Spec prepared | Waiting for confirm | 2023-12-07
| 5.3 | Re-sorting the document |  | ANI | TOMAS | Request | Spec prepared | Waiting for confirm | 2023-12-13
6 | 6.1 | Dashboard modification | Modify the dashboard due to adding the summary detail report grouping by PC no | ANI | TOMAS | Request | Spec prepared | Waiting for confirm | 2023-12-13
| 6.2 | Add new table for Table master | Keying by 1. Table ID | ANI | TOMAS | Request | Spec prepared | Waiting for confirm | 2023-12-13