## Installation schedule Internal
OUT OF SCHEDULE | Schedule installation for power meter monitoring system OTICS Project ( Internal )
| No. | Description | [7 empty] | PIC |  | Progress (%) | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon
[10 empty] | Main | Support | time axis 2024-06-22 to 2024-09-16
|  |  | 1 | 2 | 2 |  | Progress ahead of schedule |  | (Input Number "1")
|  |  |  | 2 | 2 |  | Progress as planned |  | (Input Number "2")
|  |  |  | 2 | 2 | 3 | Progress with scheduled delay |  | (Input Number "3")
|  |  |  | 2 | 4 |  | Progress with scheduled delay |  | (Input Number "4")
[10 empty] | Overall |  | 0%
| 1 | Install Support And Conduit Loop 1 | bar: 2024-06-22 to 2024-06-23
|  | ACP-CT | [7 empty] | NATTAPOL,PHATTHADOL | OTICS | 0% | bar: 2024-06-22 to 2024-06-23
|  | LP-F1 | [8 empty] | OTICS | 0% | bar: 2024-06-22 to 2024-06-23
|  | LG-GH1 | [8 empty] | OTICS | 0% | bar: 2024-06-22 to 2024-06-23
|  | LP-OF ( 2FL ) | [8 empty] | OTICS | 0% | bar: 2024-06-22 to 2024-06-23
|  | ACP-DF ( 2FL ) | [8 empty] | OTICS | 0% | bar: 2024-06-22 to 2024-06-23
|  | NR-ASSY | [8 empty] | OTICS | 0% | bar: 2024-06-22 to 2024-06-23
|  | NR-HOUSING | [8 empty] | OTICS | 0% | bar: 2024-06-22 to 2024-06-23
|  | ES01-ASSEMBLY | [8 empty] | OTICS | 0% | bar: 2024-06-22 to 2024-06-23
|  | DB1-HLA | [8 empty] | OTICS | 0% | bar: 2024-06-22 to 2024-06-23
|  | DB2-HLA | [8 empty] | OTICS | 0% | bar: 2024-06-22 to 2024-06-23
|  | DB3-HLA | [8 empty] | OTICS | 0% | bar: 2024-06-22 to 2024-06-23
|  | ACP-HLA1 | [8 empty] | OTICS | 0% | bar: 2024-06-22 to 2024-06-23
|  | MT-SHOP | [8 empty] | OTICS | 0% | bar: 2024-06-22 to 2024-06-23
|  | LP-F2 | [8 empty] | OTICS | 0% | bar: 2024-06-22 to 2024-06-23
| 2 | Install Support And Conduit Loop 2
|  | MDB-1 | [8 empty] | OTICS | 0% | bar: 2024-06-22 to 2024-06-23
|  | MDB-2 | [8 empty] | OTICS | 0% | bar: 2024-06-22 to 2024-06-23
|  | LP-CT | [8 empty] | OTICS | 0% | bar: 2024-06-22 to 2024-06-23
|  | ACP-CT | [8 empty] | OTICS | 0% | bar: 2024-06-22 to 2024-06-23
|  | RO-WATER | [8 empty] | OTICS | 0% | bar: 2024-06-22 to 2024-06-23
|  | BOSCH | [8 empty] | OTICS | 0% | bar: 2024-06-22 to 2024-06-23
|  | NR-CAP | [8 empty] | OTICS | 0% | bar: 2024-06-22 to 2024-06-23
|  | ES01-CUTTING | [8 empty] | OTICS | 0% | bar: 2024-06-22 to 2024-06-23
|  | TSC-15 | [8 empty] | OTICS | 0% | bar: 2024-06-22 to 2024-06-23
|  | RAA | [8 empty] | OTICS | 0% | bar: 2024-06-22 to 2024-06-23
|  | HOLDER | [8 empty] | OTICS | 0% | bar: 2024-06-22 to 2024-06-23
|  | CAP-CAM-SHAFT | [8 empty] | OTICS | 0% | bar: 2024-06-22 to 2024-06-23
|  | MP-COM 2 | [8 empty] | OTICS | 0% | bar: 2024-06-22 to 2024-06-23
|  | MP-COM 1 | [8 empty] | OTICS | 0% | bar: 2024-06-22 to 2024-06-23
|  | LG-GH2 | [8 empty] | OTICS | 0% | bar: 2024-06-22 to 2024-06-23
| 3 | Wiring RS485 Loop 1
|  | ACP-CT | [7 empty] | TEERADON,PHATTHADON | OTICS | 0% | bar: 2024-06-29 to 2024-06-30
|  | LP-F1 | [8 empty] | OTICS | 0% | bar: 2024-06-29 to 2024-06-30
|  | LG-GH1 | [8 empty] | OTICS | 0% | bar: 2024-06-29 to 2024-06-30
|  | LP-OF ( 2FL ) | [8 empty] | OTICS | 0% | bar: 2024-06-29 to 2024-06-30
|  | ACP-DF ( 2FL ) | [8 empty] | OTICS | 0% | bar: 2024-06-29 to 2024-06-30
|  | NR-ASSY | [8 empty] | OTICS | 0% | bar: 2024-06-29 to 2024-06-30
|  | NR-HOUSING | [8 empty] | OTICS | 0% | bar: 2024-06-29 to 2024-06-30
|  | ES01-ASSEMBLY | [8 empty] | OTICS | 0% | bar: 2024-06-29 to 2024-06-30
|  | DB1-HLA | [8 empty] | OTICS | 0% | bar: 2024-06-29 to 2024-06-30
|  | DB2-HLA | [8 empty] | OTICS | 0% | bar: 2024-06-29 to 2024-06-30
|  | DB3-HLA | [8 empty] | OTICS | 0% | bar: 2024-06-29 to 2024-06-30
|  | ACP-HLA1 | [8 empty] | OTICS | 0% | bar: 2024-06-29 to 2024-06-30
|  | MT-SHOP | [8 empty] | OTICS | 0% | bar: 2024-06-29 to 2024-06-30
|  | LP-F2 | [8 empty] | OTICS | 0% | bar: 2024-06-29 to 2024-06-30
| 4 | Wiring RS485 Loop 2
|  | MDB-1 | [7 empty] | TEERADON | OTICS | 0% | bar: 2024-07-07
|  | MDB-2 | [8 empty] | OTICS | 0% | bar: 2024-07-07
|  | LP-CT | [8 empty] | OTICS | 0% | bar: 2024-07-07
|  | ACP-CT | [8 empty] | OTICS | 0% | bar: 2024-07-07
|  | RO-WATER | [8 empty] | OTICS | 0% | bar: 2024-07-07
|  | BOSCH | [8 empty] | OTICS | 0% | bar: 2024-07-07
|  | NR-CAP | [8 empty] | OTICS | 0% | bar: 2024-07-07
|  | ES01-CUTTING | [8 empty] | OTICS | 0% | bar: 2024-07-07
|  | TSC-15 | [8 empty] | OTICS | 0% | bar: 2024-07-07
|  | RAA | [8 empty] | OTICS | 0% | bar: 2024-07-07
|  | HOLDER | [8 empty] | OTICS | 0% | bar: 2024-07-07
|  | CAP-CAM-SHAFT | [8 empty] | OTICS | 0% | bar: 2024-07-07
|  | MP-COM 2 | [8 empty] | OTICS | 0% | bar: 2024-07-07
|  | MP-COM 1 | [8 empty] | OTICS | 0% | bar: 2024-07-07
|  | LG-GH2 | [8 empty] | OTICS | 0% | bar: 2024-07-07
| 5 | Connect RS485 to Power meter Loop 1
|  | ACP-CT | [7 empty] | PHATTHADON | OTICS | 0% | bar: 2024-07-13 to 2024-07-14
|  | LP-F1 | [8 empty] | OTICS | 0% | bar: 2024-07-13 to 2024-07-14
|  | LG-GH1 | [8 empty] | OTICS | 0% | bar: 2024-07-13 to 2024-07-14
|  | LP-OF ( 2FL ) | [8 empty] | OTICS | 0% | bar: 2024-07-13 to 2024-07-14
|  | ACP-DF ( 2FL ) | [8 empty] | OTICS | 0% | bar: 2024-07-13 to 2024-07-14
|  | NR-ASSY | [8 empty] | OTICS | 0% | bar: 2024-07-13 to 2024-07-14
|  | NR-HOUSING | [8 empty] | OTICS | 0% | bar: 2024-07-13 to 2024-07-14
|  | ES01-ASSEMBLY | [8 empty] | OTICS | 0% | bar: 2024-07-13 to 2024-07-14
|  | DB1-HLA | [8 empty] | OTICS | 0% | bar: 2024-07-13 to 2024-07-14
|  | DB2-HLA | [8 empty] | OTICS | 0% | bar: 2024-07-13 to 2024-07-14
|  | DB3-HLA | [8 empty] | OTICS | 0% | bar: 2024-07-13 to 2024-07-14
|  | ACP-HLA1 | [8 empty] | OTICS | 0% | bar: 2024-07-13 to 2024-07-14
|  | MT-SHOP | [8 empty] | OTICS | 0% | bar: 2024-07-13 to 2024-07-14
|  | LP-F2 | [8 empty] | OTICS | 0% | bar: 2024-07-13 to 2024-07-14
| 6 | Connect RS485 to Power meter Loop 2
|  | MDB-1 | [8 empty] | OTICS | 0% | bar: 2024-07-13 to 2024-07-14
|  | MDB-2 | [8 empty] | OTICS | 0% | bar: 2024-07-13 to 2024-07-14
|  | LP-CT | [8 empty] | OTICS | 0% | bar: 2024-07-13 to 2024-07-14
|  | ACP-CT | [8 empty] | OTICS | 0% | bar: 2024-07-13 to 2024-07-14
|  | RO-WATER | [8 empty] | OTICS | 0% | bar: 2024-07-13 to 2024-07-14
|  | BOSCH | [8 empty] | OTICS | 0% | bar: 2024-07-13 to 2024-07-14
|  | NR-CAP | [8 empty] | OTICS | 0% | bar: 2024-07-13 to 2024-07-14
|  | ES01-CUTTING | [8 empty] | OTICS | 0% | bar: 2024-07-13 to 2024-07-14
|  | TSC-15 | [8 empty] | OTICS | 0% | bar: 2024-07-13 to 2024-07-14
|  | RAA | [8 empty] | OTICS | 0% | bar: 2024-07-13 to 2024-07-14
|  | HOLDER | [8 empty] | OTICS | 0% | bar: 2024-07-13 to 2024-07-14
|  | CAP-CAM-SHAFT | [8 empty] | OTICS | 0% | bar: 2024-07-13 to 2024-07-14
|  | MP-COM 2 | [8 empty] | OTICS | 0% | bar: 2024-07-13 to 2024-07-14
|  | MP-COM 1 | [8 empty] | OTICS | 0% | bar: 2024-07-13 to 2024-07-14
|  | LG-GH2 | [8 empty] | OTICS | 0% | bar: 2024-07-13 to 2024-07-14
| 7 | Communication test Power meter Loop 1
|  | ACP-CT | [7 empty] | NATTAPOL,TEERADON,PHATTHADON | OTICS | 0% | bar: 2024-07-21 to 2024-07-27
|  | LP-F1 | [8 empty] | OTICS | 0% | bar: 2024-07-21 to 2024-07-27
|  | LG-GH1 | [8 empty] | OTICS | 0% | bar: 2024-07-21 to 2024-07-27
|  | LP-OF ( 2FL ) | [8 empty] | OTICS | 0% | bar: 2024-07-21 to 2024-07-27
|  | ACP-DF ( 2FL ) | [8 empty] | OTICS | 0% | bar: 2024-07-21 to 2024-07-27
|  | NR-ASSY | [8 empty] | OTICS | 0% | bar: 2024-07-21 to 2024-07-27
|  | NR-HOUSING | [8 empty] | OTICS | 0% | bar: 2024-07-21 to 2024-07-27
|  | ES01-ASSEMBLY | [8 empty] | OTICS | 0% | bar: 2024-07-21 to 2024-07-27
|  | DB1-HLA | [8 empty] | OTICS | 0% | bar: 2024-07-21 to 2024-07-27
|  | DB2-HLA | [8 empty] | OTICS | 0% | bar: 2024-07-21 to 2024-07-27
|  | DB3-HLA | [8 empty] | OTICS | 0% | bar: 2024-07-21 to 2024-07-27
|  | ACP-HLA1 | [8 empty] | OTICS | 0% | bar: 2024-07-21 to 2024-07-27
|  | MT-SHOP | [8 empty] | OTICS | 0% | bar: 2024-07-21 to 2024-07-27
|  | LP-F2 | [8 empty] | OTICS | 0% | bar: 2024-07-21 to 2024-07-27
| 8 | Communication test Power meter Loop 2
|  | MDB-1 | [8 empty] | OTICS | 0% | bar: 2024-07-21 to 2024-07-27
|  | MDB-2 | [8 empty] | OTICS | 0% | bar: 2024-07-21 to 2024-07-27
|  | LP-CT | [8 empty] | OTICS | 0% | bar: 2024-07-21 to 2024-07-27
|  | ACP-CT | [8 empty] | OTICS | 0% | bar: 2024-07-21 to 2024-07-27
|  | RO-WATER | [8 empty] | OTICS | 0% | bar: 2024-07-21 to 2024-07-27
|  | BOSCH | [8 empty] | OTICS | 0% | bar: 2024-07-21 to 2024-07-27
|  | NR-CAP | [8 empty] | OTICS | 0% | bar: 2024-07-21 to 2024-07-27
|  | ES01-CUTTING | [8 empty] | OTICS | 0% | bar: 2024-07-21 to 2024-07-27
|  | TSC-15 | [8 empty] | OTICS | 0% | bar: 2024-07-21 to 2024-07-27
|  | RAA | [8 empty] | OTICS | 0% | bar: 2024-07-21 to 2024-07-27
|  | HOLDER | [8 empty] | OTICS | 0% | bar: 2024-07-21 to 2024-07-27
|  | CAP-CAM-SHAFT | [8 empty] | OTICS | 0% | bar: 2024-07-21 to 2024-07-27
|  | MP-COM 2 | [8 empty] | OTICS | 0% | bar: 2024-07-21 to 2024-07-27
|  | MP-COM 1 | [8 empty] | OTICS | 0% | bar: 2024-07-21 to 2024-07-27
|  | LG-GH2 | [8 empty] | OTICS | 0% | bar: 2024-07-21 to 2024-07-27
| 9 | Wiring lan and master box installation
|  | Wiring lan to from master box to server | [8 empty] | OTICS | 0% | bar: 2024-07-21 to 2024-07-27
|  | Master comtrol box installation | [8 empty] | OTICS | 0% | bar: 2024-07-21 to 2024-07-27
|  | Master comtrol box power on | [8 empty] | OTICS | 0% | bar: 2024-07-21 to 2024-07-27
|  | Communication test | [8 empty] | OTICS | 0% | bar: 2024-07-21 to 2024-07-27
Planned on June 18th