## Installation Main schedule
OUT OF SCHEDULE | Schedule installation DAIFUKU AREA 1 project
| No. | Description | [7 empty] | PIC |  | Progress (%) | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
[10 empty] | Main | Support | time axis 2024-05-02 to 2024-07-27
|  |  | 1 | 2 | 2 |  | Progress ahead of schedule |  | (Input Number "1")
|  |  |  | 2 | 2 |  | Progress as planned |  | (Input Number "2")
|  |  |  | 2 | 2 | 3 | Progress with scheduled delay |  | (Input Number "3")
|  |  |  | 2 | 4 |  | Progress with scheduled delay |  | (Input Number "4")
[10 empty] | Overall |  | 19%
| 1 | Hardware installation area 1 | [7 empty] | Tomas | DAIFUKU
|  | Camera Point 1 | [9 empty] | 38% | 2024-05-02: 2
|  | Camera Point 2 | [9 empty] | 38% | 2024-05-02: 2
|  | Camera Point 3 | [9 empty] | 38% | 2024-05-03: 2
|  | Camera Point 4 | [9 empty] | 38% | 2024-05-03: 2
|  | Camera Point 5 | [9 empty] | 38% | 2024-05-06: 2
|  | Camera Point 6 | [9 empty] | 38% | 2024-05-06: 2
|  | Camera Point 7 | [9 empty] | 38% | 2024-05-07: 2
|  | Camera Point 8 | [9 empty] | 38% | 2024-05-07: 2
|  | Camera Point 9 | [9 empty] | 38% | 2024-05-08: 2
|  | Camera Point 10 | [9 empty] | 38% | 2024-05-08: 2
|  | Camera Point 11 | [9 empty] | 38% | 2024-05-09: 2
|  | Camera Point 12 | [9 empty] | 38% | 2024-05-09: 2
|  | Camera Point 13 | [9 empty] | 38% | 2024-05-10: 2
|  | Camera Point 14 | [9 empty] | 38% | 2024-05-10: 2
| 2 | Sofeware setup area 1 | [7 empty] | Tomas | DAIFUKU
|  | Camera Point 1 | [9 empty] | 0% | bar: 2024-05-15
|  | Camera Point 2 | [9 empty] | 0% | bar: 2024-05-15
|  | Camera Point 3 | [9 empty] | 0% | bar: 2024-05-16
|  | Camera Point 4 | [9 empty] | 0% | bar: 2024-05-16
|  | Camera Point 5 | [9 empty] | 0% | bar: 2024-05-17
|  | Camera Point 6 | [9 empty] | 0% | bar: 2024-05-17
|  | Camera Point 7 | [9 empty] | 0% | bar: 2024-05-20
|  | Camera Point 8 | [9 empty] | 0% | bar: 2024-05-20
|  | Camera Point 9 | [9 empty] | 0% | bar: 2024-05-21
|  | Camera Point 10 | [9 empty] | 0% | bar: 2024-05-21
|  | Camera Point 11 | [9 empty] | 0% | bar: 2024-05-22
|  | Camera Point 12 | [9 empty] | 0% | bar: 2024-05-22
|  | Camera Point 13 | [9 empty] | 0% | bar: 2024-05-23
|  | Camera Point 14 | [9 empty] | 0% | bar: 2024-05-23
Planned on April 18th
Planned on June 20th

## Hardware schedule_point 1-7
OUT OF SCHEDULE | Schedule installation DAIFUKU AREA 1 project
| No. | Description | [8 empty] | PIC |  | Progress (%) | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
[11 empty] | Main | Support | time axis 2024-05-02 to 2024-07-27
|  |  |  | 1 | 2 | 2 |  | Progress ahead of schedule |  | (Input Number "1")
[5 empty] | 2 | 2 |  | Progress as planned |  | (Input Number "2")
[5 empty] | 2 | 2 | 3 | Progress with scheduled delay |  | (Input Number "3")
[5 empty] | 2 | 4 |  | Progress with scheduled delay |  | (Input Number "4")
[11 empty] | Overall |  | 38.1%
| 1 | Hardware installation area 1
| 1.1 |  | - Point 1 | [7 empty] | Tomas | DAIFUKU | 37.5%
|  |  |  | - Install Stand of Control box | [8 empty] | 100% | 2024-05-02: 2
|  |  |  | - Install control box | [8 empty] | 100% | 2024-05-02: 2
|  |  |  | - Install camera stand | [8 empty] | 100% | 2024-05-02: 2
|  |  |  | - Install camera | [8 empty] | 0% | bar: 2024-05-02
|  |  |  | - Camera position setup | [8 empty] | 0% | bar: 2024-05-02
|  |  |  | - Install Air Regulator + Air Nozzle + Setup | [8 empty] | 0% | bar: 2024-05-02
|  |  |  | - Wiring Power | [8 empty] | 0% | bar: 2024-05-15 to 2024-05-17
|  |  |  | - Wiring signal I/O | [8 empty] | 0% | bar: 2024-05-15 to 2024-05-17
| 1.2 |  | - Point 2 | [7 empty] | Tomas | DAIFUKU | 37.5%
|  |  |  | - Install Stand of Control box | [8 empty] | 100% | 2024-05-02: 2
|  |  |  | - Install control box | [8 empty] | 100% | 2024-05-02: 2
|  |  |  | - Install camera stand | [8 empty] | 100% | 2024-05-02: 2
|  |  |  | - Install camera | [8 empty] | 0% | bar: 2024-05-02
|  |  |  | - Camera position setup | [8 empty] | 0% | bar: 2024-05-02
|  |  |  | - Install Air Regulator + Air Nozzle + Setup | [8 empty] | 0% | bar: 2024-05-02
|  |  |  | - Wiring Power | [8 empty] | 0% | bar: 2024-05-15 to 2024-05-17
|  |  |  | - Wiring signal I/O | [8 empty] | 0% | bar: 2024-05-15 to 2024-05-17
| 1.3 |  | - Point 3 | [7 empty] | Tomas | DAIFUKU | 37.5%
|  |  |  | - Install Stand of Control box | [8 empty] | 100% | 2024-05-03: 2
|  |  |  | - Install control box | [8 empty] | 100% | 2024-05-03: 2
|  |  |  | - Install camera stand | [8 empty] | 100% | 2024-05-03: 2
|  |  |  | - Install camera | [8 empty] | 0% | bar: 2024-05-03
|  |  |  | - Camera position setup | [8 empty] | 0% | bar: 2024-05-03
|  |  |  | - Install Air Regulator + Air Nozzle + Setup | [8 empty] | 0% | bar: 2024-05-03
|  |  |  | - Wiring Power | [8 empty] | 0% | bar: 2024-05-15 to 2024-05-17
|  |  |  | - Wiring signal I/O | [8 empty] | 0% | bar: 2024-05-15 to 2024-05-17
| 1.4 |  | - Point 4 | [7 empty] | Tomas | DAIFUKU | 37.5%
|  |  |  | - Install Stand of Control box | [8 empty] | 100% | 2024-05-03: 2
|  |  |  | - Install control box | [8 empty] | 100% | 2024-05-03: 2
|  |  |  | - Install camera stand | [8 empty] | 100% | 2024-05-03: 2
|  |  |  | - Install camera | [8 empty] | 0% | bar: 2024-05-03
|  |  |  | - Camera position setup | [8 empty] | 0% | bar: 2024-05-03
|  |  |  | - Install Air Regulator + Air Nozzle + Setup | [8 empty] | 0% | bar: 2024-05-03
|  |  |  | - Wiring Power | [8 empty] | 0% | bar: 2024-05-15 to 2024-05-17
|  |  |  | - Wiring signal I/O | [8 empty] | 0% | bar: 2024-05-15 to 2024-05-17
| 1.5 |  | - Point 5 | [7 empty] | Tomas | DAIFUKU | 37.5%
|  |  |  | - Install Stand of Control box | [8 empty] | 100% | 2024-05-06: 2
|  |  |  | - Install control box | [8 empty] | 100% | 2024-05-06: 2
|  |  |  | - Install camera stand | [8 empty] | 100% | 2024-05-06: 2
|  |  |  | - Install camera | [8 empty] | 0% | bar: 2024-05-06
|  |  |  | - Camera position setup | [8 empty] | 0% | bar: 2024-05-06
|  |  |  | - Install Air Regulator + Air Nozzle + Setup | [8 empty] | 0% | bar: 2024-05-06
|  |  |  | - Wiring Power | [8 empty] | 0% | bar: 2024-05-15 to 2024-05-17
|  |  |  | - Wiring signal I/O | [8 empty] | 0% | bar: 2024-05-15 to 2024-05-17
| 1.6 |  | - Point 6 | [7 empty] | Tomas | DAIFUKU | 37.5%
|  |  |  | - Install Stand of Control box | [8 empty] | 100% | 2024-05-06: 2
|  |  |  | - Install control box | [8 empty] | 100% | 2024-05-06: 2
|  |  |  | - Install camera stand | [8 empty] | 100% | 2024-05-06: 2
|  |  |  | - Install camera | [8 empty] | 0% | bar: 2024-05-06
|  |  |  | - Camera position setup | [8 empty] | 0% | bar: 2024-05-06
|  |  |  | - Install Air Regulator + Air Nozzle + Setup | [8 empty] | 0% | bar: 2024-05-06
|  |  |  | - Wiring Power | [8 empty] | 0% | bar: 2024-05-15 to 2024-05-17
|  |  |  | - Wiring signal I/O | [8 empty] | 0% | bar: 2024-05-15 to 2024-05-17
| 1.7 |  | - Point 7 | [7 empty] | Tomas | DAIFUKU | 37.5%
|  |  |  | - Install Stand of Control box | [8 empty] | 100% | 2024-05-07: 2
|  |  |  | - Install control box | [8 empty] | 100% | 2024-05-07: 2
|  |  |  | - Install camera stand | [8 empty] | 100% | 2024-05-07: 2
|  |  |  | - Install camera | [8 empty] | 0% | bar: 2024-05-07
|  |  |  | - Camera position setup | [8 empty] | 0% | bar: 2024-05-07
|  |  |  | - Install Air Regulator + Air Nozzle + Setup | [8 empty] | 0% | bar: 2024-05-07
|  |  |  | - Wiring Power | [8 empty] | 0% | bar: 2024-05-15 to 2024-05-17
|  |  |  | - Wiring signal I/O | [8 empty] | 0% | bar: 2024-05-15 to 2024-05-17
Planned on April 18th
Planned on June 20th

## Hardware schedule_point 8-14
OUT OF SCHEDULE | Schedule installation DAIFUKU AREA 1 project
| No. | Description | [8 empty] | PIC |  | Progress (%) | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
[11 empty] | Main | Support | time axis 2024-05-02 to 2024-07-27
|  |  |  | 1 | 2 | 2 |  | Progress ahead of schedule |  | (Input Number "1")
[5 empty] | 2 | 2 |  | Progress as planned |  | (Input Number "2")
[5 empty] | 2 | 2 | 3 | Progress with scheduled delay |  | (Input Number "3")
[5 empty] | 2 | 4 |  | Progress with scheduled delay |  | (Input Number "4")
[11 empty] | Overall |  | 38.1%
| 1 | Hardware installation area 1
| 1.8 |  | - Point 8 | [7 empty] | Tomas | DAIFUKU | 37.5%
|  |  |  | - Install Stand of Control box | [8 empty] | 100% | 2024-05-07: 2
|  |  |  | - Install control box | [8 empty] | 100% | 2024-05-07: 2
|  |  |  | - Install camera stand | [8 empty] | 100% | 2024-05-07: 2
|  |  |  | - Install camera | [8 empty] | 0% | bar: 2024-05-07
|  |  |  | - Camera position setup | [8 empty] | 0% | bar: 2024-05-07
|  |  |  | - Install Air Regulator + Air Nozzle + Setup | [8 empty] | 0% | bar: 2024-05-07
|  |  |  | - Wiring Power | [8 empty] | 0% | bar: 2024-05-15 to 2024-05-17
|  |  |  | - Wiring signal I/O | [8 empty] | 0% | bar: 2024-05-15 to 2024-05-17
| 1.9 |  | - Point 9 | [7 empty] | Tomas | DAIFUKU | 37.5%
|  |  |  | - Install Stand of Control box | [8 empty] | 100% | 2024-05-08: 2
|  |  |  | - Install control box | [8 empty] | 100% | 2024-05-08: 2
|  |  |  | - Install camera stand | [8 empty] | 100% | 2024-05-08: 2
|  |  |  | - Install camera | [8 empty] | 0% | bar: 2024-05-08
|  |  |  | - Camera position setup | [8 empty] | 0% | bar: 2024-05-08
|  |  |  | - Install Air Regulator + Air Nozzle + Setup | [8 empty] | 0% | bar: 2024-05-08
|  |  |  | - Wiring Power | [8 empty] | 0% | bar: 2024-05-15 to 2024-05-17
|  |  |  | - Wiring signal I/O | [8 empty] | 0% | bar: 2024-05-15 to 2024-05-17
| 1.1 |  | - Point 10 | [7 empty] | Tomas | DAIFUKU | 37.5%
|  |  |  | - Install Stand of Control box | [8 empty] | 100% | 2024-05-08: 2
|  |  |  | - Install control box | [8 empty] | 100% | 2024-05-08: 2
|  |  |  | - Install camera stand | [8 empty] | 100% | 2024-05-08: 2
|  |  |  | - Install camera | [8 empty] | 0% | bar: 2024-05-08
|  |  |  | - Camera position setup | [8 empty] | 0% | bar: 2024-05-08
|  |  |  | - Install Air Regulator + Air Nozzle + Setup | [8 empty] | 0% | bar: 2024-05-08
|  |  |  | - Wiring Power | [8 empty] | 0% | bar: 2024-05-15 to 2024-05-17
|  |  |  | - Wiring signal I/O | [8 empty] | 0% | bar: 2024-05-15 to 2024-05-17
| 1.11 |  | - Point 11 | [7 empty] | Tomas | DAIFUKU | 37.5%
|  |  |  | - Install Stand of Control box | [8 empty] | 100% | 2024-05-09: 2
|  |  |  | - Install control box | [8 empty] | 100% | 2024-05-09: 2
|  |  |  | - Install camera stand | [8 empty] | 100% | 2024-05-09: 2
|  |  |  | - Install camera | [8 empty] | 0% | bar: 2024-05-09
|  |  |  | - Camera position setup | [8 empty] | 0% | bar: 2024-05-09
|  |  |  | - Install Air Regulator + Air Nozzle + Setup | [8 empty] | 0% | bar: 2024-05-09
|  |  |  | - Wiring Power | [8 empty] | 0% | bar: 2024-05-15 to 2024-05-17
|  |  |  | - Wiring signal I/O | [8 empty] | 0% | bar: 2024-05-15 to 2024-05-17
| 1.12 |  | - Point 12 | [7 empty] | Tomas | DAIFUKU | 37.5%
|  |  |  | - Install Stand of Control box | [8 empty] | 100% | 2024-05-09: 2
|  |  |  | - Install control box | [8 empty] | 100% | 2024-05-09: 2
|  |  |  | - Install camera stand | [8 empty] | 100% | 2024-05-09: 2
|  |  |  | - Install camera | [8 empty] | 0% | bar: 2024-05-09
|  |  |  | - Camera position setup | [8 empty] | 0% | bar: 2024-05-09
|  |  |  | - Install Air Regulator + Air Nozzle + Setup | [8 empty] | 0% | bar: 2024-05-09
|  |  |  | - Wiring Power | [8 empty] | 0% | bar: 2024-05-15 to 2024-05-17
|  |  |  | - Wiring signal I/O | [8 empty] | 0% | bar: 2024-05-15 to 2024-05-17
| 1.13 |  | - Point 13 | [7 empty] | Tomas | DAIFUKU | 37.5%
|  |  |  | - Install Stand of Control box | [8 empty] | 100% | 2024-05-10: 2
|  |  |  | - Install control box | [8 empty] | 100% | 2024-05-10: 2
|  |  |  | - Install camera stand | [8 empty] | 100% | 2024-05-10: 2
|  |  |  | - Install camera | [8 empty] | 0% | bar: 2024-05-10
|  |  |  | - Camera position setup | [8 empty] | 0% | bar: 2024-05-10
|  |  |  | - Install Air Regulator + Air Nozzle + Setup | [8 empty] | 0% | bar: 2024-05-10
|  |  |  | - Wiring Power | [8 empty] | 0% | bar: 2024-05-15 to 2024-05-17
|  |  |  | - Wiring signal I/O | [8 empty] | 0% | bar: 2024-05-15 to 2024-05-17
| 1.14 |  | - Point 14 | [7 empty] | Tomas | DAIFUKU | 37.5%
|  |  |  | - Install Stand of Control box | [8 empty] | 100% | 2024-05-10: 2
|  |  |  | - Install control box | [8 empty] | 100% | 2024-05-10: 2
|  |  |  | - Install camera stand | [8 empty] | 100% | 2024-05-10: 2
|  |  |  | - Install camera | [8 empty] | 0% | bar: 2024-05-10
|  |  |  | - Camera position setup | [8 empty] | 0% | bar: 2024-05-10
|  |  |  | - Install Air Regulator + Air Nozzle + Setup | [8 empty] | 0% | bar: 2024-05-10
|  |  |  | - Wiring Power | [8 empty] | 0% | bar: 2024-05-15 to 2024-05-17
|  |  |  | - Wiring signal I/O | [8 empty] | 0% | bar: 2024-05-15 to 2024-05-17
Planned on April 18th
Planned on June 20th

## Software schedule
OUT OF SCHEDULE | Schedule installation DAIFUKU AREA 1 project
| No. | Description | [8 empty] | PIC |  | Progress (%) | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
[11 empty] | Main | Support | time axis 2024-05-02 to 2024-07-27
|  |  |  | 1 | 2 | 2 |  | Progress ahead of schedule |  | (Input Number "1")
[5 empty] | 2 | 2 |  | Progress as planned |  | (Input Number "2")
[5 empty] | 2 | 2 | 3 | Progress with scheduled delay |  | (Input Number "3")
[5 empty] | 2 | 4 |  | Progress with scheduled delay |  | (Input Number "4")
[11 empty] | Overall |  | 0%
| 1 | Software setup on site area 1
| 1.1 |  | - Point 1 | [7 empty] | Tomas | DAIFUKU
|  |  |  | - Camera parameter setup ( *Request keyence support ) | [8 empty] | 0% | bar: 2024-05-15
|  |  |  | - Camera setup find tune ( *Request keyence support ) | [8 empty] | 0% | bar: 2024-05-15
|  |  |  | - Test camera running | [8 empty] | 0% | bar: 2024-05-15
|  |  |  | - Test communication send data | [8 empty] | 0% | bar: 2024-05-15
| 1.2 |  | - Point 2 | [7 empty] | Tomas | DAIFUKU
|  |  |  | - Camera parameter setup ( *Request keyence support ) | [8 empty] | 0% | bar: 2024-05-15
|  |  |  | - Camera setup find tune ( *Request keyence support ) | [8 empty] | 0% | bar: 2024-05-15
|  |  |  | - Test camera running | [8 empty] | 0% | bar: 2024-05-15
|  |  |  | - Test communication send data | [8 empty] | 0% | bar: 2024-05-15
| 1.3 |  | - Point 3 | [7 empty] | Tomas | DAIFUKU
|  |  |  | - Camera parameter setup ( *Request keyence support ) | [8 empty] | 0% | bar: 2024-05-16
|  |  |  | - Camera setup find tune ( *Request keyence support ) | [8 empty] | 0% | bar: 2024-05-16
|  |  |  | - Test camera running | [8 empty] | 0% | bar: 2024-05-16
|  |  |  | - Test communication send data | [8 empty] | 0% | bar: 2024-05-16
| 1.4 |  | - Point 4 | [7 empty] | Tomas | DAIFUKU
|  |  |  | - Camera parameter setup ( *Request keyence support ) | [8 empty] | 0% | bar: 2024-05-16
|  |  |  | - Camera setup find tune ( *Request keyence support ) | [8 empty] | 0% | bar: 2024-05-16
|  |  |  | - Test camera running | [8 empty] | 0% | bar: 2024-05-16
|  |  |  | - Test communication send data | [8 empty] | 0% | bar: 2024-05-16
| 1.5 |  | - Point 5 | [7 empty] | Tomas | DAIFUKU
|  |  |  | - Camera parameter setup ( *Request keyence support ) | [8 empty] | 0% | bar: 2024-05-17
|  |  |  | - Camera setup find tune ( *Request keyence support ) | [8 empty] | 0% | bar: 2024-05-17
|  |  |  | - Test camera running | [8 empty] | 0% | bar: 2024-05-17
|  |  |  | - Test communication send data | [8 empty] | 0% | bar: 2024-05-17
| 1.6 |  | - Point 6 | [7 empty] | Tomas | DAIFUKU
|  |  |  | - Camera parameter setup ( *Request keyence support ) | [8 empty] | 0% | bar: 2024-05-17
|  |  |  | - Camera setup find tune ( *Request keyence support ) | [8 empty] | 0% | bar: 2024-05-17
|  |  |  | - Test camera running | [8 empty] | 0% | bar: 2024-05-17
|  |  |  | - Test communication send data | [8 empty] | 0% | bar: 2024-05-17
| 1.7 |  | - Point 7 | [7 empty] | Tomas | DAIFUKU
|  |  |  | - Camera parameter setup ( *Request keyence support ) | [8 empty] | 0% | bar: 2024-05-20
|  |  |  | - Camera setup find tune ( *Request keyence support ) | [8 empty] | 0% | bar: 2024-05-20
|  |  |  | - Test camera running | [8 empty] | 0% | bar: 2024-05-20
|  |  |  | - Test communication send data | [8 empty] | 0% | bar: 2024-05-20
| 1.8 |  | - Point 8 | [7 empty] | Tomas | DAIFUKU
|  |  |  | - Camera parameter setup ( *Request keyence support ) | [8 empty] | 0% | bar: 2024-05-20
|  |  |  | - Camera setup find tune ( *Request keyence support ) | [8 empty] | 0% | bar: 2024-05-20
|  |  |  | - Test camera running | [8 empty] | 0% | bar: 2024-05-20
|  |  |  | - Test communication send data | [8 empty] | 0% | bar: 2024-05-20
| 1.9 |  | - Point 9 | [7 empty] | Tomas | DAIFUKU
|  |  |  | - Camera parameter setup ( *Request keyence support ) | [8 empty] | 0% | bar: 2024-05-21
|  |  |  | - Camera setup find tune ( *Request keyence support ) | [8 empty] | 0% | bar: 2024-05-21
|  |  |  | - Test camera running | [8 empty] | 0% | bar: 2024-05-21
|  |  |  | - Test communication send data | [8 empty] | 0% | bar: 2024-05-21
| 1.1 |  | - Point 10 | [7 empty] | Tomas | DAIFUKU
|  |  |  | - Camera parameter setup ( *Request keyence support ) | [8 empty] | 0% | bar: 2024-05-21
|  |  |  | - Camera setup find tune ( *Request keyence support ) | [8 empty] | 0% | bar: 2024-05-21
|  |  |  | - Test camera running | [8 empty] | 0% | bar: 2024-05-21
|  |  |  | - Test communication send data | [8 empty] | 0% | bar: 2024-05-21
| 1.11 |  | - Point 11 | [7 empty] | Tomas | DAIFUKU
|  |  |  | - Camera parameter setup ( *Request keyence support ) | [8 empty] | 0% | bar: 2024-05-22
|  |  |  | - Camera setup find tune ( *Request keyence support ) | [8 empty] | 0% | bar: 2024-05-22
|  |  |  | - Test camera running | [8 empty] | 0% | bar: 2024-05-22
|  |  |  | - Test communication send data | [8 empty] | 0% | bar: 2024-05-22
| 1.12 |  | - Point 12 | [7 empty] | Tomas | DAIFUKU
|  |  |  | - Camera parameter setup ( *Request keyence support ) | [8 empty] | 0% | bar: 2024-05-22
|  |  |  | - Camera setup find tune ( *Request keyence support ) | [8 empty] | 0% | bar: 2024-05-22
|  |  |  | - Test camera running | [8 empty] | 0% | bar: 2024-05-22
|  |  |  | - Test communication send data | [8 empty] | 0% | bar: 2024-05-22
| 1.13 |  | - Point 13 | [7 empty] | Tomas | DAIFUKU
|  |  |  | - Camera parameter setup ( *Request keyence support ) | [8 empty] | 0% | bar: 2024-05-23
|  |  |  | - Camera setup find tune ( *Request keyence support ) | [8 empty] | 0% | bar: 2024-05-23
|  |  |  | - Test camera running | [8 empty] | 0% | bar: 2024-05-23
|  |  |  | - Test communication send data | [8 empty] | 0% | bar: 2024-05-23
| 1.14 |  | - Point 14 | [7 empty] | Tomas | DAIFUKU
|  |  |  | - Camera parameter setup ( *Request keyence support ) | [8 empty] | 0% | bar: 2024-05-23
|  |  |  | - Camera setup find tune ( *Request keyence support ) | [8 empty] | 0% | bar: 2024-05-23
|  |  |  | - Test camera running | [8 empty] | 0% | bar: 2024-05-23
|  |  |  | - Test communication send data | [8 empty] | 0% | bar: 2024-05-23
Planned on April 18th
Planned on June 20th