## Slide 1: Infrastructure IoT project meeting Date : 06/06/24 Made for JATH
TOMAS TECH Co., Ltd.

## Slide 2
| Meeting agenda
Update progress work 01/06/24 – 02/06/24
Installation plan 09/06/24
Prepare installation 08/06/24

## Slide 3
| Installation plan 01/06/24

## Slide 4
| Installation plan 02/06/24

## Slide 5
| Power meter installation overall ( 27/05/24 )
100%
100%
95%
70%
75%
90%
100%

## Slide 6
| Power meter installation overall ( 02/06/24 – 03/06/24 )
100%
100%
95%
90%
90%
90%
100%

## Slide 7: Installation Plan 09/06/24 ( Shutdown plant )
TOMAS TECH Co., Ltd.

## Slide 8
Person in charge of infrastructure project Date : 09/06/24 working time 07:00 – 19:00
TOMAS TECH TEAM
CT Wiring and connect to power meter
Flow meter installation
[ Factory 2 ]
K.Santi Loop 6,MDB room
K.Nattapol
Team E
K.Konlawat ( Loop 2,3,4 )
Team A ( 4 Person )
Team B ( 4 Person )
Team C ( 4 Person )
Control master box installation
Chiller room
K.Nattapol
Team D

## Slide 9
Working area point 09/06/24

## Slide 10
| Prepare scaffolding before installation
Installation scaffolding
Generator for welding installation point
Generator for Lighting

## Slide 11
| Scaffolding dimension ( 3 Floor )
ระยะความสูงต่อ 1 ชั้น

## Slide 12
| Scaffolding request from

## Slide 13
| Master control box installation confrim

## Slide 14
Request and comment by JATH

## Slide 15
Thank you for join meeting
By TOMAS TECH TEAM