## Phase1
[Nidec Techno Motor (Thailand) Co.,Ltd] Project Schedule | [7 empty] | Copyright© TOMAS TECH CORPORATION. All rights reserved.
[Nidec Techno Motor (Thailand) Co.,Ltd]
| Project Start Date | 2024-09-16 |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Week 22 | [6 empty] | Week 23 | [6 empty] | Week 24 | [6 empty] | Week 25 | [6 empty] | Week 26 | [6 empty] | Week 27 | [6 empty] | Week 28 | [6 empty] | Week 29 | [6 empty] | Week 30 | [6 empty] | Week 31 | [6 empty] | Week 32 | [6 empty] | Week 33 | [6 empty] | Week 34 | [6 empty] | Week 35 | [6 empty] | Week 36 | [6 empty] | Week 37 | [6 empty] | Week 38 | [6 empty] | Week 39 | [6 empty] | Week 40 | [6 empty] | Week 41 | [6 empty] | Week 42 | [6 empty] | Week 43
| Project Lead | 2025-01-30 | [5 empty] | 2024-09-16 | [6 empty] | 2024-09-23 | [6 empty] | 2024-09-30 | [6 empty] | 2024-10-07 | [6 empty] | 2024-10-14 | [6 empty] | 2024-10-21 | [6 empty] | 2024-10-28 | [6 empty] | 2024-11-04 | [6 empty] | 2024-11-11 | [6 empty] | 2024-11-18 | [6 empty] | 2024-11-25 | [6 empty] | 2024-12-02 | [6 empty] | 2024-12-09 | [6 empty] | 2024-12-16 | [6 empty] | 2024-12-23 | [6 empty] | 2024-12-30 | [6 empty] | 2025-01-06 | [6 empty] | 2025-01-13 | [6 empty] | 2025-01-20 | [6 empty] | 2025-01-27 | [6 empty] | 2025-02-03 | [6 empty] | 2025-02-10 | [6 empty] | 2025-02-17 | [6 empty] | 2025-02-24 | [6 empty] | 2025-03-03 | [6 empty] | 2025-03-10 | [6 empty] | 2025-03-17 | [6 empty] | 2025-03-24 | [6 empty] | 2025-03-31 | [6 empty] | 2025-04-07 | [6 empty] | 2025-04-14 | [6 empty] | 2025-04-21 | [6 empty] | 2025-04-28 | [6 empty] | 2025-05-05 | [6 empty] | 2025-05-12 | [6 empty] | 2025-05-19 | [6 empty] | 2025-05-26 | [6 empty] | 2025-06-02 | [6 empty] | 2025-06-09 | [6 empty] | 2025-06-16 | [6 empty] | 2025-06-23 | [6 empty] | 2025-06-30 | [6 empty] | 2025-07-07
 | time axis 2024-09-16 to 2025-07-13
WBS | TASK | PIC | START | END | DAYS | % DONE | WORK DAYS | time axis 2024-09-16 to 2025-07-13
1 | Kick-off meeting |  |  | - |  |  | -
1.1 | Kick-off meeting after PO | NTMT/Tomas | 2024-09-18 | 2024-09-18 | 1 | 0% | 1
1.2 |  |  |  | - |  |  | -
1.3 |  |  |  | - |  |  | -
1.4 |  |  |  | - |  |  | -
2 | Software schedule |  |  | - |  |  | -
2.1 | Requirements confirmation | NTMT/Tomas | 2024-09-18 | 2024-10-17 | 30 | 0% | 22
2.2 | Data organization/confirmation | NTMT/Tomas | 2024-09-18 | 2024-10-17 | 30 | 0% | 22
2.3 | System Design | Tomas | 2024-10-01 | 2024-10-20 | 20 | 0% | 14
2.4 | Software development | Tomas | 2024-10-14 | 2024-12-22 | 70 | 0% | 50
2.5 | Software test | Tomas | 2024-12-01 | 2024-12-22 | 22 | 0% | 15
2.6 | [6 empty] | -
3 | Hardware schedule |  |  | - |  |  | -
3.1 | - | - | - | - | 0 | 0% | -
3.2 | - | - | - | - | 0 | 0% | -
3.3 | - | - | - | - | 0 | 0% | -
3.4 | - | - | - | - | 0 | 0% | -
3.5 | - | - | - | - | 0 | 0% | -
3.6 | - | - | - | - | 0 | 0% | -
3.7 | - | - | - | - | 0 | 0% | -
4 | Installation |  |  | - |  |  | -
4.1 | Software installation | NTMT/Tomas | 2024-12-23 | 2024-12-27 | 5 | 0% | 5
4.2 | Teaching for UT | NTMT/Tomas | 2024-12-23 | 2024-12-27 | 5 | 0% | 5
4.3 | User Testing & Trial | NTMT/Tomas | 2024-12-23 | 2024-12-27 | 5 | 0% | 5
4.4 | Supports user feedback | NTMT/Tomas | 2024-12-23 | 2024-12-27 | 5 | 0% | 5
4.5 | Teaching for Go live | NTMT/Tomas | 2024-12-23 | 2024-12-27 | 5 | 0% | 5
4.6 | Go live | NTMT/Tomas | 2024-12-27 | 2024-12-27 | 1 | 0% | 1
4.7 |  |  |  | - |  |  | -
4.8 | [6 empty] | -
TEMPLATE ROWS
See the Help worksheet to learn how to use these rows. You can hide these rows before printing.
1 | [ Level 1 Task or Phase ] |  |  | - |  |  | -
1.1 | . [ Level 2 Task ] |  |  | - |  |  | -
1.1.1 | . . [ Level 3 Task ] |  |  | - |  |  | -
1.1.1.1 | . . . [ Level 4 Task ] |  |  | - |  |  | -
► Watch How to Create a Gantt Chart in Excel
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.