## Summary
Project punch list TRS for Delta
Customer : Shodensha (Thailand) Co., Ltd.
Create:02-OCt-2023
Update:02-Oct-2023
No. | Date | Items | Fanction | Description | Correspondence | Capture | In charge | Finish Date |  | Status | UAT | Note
[8 empty] | Plan | Actual
1 | 2023-10-02 | Task | Master settings | If it sets an image as the master, the resolution will change. |  | 111 | Tomas |  |  | OK
2 | 2023-10-02 | Task | Master settings | The default on the file selection screen for master editing is "000 Working file". Is it possible to make it a "003 master file"? |  | 222 | Tomas |  |  | OK
3 | 2023-10-02 | Task | Master settings | Specifying an Excel form is optional. |  | 333 | Tomas |  |  | OK
4 | 2023-10-02 | Task | Master settings | When creating a new master, click Save to create a 000 working file. Must be create file 003 | "Working“ .000 “Completion“ .001 “Error“ .002 “Master file” 003 | 444 555 | Tomas |  |  | OK
5 | 2023-10-12 |  |  | Error message pop up when press delete key in master maintenance |  | 006
6 | 2023-10-12 |  |  | Could you set Auto fit setting for text? |  | 007
7 | 2023-10-12 |  |  | Error message pop up when press Save or Save as |  | 008
8 | 2023-10-12 |  |  | Image resolution problem has not fixed |  | 009
9
10
11
12
13
14 | [11 empty] | Change 600 to '60 * 60 * 4' in global_env.php at line DEFINE('MCACHE_EXPIRE', 60 * 60 * 4);
15 | [11 empty] | Not found an error.
16
17 | [11 empty] | The table header can be fixed but the vertical scrollbar must be moved to the end of rows.
18 | [11 empty] | It needs to update the reader_name allocated length(16 to 50) in SQL function getTraceabilityData, table tblTraceabilityData and tblTraceabilityDataHis.
19 | [11 empty] | It isn't used and able to remove.
20 | [11 empty] | It has been already show the big letters.
21
22 | [11 empty] | Read_time is already updated but I modified the updateAfter trigger to update the RegDate. It needs to be update the trigger on customer site.
23 | [11 empty] | Improved log pattern.Add Log level INFO, DEBUG, WARN, ERROR
24 | [11 empty] | Need to update new function getTraceabilityData and new web file.
25
26
27 | [11 empty] | Records should be 2 for addition 1 process adding.
28 | [11 empty] | Casting app has been updated.
29 | [11 empty] | It will update the Read_Time and RegDate for exists data.
30
31
32 | [11 empty] | I can't reproduce the case referred to sheet 16 but I found something mistake in SQL function when try to run the deep test that might be result the problem. It has to be updated the SQL function and retest on production site again.
33
34
35
36
37
38
38
38
39
40
Note on F42: [スレッド化されたコメント] 使用している Excel のバージョンでは、このスレッド化されたコメントを表示できますが、新しいバージョンの Excel でファイルを開いた場合はコメントに対する編集がすべて削除されます。詳細: https://go.microsoft.com/fwlink/?linkid=870924 コメント: SELECT * FROM tblTraceabilityData WHERE serial_no = '1634260323162519' INSERT INTO tblReaderMst (Reader_No, Process_No, Line_No, Packing_Pcs, Reader_Name, Company_code, Records, Process1, Process2, Process3, Process4, Process5) VALUES (52,12,1,0,'V-16','1',1,'','','','','') INSERT INTO tblTraceabilityData ( Reader_No, Serial_No, Read_Time, Data1, Data2, LeakTest_Code ) SELECT 1, '1634260323162519', '2023-03-28 08:44:02', '', '', '' UNION SELECT 2, '1634260323162519', '2023-03-30 08:44:09', '', '', '' UNION SELECT 4, '1634260323162519', '2023-03-30 08:54:12', '', '', '' UNION SELECT 5, '1634260323162519', '2023-03-30 09:20:49', '+006.5', '1', 'R0012701322F23085A4807038001' UNION SELECT 52, '1634260323162519', '2023-03-27 20:42:34', '', '', ''