## MAST-PD
Group NO | Group | Sub-Task | Item No | Device | Function | Expected result | Actual result | Status | Date | Tester | Approval | Remark
1 | Login | - | 1.1 | Web | Production Login | The users in the DC, PO, and PA departments can log in to the system using the following credentials: Username: Full Name Password: 1234 |  | OK | 2025-01-31 | Puk
2 | Login | Visibility of data | 2.1 | Web | The visibility of data for the Production | After logging in, users in the DC, PO, and PA departments will see the main menu of the system as follows: 1. Dashboard 2. Schedule PD 3. Inbound PD 4. Outbound PD 5. Stock Management 6. Master Management |  | OK | 2025-01-31 | Puk
3 | Schedule PD | Inbound Schedule | 3.1 | Web | Search | Can search for Inbound data based on the following conditions: Supplier – Search by the supplier' code. Rank – Filter the data by rank or priority level. Date – Search based on a specific date or date range. Status – Filter by the status of the Inbound process (e.g., Schedule Register, Completed, etc.). |  | OK | 2025-01-31 | Puk
|  |  | 3.2 | Web | Create | Users can manually add a schedule in the system by clicking the "Create" button |  | OK | 2025-01-31 | Puk
|  |  | 3.3 | Web | Export CSV | The data displayed in the DataTable can be exported as a CSV file based on the search conditions applied |  | OK | 2025-01-31 | Puk
|  |  | 3.4 | Web | Update Status Cancel | Schedules that are canceled will be displayed with a red highlight on the item |  | OK | 2025-01-31 | Puk
|  |  | 3.5 | Web | Update Status Reactivate | Schedules can be used again and don't displayed with a red highlight on the item |  | OK | 2025-01-31 | Puk
|  |  | 3.6 | Web | Update Status Complate | Schedules that are Complete will be displayed with a green highlight on the item |  | OK | 2025-01-31 | Puk
|  | Inbound Schedule Detail | 3.7 | Web | Search | Can search for Inbound data based on the following conditions: Supplier – Search by the supplier' code. Rank – Filter the data by rank or priority level. Inbound Date – Search based on a specific date or date range. Delivery Date – Search based on a specific date or date range. Status – Filter by the status of the Inbound process (e.g., Schedule Register, Completed, etc.). Linkage Status – (Not applicable, Not linked, etc.). |  | OK | 2025-01-31 | Puk
|  |  | 3.8 | Web | Export CSV | The data displayed in the DataTable can be exported as a CSV file based on the search conditions applied |  | OK | 2025-01-31 | Puk
|  |  | 3.9 | Web | Resend | Update the Linkage Status again in the ExportInboundDPP table |  | OK | 2025-01-31 | Puk
|  | Outbound Schedule | 3.10 | Web | Search | Can search for Inbound data based on the following conditions: Rank – Filter the data by rank or priority level. Date – Search based on a specific date or date range. Status – Filter by the status of the Inbound process (e.g., Schedule Register, Completed, etc.). |  | OK | 2025-01-31 | Puk
|  |  | 3.11 | Web | Create | Users can manually add a schedule in the system by clicking the "Create" button |  | OK | 2025-01-31 | Puk
|  |  | 3.12 | Web | Export CSV | The data displayed in the DataTable can be exported as a CSV file based on the search conditions applied |  | OK | 2025-01-31 | Puk
|  |  | 3.13 | Web | Update Status Cancel | Schedules that are canceled will be displayed with a red highlight on the item |  | OK | 2025-01-31 | Puk
|  |  | 3.14 | Web | Update Status Reactivate | Schedules can be used again and don't displayed with a red highlight on the item |  | OK | 2025-01-31 | Puk
|  |  | 3.15 | Web | Update Status Complate | Schedules that are Complete will be displayed with a green highlight on the item |  | OK | 2025-01-31 | Puk
|  | Outbound Schedule Detail | 3.16 | Web | Search | Can search for Inbound data based on the following conditions: Rank – Filter the data by rank or priority level. Inbound Date – Search based on a specific date or date range. Delivery Date – Search based on a specific date or date range. Status – Filter by the status of the Inbound process (e.g., Schedule Register, Completed, etc.). Linkage Status – (Not applicable, Not linked, etc.). |  | OK | 2025-01-31 | Puk
|  |  | 3.17 | Web | Export CSV | The data displayed in the DataTable can be exported as a CSV file based on the search conditions applied |  | OK | 2025-01-31 | Puk
|  |  | 3.18 | Web | Resend | Update the Linkage Status again in the ExportInboundDPP table |  | OK | 2025-01-31 | Puk
4 | Inbound PD | Inbound Inquiry / Report | 4.1 | Web | Search | Data can be searched using Supplier, Rank, Inbound Date and displays the results in a DataTable |  | OK | 2025-01-31 | Puk
|  |  | 4.2 | Web | Export CSV | The data displayed in the DataTable can be exported as a CSV file based on the search conditions applied |  | OK | 2025-01-31 | Puk
|  |  | 4.3 | Web | Export PDF | The data displayed in the DataTable can be exported as a PDF file based on the search conditions applied |  | OK | 2025-01-31 | Puk
5 | Outbound PD | Outbound Inquiry / Report | 5.1 | Web | Search | Data can be searched using Outbound Date, Rank and displays the results in a DataTable |  | OK | 2025-01-31 | Puk
|  |  | 5.2 | Web | Export CSV | The data displayed in the DataTable can be exported as a CSV file based on the search conditions applied |  | OK | 2025-01-31 | Puk
|  |  | 5.3 | Web | Export PDF | The data displayed in the DataTable can be exported as a PDF file based on the search conditions applied |  | OK | 2025-01-31 | Puk
6 | Stock Management | Stock Inquiry / Report | 6.1 | Web | Search | Data can be searched using Part No and Location Code and displays the results in a DataTable |  | OK | 2025-01-31 | Puk
|  |  | 6.2 | Web | Export CSV | The data displayed in the DataTable can be exported as a CSV file based on the search conditions applied |  | OK | 2025-01-31 | Puk
|  |  | 6.3 | Web | Export PDF | The data displayed in the DataTable can be exported as a PDF file based on the search conditions applied |  | OK | 2025-01-31 | Puk
|  | Stock Maintenance | 6.4 | Web | Search | Data can be searched using Item Code and Location Code and displays the results in a DataTable |  | OK | 2025-01-31 | Puk
|  |  | 6.5 | Database | Search | The data displayed in the DataTable on the view page is sourced from the table "StockDPP" |  | OK | 2025-01-31 | Puk
|  |  | 6.6 | Web | Add | Product information, including quantity and location, can be added to the system |  | OK | 2025-01-31 | Puk
|  |  | 6.7 | Web | Remove Zero Qty | The system will delete data under the condition that Stock Qty = 0 If the deletion is successful, an alert will be displayed: "Zero quantity rows have been removed successfully" |  | OK | 2025-01-31 | Puk
|  |  | 6.8 | Web | Update | After entering the desired quantity in the "Stock Quantity" column and clicking "Update," the system will update the data based on the entered quantity |  | OK | 2025-01-31 | Puk
|  | Stocktaking | 6.9 | Web | Search | Data can be searched using Year, Month, Item Code, Location and displays the results in a DataTable when there is Stocktaking data in the system. |  | OK | 2025-01-31 | Puk
|  |  | 6.10 | Web | Start | Stocktaking data will be added to the system by selecting records from LabelStatus with statuses 2 or 5, which have not yet been recorded in the Stocktaking |  | OK | 2025-01-31 | Puk
|  |  | 6.11 | Web | Record the stock count | The counted quantity can be recorded in the system |  | OK | 2025-01-31 | Puk
|  |  | 6.12 | Web | Update Status Recheck | Update the status of the selected items to "Recheck" |  | OK | 2025-01-31 | Puk
|  |  | 6.13 | Web | Update Status Confirm | Update the status of the selected items to "Confirm" |  | OK | 2025-01-31 | Puk
|  |  | 6.14 | Web | Delete | Data can be deleted from the system, and once deleted, it will no longer be visible |  | OK | 2025-01-31 | Puk
|  |  | 6.15 | Web | Export CSV | The data displayed in the DataTable can be exported as a CSV file based on the search conditions applied |  | OK | 2025-01-31 | Puk
|  | Stock Maintenance Inquiry / Report | 6.16 | Web | Search | Data can be searched using Part No, Section, Date and displays the results in a DataTable |  | OK | 2025-01-31 | Puk
|  |  | 6.17 | Web | Export CSV | The data displayed in the DataTable can be exported as a CSV file based on the search conditions applied |  | OK | 2025-01-31 | Puk
|  |  | 6.18 | Web | Export PDF | The data displayed in the DataTable can be exported as a PDF file based on the search conditions applied |  | OK | 2025-01-31 | Puk
|  | Inventory Linkage | 6.19 | Web | Search | Data can be searched using Warehouse 1, Lot No, Part No, Location ID, Linkage Status and displays the results in a DataTable |  | OK | 2025-01-31 | Puk
|  |  | 6.20 | Web | Export CSV | The data displayed in the DataTable can be exported as a CSV file based on the search conditions applied |  | OK | 2025-01-31 | Puk
|  |  | 6.21 | Web | Resend | Set the status_export to 0 in the ExportInventory table. |  | OK | 2025-01-31 | Puk
|  | Tag Label | 6.22 | Web | Search | Data can be searched using Year, Month, Lot No, Part no, Location, Status and displays the results in a DataTable |  | OK | 2025-01-31 | Puk
|  |  | 6.23 | Web | Export CSV | The data displayed in the DataTable can be exported as a CSV file based on the search conditions applied |  | OK | 2025-01-31 | Puk
|  |  | 6.24 | Web | Update Status Confirm | The labels that have been updated and confirmed will have the status "PRINTED" |  | OK | 2025-01-31 | Puk
|  |  | 6.25 | Web | Delete | Data can be deleted from the system, and once deleted, it will no longer be visible |  | OK | 2025-01-31 | Puk
|  |  | 6.26 | Web | Tag Generator | If the department is DC, when generating the tag, additional information such as Model, Color, Machine No, Shift, and OK/NG will be included, and the generated tag will appear as shown in the image | #VALUE! | OK | 2025-01-31 | Puk
|  |  | 6.27 | Web | Import CSV File for print Label | Import a CSV file to generate labels in the system and print them After uploading the CSV file, the system will display the Model to confirm the data before generating the labels |  | OK | 2025-01-31 | Puk
|  |  | 6.28 | Web | Reprint | Display the labels that need to be reprinted and allow printing of the labels |  | OK | 2025-01-31 | Puk
|  | NG Inquiry / Report | 6.29 | Web | Search | Data can be searched using Item Code, Date and displays the results in a DataTable |  | OK | 2025-01-31 | Puk
|  |  | 6.30 | Web | Export CSV | The data displayed in the DataTable can be exported as a CSV file based on the search conditions applied |  | OK | 2025-01-31 | Puk
|  |  | 6.31 | Web | Export PDF | The data displayed in the DataTable can be exported as a PDF file based on the search conditions applied |  | OK | 2025-01-31 | Puk
|  | Traceability Report | 6.32 | Web | Search | Data can be searched using Item Code and displays the results in a DataTable |  | OK | 2025-01-31 | Puk
|  |  | 6.33 | Web | Export CSV | The data displayed in the DataTable can be exported as a CSV file based on the search conditions applied |  | OK | 2025-01-31 | Puk
|  |  | 6.34 | Web | Export PDF | The data displayed in the DataTable can be exported as a PDF file based on the search conditions applied |  | OK | 2025-01-31 | Puk
|  | Change Location | 6.35 | Web | Search | Data can be searched using Item Code, Location and displays the results in a DataTable |  | OK | 2025-01-31 | Puk
|  |  | 6.36 | Web | Export CSV | The data displayed in the DataTable can be exported as a CSV file based on the search conditions applied |  | OK | 2025-01-31 | Puk
|  |  | 6.37 | Web | Change Location | If the location is moved, for example, from Part: AA Location: 01 Qty: 500, and AA is moved to Location: 02 with a quantity of 150, then Location: 01 will have 350 remaining, and Location: 02 will have 150 |  | OK | 2025-01-31 | Puk
7 | Master Management | MRP Factory master | 7.1 | Web | Search | The MRP Factory Master allows users to search for data based on conditions such as Factory Code and Customer Code, and displays the results in a DataTable |  | OK | 2025-01-31 | Puk
|  |  | 7.2 | Database | Search | The data displayed in the DataTable on the view page is sourced from the table "ImportMRPfactoryDPP" |  | OK | 2025-01-31 | Puk
|  |  | 7.3 | Web | Export CSV | The data displayed in the DataTable can be exported as a CSV file based on the search conditions applied |  | OK | 2025-01-31 | Puk
|  |  | 7.4 | Web | Import CSV | Data can be imported into the system in CSV format, following the same table header structure as the exported CSV file |  | OK | 2025-01-31 | Puk
|  |  | 7.5 | Web | Delete | Data can be deleted from the system, and once deleted, it will no longer be visible |  | OK | 2025-01-31 | Puk
|  | Supplier Master | 7.6 | Web | Search | The Supplier Master allows users to search for data based on conditions such as Supplier Code and displays the results in a DataTable |  | OK | 2025-01-31 | Puk
|  |  | 7.7 | Database | Search | The data displayed in the DataTable on the view page is sourced from the table "SupplierDPP" |  | OK | 2025-01-31 | Puk
|  |  | 7.8 | Web | Export CSV | The data displayed in the DataTable can be exported as a CSV file based on the search conditions applied |  | OK | 2025-01-31 | Puk
|  |  | 7.9 | Web | Import CSV | Data can be imported into the system in CSV format, following the same table header structure as the exported CSV file |  | OK | 2025-01-31 | Puk
|  |  | 7.10 | Web | Delete | Data can be deleted from the system, and once deleted, it will no longer be visible |  | OK | 2025-01-31 | Puk
|  |  | 7.11 | Web | Create Manual | Suppliers can be added to the system, and the Supplier Code must be unique for each Department If the Supplier Code is already in use, an error message will be displayed in red: "This Supplier code is already in use" |  | OK | 2025-01-31 | Puk
|  | Supplier Master Information | 7.12 | Web | Search | The Supplier Master Information allows users to search for data based on conditions such as Customer Code, Supplier Code and displays the results in a DataTable |  | OK | 2025-01-31 | Puk
|  |  | 7.13 | Database | Search | The data displayed in the DataTable on the view page is sourced from the table "ImportSupplierDPP" |  | OK | 2025-01-31 | Puk
|  |  | 7.14 | Web | Export CSV | The data displayed in the DataTable can be exported as a CSV file based on the search conditions applied |  | OK | 2025-01-31 | Puk
|  |  | 7.15 | Web | Import CSV | Data can be imported into the system in CSV format, following the same table header structure as the exported CSV file |  | OK | 2025-01-31 | Puk
|  |  | 7.16 | Web | Delete | Data can be deleted from the system, and once deleted, it will no longer be visible |  | OK | 2025-01-31 | Puk
|  | Department Master | 7.17 | Web | Search | The Department Master allows users to search for data based on conditions such as Department Name and displays the results in a DataTable |  | OK | 2025-01-31 | Puk
|  |  | 7.18 | Web | Export CSV | The data displayed in the DataTable can be exported as a CSV file based on the search conditions applied |  | OK | 2025-01-31 | Puk
|  |  | 7.19 | Web | Import CSV | Data can be imported into the system in CSV format, following the same table header structure as the exported CSV file |  | OK | 2025-01-31 | Puk
|  |  | 7.20 | Web | Delete | Data can be deleted from the system, and once deleted, it will no longer be visible |  | OK | 2025-01-31 | Puk
|  |  | 7.21 | Web | Create Manual | Department can be added to the system, and the Department Code must be unique If the Department Code is already in use, an error message will be displayed in red: "This Department code is already in use" |  | OK | 2025-01-31 | Puk
|  | Item Master Information | 7.22 | Web | Search | The Item Master Information allows users to search for data based on conditions such as Parts No, HL DWG No and displays the results in a DataTable |  | OK | 2025-01-31 | Puk
|  |  | 7.23 | Database | Search | The data displayed in the DataTable on the view page is sourced from the table "ImportItemDPP" |  | OK | 2025-01-31 | Puk
|  |  | 7.24 | Web | Export CSV | The data displayed in the DataTable can be exported as a CSV file based on the search conditions applied |  | OK | 2025-01-31 | Puk
|  |  | 7.25 | Web | Import CSV | Data can be imported into the system in CSV format, following the same table header structure as the exported CSV file |  | OK | 2025-01-31 | Puk
|  |  | 7.26 | Web | Delete | Data can be deleted from the system, and once deleted, it will no longer be visible |  | OK | 2025-01-31 | Puk
|  | Item Master | 7.27 | Web | Search | The Item Master allows users to search for data based on conditions such as Item Code, Supplier Name and displays the results in a DataTable |  | OK | 2025-01-31 | Puk
|  |  | 7.28 | Database | Search | The data displayed in the DataTable on the view page is sourced from the table "ItemDPP" |  | OK | 2025-01-31 | Puk
|  |  | 7.29 | Web | Export CSV | The data displayed in the DataTable can be exported as a CSV file based on the search conditions applied |  | OK | 2025-01-31 | Puk
|  |  | 7.30 | Web | Import CSV | Data can be imported into the system in CSV format, following the same table header structure as the exported CSV file |  | OK | 2025-01-31 | Puk
|  |  | 7.31 | Web | Delete | Data can be deleted from the system, and once deleted, it will no longer be visible |  | OK | 2025-01-31 | Puk
|  |  | 7.32 | Web | Create Manual | Items can be added to the system, and the Item code must be unique for each Department If the Item code is already in use, an error message will be displayed in red: "This Item code is already in use" |  | OK | 2025-01-31 | Puk
|  | Bucket Quantity | 7.33 | Web | Search | The Bucket Quantity allows users to search for data based on conditions such as Parts No and displays the results in a DataTable |  | OK | 2025-01-31 | Puk
|  |  | 7.34 | Database | Search | The data displayed in the DataTable on the view page is sourced from the table "ImportBucketQuantityDPP" |  | OK | 2025-01-31 | Puk
|  |  | 7.35 | Web | Export CSV | The data displayed in the DataTable can be exported as a CSV file based on the search conditions applied |  | OK | 2025-01-31 | Puk
|  |  | 7.36 | Web | Import CSV | Data can be imported into the system in CSV format, following the same table header structure as the exported CSV file |  | OK | 2025-01-31 | Puk
|  |  | 7.37 | Web | Delete | Data can be deleted from the system, and once deleted, it will no longer be visible |  | OK | 2025-01-31 | Puk
|  | Packing Standard | 7.38 | Web | Search | The Packing Standard allows users to search for data based on conditions such as Item Code, Package, Unit and displays the results in a DataTable |  | OK | 2025-01-31 | Puk
|  |  | 7.39 | Database | Search | The data displayed in the DataTable on the view page is sourced from the table "PackingStandardDPP" |  | OK | 2025-01-31 | Puk
|  |  | 7.40 | Web | Export CSV | The data displayed in the DataTable can be exported as a CSV file based on the search conditions applied |  | OK | 2025-01-31 | Puk
|  |  | 7.41 | Web | Import CSV | Data can be imported into the system in CSV format, following the same table header structure as the exported CSV file |  | OK | 2025-01-31 | Puk
|  |  | 7.42 | Web | Delete | Data can be deleted from the system, and once deleted, it will no longer be visible |  | OK | 2025-01-31 | Puk
|  |  | 7.43 | Web | Create Manual | Packing Standard can be added to the system |  | OK | 2025-01-31 | Puk
|  | Location Master | 7.44 | Web | Search | The Location Master allows users to search for data based on conditions such as Location Code, Factory Code and displays the results in a DataTable |  | OK | 2025-01-31 | Puk
|  |  | 7.45 | Database | Search | The data displayed in the DataTable on the view page is sourced from the table "LocationDPP" |  | OK | 2025-01-31 | Puk
|  |  | 7.46 | Web | Export CSV | The data displayed in the DataTable can be exported as a CSV file based on the search conditions applied |  | OK | 2025-01-31 | Puk
|  |  | 7.47 | Web | Import CSV | Data can be imported into the system in CSV format, following the same table header structure as the exported CSV file |  | OK | 2025-01-31 | Puk
|  |  | 7.48 | Web | Delete | Data can be deleted from the system, and once deleted, it will no longer be visible |  | OK | 2025-01-31 | Puk
|  |  | 7.49 | Web | Create Manual | Locations can be added to the system, and the Location code must be unique for each Department If the Location code is already in use, an error message will be displayed in red: "This location code is already in use" |  | OK | 2025-01-31 | Puk
|  | User Master | 7.50 | Web | Search | The User Master allows users to search for data based on conditions such as User Code and displays the results in a DataTable |  | OK | 2025-01-31 | Puk
|  |  | 7.51 | Web | Export CSV | The data displayed in the DataTable can be exported as a CSV file based on the search conditions applied |  | OK | 2025-01-31 | Puk
|  |  | 7.52 | Web | Import CSV | Data can be imported into the system in CSV format, following the same table header structure as the exported CSV file |  | OK | 2025-01-31 | Puk
|  |  | 7.53 | Web | Delete | Data can be deleted from the system, and once deleted, it will no longer be visible |  | OK | 2025-01-31 | Puk
|  |  | 7.54 | Web | Create Manual | User can be added to the system and it is not possible to add a new record to the User Master if the User Code already exists. |  | OK | 2025-01-31 | Puk
|  | User Credential | 7.55 | Web | Search | The User Credential allows users to search for data based on conditions such as User Code and displays the results in a DataTable |  | OK | 2025-01-31 | Puk
|  |  | 7.56 | Web | Export CSV | The data displayed in the DataTable can be exported as a CSV file based on the search conditions applied |  | OK | 2025-01-31 | Puk
|  |  | 7.57 | Web | Import CSV | Data can be imported into the system in CSV format, following the same table header structure as the exported CSV file |  | OK | 2025-01-31 | Puk
|  |  | 7.58 | Web | Delete | Data can be deleted from the system, and once deleted, it will no longer be visible |  | OK | 2025-01-31 | Puk
|  |  | 7.59 | Web | Create Manual | User Credential can be added to the system, and the User Code must be unique If the User Code is already in use, an error message will be displayed in red: "This User code is already in use" |  | OK | 2025-01-31 | Puk
|  | Name Master | 7.60 | Web | Search | The Name Master allows users to search for data based on conditions such as Name Code and displays the results in a DataTable |  | OK | 2025-01-31 | Puk
|  |  | 7.61 | Web | Export CSV | The data displayed in the DataTable can be exported as a CSV file based on the search conditions applied |  | OK | 2025-01-31 | Puk
|  |  | 7.62 | Web | Import CSV | Data can be imported into the system in CSV format, following the same table header structure as the exported CSV file |  | OK | 2025-01-31 | Puk
|  |  | 7.63 | Web | Delete | Data can be deleted from the system, and once deleted, it will no longer be visible |  | OK | 2025-01-31 | Puk
|  |  | 7.64 | Web | Create Manual | Name Master can be added to the system |  | OK | 2025-01-31 | Puk
|  | Authority Master | 7.65 | Web | Search | The Authority Master allows users to search for data based on conditions such as Authority Code and displays the results in a DataTable |  | OK | 2025-01-31 | Puk
|  |  | 7.66 | Web | Export CSV | The data displayed in the DataTable can be exported as a CSV file based on the search conditions applied |  | OK | 2025-01-31 | Puk
|  |  | 7.67 | Web | Import CSV | Data can be imported into the system in CSV format, following the same table header structure as the exported CSV file |  | OK | 2025-01-31 | Puk
|  |  | 7.68 | Web | Delete | Data can be deleted from the system, and once deleted, it will no longer be visible |  | OK | 2025-01-31 | Puk
|  |  | 7.69 | Web | Create Manual | Authority Master can be added to the system |  | OK | 2025-01-31 | Puk
|  | NG Reason master | 7.70 | Web | Search | The NG Reason master allows users to search for data based on conditions such as Process Code and displays the results in a DataTable |  | OK | 2025-01-31 | Puk
|  |  | 7.71 | Web | Export CSV | The data displayed in the DataTable can be exported as a CSV file based on the search conditions applied |  | OK | 2025-01-31 | Puk
|  |  | 7.72 | Web | Import CSV | Data can be imported into the system in CSV format, following the same table header structure as the exported CSV file |  | OK | 2025-01-31 | Puk
|  |  | 7.73 | Web | Delete | Data can be deleted from the system, and once deleted, it will no longer be visible |  | OK | 2025-01-31 | Puk
|  |  | 7.74 | Web | Create Manual | NG Reason master can be added to the system |  | OK | 2025-01-31 | Puk
|  | Process Master | 7.75 | Web | Search | The Process Master allows users to search for data based on conditions such as Process Code and displays the results in a DataTable |  | OK | 2025-01-31 | Puk
|  |  | 7.76 | Web | Export CSV | The data displayed in the DataTable can be exported as a CSV file based on the search conditions applied |  | OK | 2025-01-31 | Puk
|  |  | 7.77 | Web | Import CSV | Data can be imported into the system in CSV format, following the same table header structure as the exported CSV file |  | OK | 2025-01-31 | Puk
|  |  | 7.78 | Web | Delete | Data can be deleted from the system, and once deleted, it will no longer be visible |  | OK | 2025-01-31 | Puk
|  |  | 7.79 | Web | Create Manual | Process Master can be added to the system |  | OK | 2025-01-31 | Puk
|  | Label setting | 7.80 | Web | Search | The Label setting allows users to search for data based on conditions such as Function ID and displays the results in a DataTable |  | OK | 2025-01-31 | Puk
|  |  | 7.81 | Web | Export CSV | The data displayed in the DataTable can be exported as a CSV file based on the search conditions applied |  | OK | 2025-01-31 | Puk
|  |  | 7.82 | Web | Import CSV | Data can be imported into the system in CSV format, following the same table header structure as the exported CSV file |  | OK | 2025-01-31 | Puk
|  |  | 7.83 | Web | Delete | Data can be deleted from the system, and once deleted, it will no longer be visible |  | OK | 2025-01-31 | Puk
|  |  | 7.84 | Web | Create Manual | Label setting can be added to the system |  | OK | 2025-01-31 | Puk

## MAST-Handy
Group NO | Group | Sub-Task | Item No | Device | Function | Expected result | Actual result | Status | Date | Tester | Approval | Remark
1 | Login | - | 1.1 | Handy | Production Login | The users in the DC, PO, and PA departments can log in to the system using the following credentials: Username: Full Name Password: 1234 |  | OK | 2025-01-31
2 | Login | Visibility of data | 2.1 | Handy | The visibility of data for the Production | After logging in, users in the DC, PO, and PA departments will see the main menu of the system as follows: 1. Inbound 2. Inventory Fluctuation 3. Outbound 4. Stock Management 5. Printer Setting |  | OK | 2025-01-31
3 | Inbound | Label Manual | 3.1 | Handy | Label Manual | Can search for Inbound data based on the following conditions: Part No - Able to search by scrolling, typing or scan QR code(normal label) or barcode (only part no). Actual total Qty - Specify the quantity to create a label Confirm - Send data label to printer Clear- Clear data on screen |  | OK | 2025-01-31
|  |  | 3.2 | Handy | Relabeling | Can search for Inbound data based on the following conditions: Part No - Scan barcode (The part details will be displayed after scanning the barcode) Outbound qty - Specify the quantity to be removed from stock Confirm - Auto create NG label and new Stock label Clear- Clear data on screen |  | OK | 2025-01-31
|  |  | 3.3 | Handy | Re-Print Label | Can search for Inbound data based on the following conditions: Part No - Scan barcode (The part details will be displayed after scanning the barcode) Confirm - Send data label to printer Clear- Clear data on screen |  | OK | 2025-01-31
|  | Inbound Manual | 3.4 | Handy | Add the items to stock | Can search for Inbound data based on the following conditions: Part No - Scan barcode (The part details will be displayed after scanning the barcode) The part details will be listed in the table, including the quantity based on the scanned label. Photo matching - Click part no(Camara image) show screen Image part Location - Able to search by scrolling, typing or scan QR code(normal label) or barcode (only location). Confirm - Save data to Inbound table Clear- Clear data on screen |  | OK | 2025-01-31
4 |  | Inventory Fluctuation | 4.1 | Handy | Tranfer in process | Can search for Inbound data based on the following conditions: Part No - Scan barcode (The part details will be displayed after scanning the barcode) The part details will be listed in the table, including the quantity based on the scanned label. Location - Able to search by scrolling, typing or scan QR code(normal label) or barcode (only location). Confirm - Save data to Outbound,Inboud table Clear- Clear data on screen |  | OK | 2025-01-31
|  |  | 4.2 | Handy | NG Manual | Can search for Inbound data based on the following conditions: Part No - Scan barcode (The part details will be displayed after scanning the barcode) The part details will be listed in the table, including the quantity based on the scanned label. Photo matching - Click part no(Camara image) show screen Image part Button Add - show popup Add Ng Data (Reason,Process,Qty) Confirm - Save data and Export to AS-400 Clear- Clear data on screen"
5 | Outbound PD | Work Outbound | 5.1 | Handy | Show Items Order No | Show the list from the current day to the next seven days. |  | OK | 2025-01-31
|  |  | 5.1.1 | Handy | Show Detail Order No | -Show the list of lotno, location, and quantity in stock for all items in the part 1.) check duplicate scan label 2.) check lot no (fifo) 3.) check repack qty 4.) check qty label with order qty Confirm - Save data to Outbound (Inbound when case repack) Clear- Clear data on screen"
|  | Production Outbound | 5.2 | Handy | Show Items Order No | Show the list from the current day to the next seven days. |  | OK | 2025-01-31
|  |  | 5.2.1 | Handy | Show Detail Order No | -Show the list of lotno, location, and quantity in stock for all items in the part 1.) check duplicate scan label 2.) check lot no (fifo) 3.) check repack qty 4.) check qty label with order qty Confirm - Save data to Outbound (Inbound when case repack) Clear- Clear data on screen"
|  | Outbound Manual | 5.3 | Handy | Scan | Can search for Inbound data based on the following conditions: Part No - Able to search by scrolling, typing or scan QR code(normal label) or barcode (only part no). Confirm - Save data to Outbound Clear- Clear data on screen |  | OK | 2025-01-31
6 | Stock Management | Stock Check | 6.1 | Handy | Search | Data can be searched using Part No and Location Code and displays the results in a Table |  | OK | 2025-01-31
|  | StockTaking | 6.2 | Handy | Search/Scan part | -Can search for Location based on the following conditions: Location No - Scan barcode (The location will be displayed after scanning the barcode) Part No - Scan barcode (The part will be displayed after scanning the barcode) The part information will only display items that are in that location Confirm - Save data to Table StockTaking Clear- Clear data on screen" |  | OK | 2025-01-31
|  | Change Location | 6.2 | Handy | Scan | -First time Scan part for move location -Second time Scan part for confirm Qty -Enter information new locationConfirm -Save data to Tablet Outbound and Inbound new location data -Clear- Clear data on screen"
7 | Printer Setting |  | 7.1 | Handy | scan | Scan qrcode for Printer name connettion |  | OK | 2025-01-31

## Mast-Linkage
Group NO | Group | Sub-Task | Item No | Device | Function | Expected result | Actual result | Status | Date | Tester | Approval | Remark
1 | Import | Item master | 1.1 | Window Application | Import file FCT82T_yyyyMMddHHmmss.csv | Conducted from Monday to Saturday from 6:00 to 23:30 (Creation process executed once every 60 seconds) |  | OK | 2025-01-31
|  | Delivery information | 1.2 | Window Application | Import file FCT86T_yyyyMMddHHmmss.csv | Conducted from Monday to Saturday from 6:00 to 23:30 (Creation process executed once every 60 seconds) |  | OK | 2025-01-31
|  | Process master | 1.3 | Window Application | Import file FCT87T_yyyyMMddHHmmss.csv | Conducted from Monday to Saturday from 6:00 to 23:30 (Creation process executed once every 60 seconds) |  | OK | 2025-01-31
|  | NG Reason master | 1.4 | Window Application | Import file FCT88T_yyyyMMddHHmmss.csv | Conducted from Monday to Saturday from 6:00 to 23:30 (Creation process executed once every 60 seconds) |  | OK | 2025-01-31
2 | Export | Inbound Information | 2.1 | Window Application | Export file FCT93yyyyMMddHHmm.csv | Conducted from Monday to Saturday from 6:00 to 23:30 (Creation process executed once every 60 seconds) |  | OK | 2025-01-31
|  | Outbound Information | 2.2 | Window Application | Export file FCT94yyyyMMddHHmm.csv | Conducted from Monday to Saturday from 6:00 to 23:30 (Creation process executed once every 60 seconds) |  | OK | 2025-01-31
|  | Inventory information | 2.3 | Window Application | Export file FCT95yyyyMMddHHmm.csv | Conducted from Monday to Saturday at 21:00 (Import process executed once per day) |  | OK | 2025-01-31
|  | NG information | 2.4 | Window Application | Export file FCT96yyyyMMddHHmm.csv | Conducted from Monday to Saturday from 6:00 to 23:30 (Creation process executed once every 60 seconds) |  | OK | 2025-01-31