## Master
[Thai Inaba Foods Co.,Ltd.] Project Schedule | [8 empty] | Copyright© TOMAS TECH CORPORATION. All rights reserved.
[Thai Inaba Foods Co.,Ltd.]
| Project Start Date | 2025-03-10 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Week 22 | [6 empty] | Week 23 | [6 empty] | Week 24 | [6 empty] | Week 25 | [6 empty] | Week 26 | [6 empty] | Week 27 | [6 empty] | Week 28 | [6 empty] | Week 29 | [6 empty] | Week 30 | [6 empty] | Week 31 | [6 empty] | Week 32 | [6 empty] | Week 33 | [6 empty] | Week 34 | [6 empty] | Week 35 | [6 empty] | Week 36 | [6 empty] | Week 37 | [6 empty] | Week 38 | [6 empty] | Week 39 | [6 empty] | Week 40 | [6 empty] | Week 41 | [6 empty] | Week 42 | [6 empty] | Week 43
| Project Lead | 2025-11-30 | [6 empty] | 2025-03-10 | [6 empty] | 2025-03-17 | [6 empty] | 2025-03-24 | [6 empty] | 2025-03-31 | [6 empty] | 2025-04-07 | [6 empty] | 2025-04-14 | [6 empty] | 2025-04-21 | [6 empty] | 2025-04-28 | [6 empty] | 2025-05-05 | [6 empty] | 2025-05-12 | [6 empty] | 2025-05-19 | [6 empty] | 2025-05-26 | [6 empty] | 2025-06-02 | [6 empty] | 2025-06-09 | [6 empty] | 2025-06-16 | [6 empty] | 2025-06-23 | [6 empty] | 2025-06-30 | [6 empty] | 2025-07-07 | [6 empty] | 2025-07-14 | [6 empty] | 2025-07-21 | [6 empty] | 2025-07-28 | [6 empty] | 2025-08-04 | [6 empty] | 2025-08-11 | [6 empty] | 2025-08-18 | [6 empty] | 2025-08-25 | [6 empty] | 2025-09-01 | [6 empty] | 2025-09-08 | [6 empty] | 2025-09-15 | [6 empty] | 2025-09-22 | [6 empty] | 2025-09-29 | [6 empty] | 2025-10-06 | [6 empty] | 2025-10-13 | [6 empty] | 2025-10-20 | [6 empty] | 2025-10-27 | [6 empty] | 2025-11-03 | [6 empty] | 2025-11-10 | [6 empty] | 2025-11-17 | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08 | [6 empty] | 2025-12-15 | [6 empty] | 2025-12-22 | [6 empty] | 2025-12-29
 | time axis 2025-03-10 to 2026-01-04
WBS | TASK | PIC | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2025-03-10 to 2026-01-04
1 | Kick-off meeting |  |  |  | - |  |  | -
1.1 | Kick-off meeting after PO | Inaba/Tomas |  | 2025-03-10 | 2025-03-10 | 1 | 100% | 1
2 | Software schedule |  |  |  | - |  |  | -
2.1 | Requirements confirmation | Inaba/Tomas |  | 2025-03-10 | 2025-06-17 | 100 | 100% | 72
2.2 | Data organization/confirmation | Inaba |  | 2025-03-10 | 2025-06-17 | 100 | 100% | 72
2.3 | System Design | Tomas |  | 2025-03-20 | 2025-06-12 | 85 | 100% | 61
2.4 | Software development | Tomas |  | 2025-04-26 | 2025-09-27 | 155 | 88% | 110
2.5 | Software test | Tomas |  | 2025-08-13 | 2025-09-27 | 46 | 59% | 33
2.6 | Internal final test | Tomas |  | 2025-08-13 | 2025-09-27 | 46 | 59% | 33
2.7 | [7 empty] | -
3 | Hardware schedule |  |  |  | - |  |  | -
3.1 | Requirements confirmation | Inaba |  | 2025-03-10 | 2025-03-10 |  | 100% | 1
3.2 | System Design | Inaba |  | 2025-03-10 | 2025-03-10 |  | 100% | 1
3.3 | Hardware procurement | Inaba |  | 2025-03-10 | 2025-03-10 |  | 100% | 1
4 | Installation |  |  |  | - |  |  | -
4.1 | Software installation | Tomas |  | 2025-08-13 | 2025-09-27 | 46 | 59% | 33
4.2 | Hardware installation | Inaba |  | 2025-03-10 | 2025-03-10 | 1 | 100% | 1
4.3 | Teaching for UT | Inaba/Tomas |  | 2025-09-13 | 2025-11-01 | 50 | 0% | 35
4.4 | User Testing & Trial | Inaba/Tomas |  | 2025-09-13 | 2025-11-01 | 50 | 0% | 35
4.5 | Supports user feedback | Inaba/Tomas |  | 2025-09-13 | 2025-11-01 | 50 | 0% | 35
4.6 | Teaching for Go live | Inaba/Tomas |  | 2025-10-26 | 2025-11-01 | 7 | 0% | 5
4.7 | Go live | Inaba/Tomas |  | 2025-11-03 | 2025-11-03 | 1 | 0% | 1
TEMPLATE ROWS
See the Help worksheet to learn how to use these rows. You can hide these rows before printing.
1 | [ Level 1 Task or Phase ] |  |  |  | - |  |  | -
1.1 | . [ Level 2 Task ] |  |  |  | - |  |  | -
1.1.1 | . . [ Level 3 Task ] |  |  |  | - |  |  | -
1.1.1.1 | . . . [ Level 4 Task ] |  |  |  | - |  |  | -
► Watch How to Create a Gantt Chart in Excel
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.

## Dev Task list
[Thai Inaba Foods Co.,Ltd.] Project Schedule
[Thai Inaba Foods Co.,Ltd.]
| Project Start Date | 2025-03-10 |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Week 22 | [6 empty] | Week 23 |  |  |  | Week 23.5714285714286 | [6 empty] | Week 24.5714285714286 | [6 empty] | Week 25.5714285714286 | [6 empty] | Week 26.5714285714286 | [6 empty] | Week 27.5714285714286 | [6 empty] | Week 28.5714285714286 |  |  |  | Week 29.1428571428571 | [6 empty] | Week 30.1428571428571 | [6 empty] | Week 31.1428571428571
| Project Lead | 2025-11-30 | [5 empty] | 2025-03-10 | [6 empty] | 2025-03-17 | [6 empty] | 2025-03-24 | [6 empty] | 2025-03-31 | [6 empty] | 2025-04-07 | [6 empty] | 2025-04-14 | [6 empty] | 2025-04-21 | [6 empty] | 2025-04-28 | [6 empty] | 2025-05-05 | [6 empty] | 2025-05-12 | [6 empty] | 2025-05-19 | [6 empty] | 2025-05-26 | [6 empty] | 2025-06-02 | [6 empty] | 2025-06-09 | [6 empty] | 2025-06-16 | [6 empty] | 2025-06-23 | [6 empty] | 2025-06-30 | [6 empty] | 2025-07-07 | [6 empty] | 2025-07-14 | [6 empty] | 2025-07-21 | [6 empty] | 2025-07-28 | [6 empty] | 2025-08-04 | [6 empty] | 2025-08-11 |  |  |  | 2025-08-15 | [6 empty] | 2025-08-22 | [6 empty] | 2025-08-29 | [6 empty] | 2025-09-05 | [6 empty] | 2025-09-12 | [6 empty] | 2025-09-19 |  |  |  | 2025-09-23 | [6 empty] | 2025-09-30 | [6 empty] | 2025-10-07
 | time axis 2025-03-10 to 2025-10-19
WBS | TASK | PIC | START | END | DAYS | % DONE | WORK DAYS | time axis 2025-03-10 to 2025-10-19
1 | Software Task schedule |  |  | - |  |  | -
1.1 | System Design | Tomas
1.1.1 | Web application function | Anek | 2025-03-20 | 2025-06-12 | 85 | 100% | 61
1.1.3 | Handy terminal application function | Anek | 2025-03-20 | 2025-06-12 | 85 | 100% | 61
1.2 | Software development | Tomas
1.2.1 | Development standard writing | Pai | 2025-06-01 | 2025-06-12 | 12 | 100% | 9
1.3 | Handy terminal application | Tomas | 2025-04-26 | 2025-09-27 | 155 | 75% | 110
1.3.1 | Android Handy terminal User Login | Pai |  |  |  | 100% | -
1.3.2 | Main Menu | Pai |  |  |  | 100% | -
1.3.3 | Handy terminal function Inbound | Pai |  |  |  | 100% | -
1.3.4 | Inbound Menu | Pai |  |  |  | 100% | -
1.3.5 | Package Inbound Schedule (PO) | Pai |  |  |  | 100% | -
1.3.6 | Package Inbound Schedule (PO) – Inbound Detail | Pai |  |  |  | 100% | -
1.3.7 | Before Retord Semi Inbound Schedule (Production plan) | Pai |  |  |  | 80%
1.3.8 | After Retord Semi Inbound Schedule (Production plan) – Inbound Detail | Pai |  |  |  | 80%
1.3.9 | Semi Outbound (Packing plan) | Pai |  |  |  | 15% | -
1.3.10 | Inbound Manual | Pai |  |  |  | 80% | -
1.3.11 | FG Inbound Schedule (Packing Paln) | Pai |  |  |  | 90% | -
1.3.12 | QC Check Hold | Pai |  |  |  | 10% | -
1.3.13 | Outbound Menu | Pai |  |  |  | 10% | -
1.3.14 | Outbound Schedule Semi ( Packing paln) | Pai |  |  |  | 10% | -
1.3.15 | QC Check Random | Pai |  |  |  | 10% | -
1.3.16 | Paln load Order , Delivery | Pai |  |  |  | 10% | -
1.3.17 | Outbound Manual | Pai |  |  |  | 75% | -
1.3.18 | Stock management Menu | Pai |  |  |  | 75% | -
1.3.19 | Stock Check | Pai |  |  |  | 75% | -
1.3.20 | Stock Counting | Pai |  |  |  | 75% | -
1.3.21 | Change Location Pallet , Basket , Location | Pai |  |  |  | 75% | -
1.3.22 | Transfer | Pai |  |  |  | 10% | -
1.4 | PC Web application | Tomas | 2025-04-26 | 2025-09-27 | 155 | 75% | 110
1.4.1 | Login Menu | Puk |  |  |  | 100% | -
1.4.2 | Main Menu | Puk |  |  |  | 90% | -
1.4.3 | Schedule – Import | Puk |  |  |  | 90% | -
1.4.4 | Schedule – Import Status | Puk |  |  |  | 95% | -
1.4.5 | Schedule - Inbound Packaging ( PO ) | Puk |  |  |  | 95% | -
1.4.6 | Schedule - Inbound FG ( Packing plan) | Puk |  |  |  | 10% | -
1.4.7 | Schedule - Inbound Semi (Pd) | Puk |  |  |  | 80% | -
1.4.8 | Schedule - Inbound Schedule Detail | Puk |  |  |  | 80% | -
1.4.9 | Schedule - Plan load Group LOT | Puk |  |  |  | 10% | -
1.4.10 | Schedule – Outbound Semi (Packing plan) | Puk |  |  |  | 0% | -
1.4.11 | Schedule – Outbound Delivery ( Plan load ) | Puk |  |  |  | 0% | -
1.4.12 | Schedule – Transfer | Puk |  |  |  | 0% | -
1.4.13 | Schedule – Outbound Schedule Details | Puk |  |  |  | 0% | -
1.4.14 | Inbound Inquiry / Detail | Puk |  |  |  | 50% | -
1.4.15 | Outbound inquiry / Detail | Puk |  |  |  | 50% | -
1.4.16 | Stock Inquiry Report | Puk |  |  |  | 75% | -
1.4.17 | Stock Maintenance | Puk |  |  |  | 75% | -
1.4.18 | Stock Counting | Puk |  |  |  | 75% | -
1.4.19 | Stock Maintenance Inquiry / Report | Puk |  |  |  | 0% | -
1.4.20 | Label Creations | Puk |  |  |  | 0% | -
1.4.21 | Master data | Puk |  |  |  | 50% | -
1.5 | AS/RS intrigration development | Tomas
1.5.1 | Storage Plan | Puk | 2025-09-03 | 2025-10-02 | 30 | 0% | 22
1.5.3 | Storage Plan response | Puk |  |  |  | 0% | -
1.5.4 | Retrieval Paln | Puk |  |  |  | 0% | -
1.5.5 | Retrieval Paln response | Puk |  |  |  | 0% | -
2.1 | Software test | Tomas
2.1.1 | Dev/Testing system install, system install | Puk | 2025-08-13 | 2025-09-27 | 46 | 46% | 33
2.1.2 | Internal Final Test | Puk | 2025-08-13 | 2025-09-27 | 46 | 46% | 33
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on E7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on F7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on G7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on H7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.

## Internal And UAT Testing Plan
[Thai Inaba Foods Co.,Ltd.] Project Schedule
[Thai Inaba Foods Co.,Ltd.]
| Project Start Date | 2025-08-04 |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Week 22 | [6 empty] | Week 23 |  |  |  | Week 23.5714285714286 | [6 empty] | Week 24.5714285714286 | [6 empty] | Week 25.5714285714286 | [6 empty] | Week 26.5714285714286 | [6 empty] | Week 27.5714285714286 | [6 empty] | Week 28.5714285714286
| Project Lead | 2025-09-30 | [5 empty] | 2025-08-04 | [6 empty] | 2025-08-11 | [6 empty] | 2025-08-18 | [6 empty] | 2025-08-25 | [6 empty] | 2025-09-01 | [6 empty] | 2025-09-08 | [6 empty] | 2025-09-15 | [6 empty] | 2025-09-22 | [6 empty] | 2025-09-29 | [6 empty] | 2025-10-06 | [6 empty] | 2025-10-13 | [6 empty] | 2025-10-20 | [6 empty] | 2025-10-27 | [6 empty] | 2025-11-03 | [6 empty] | 2025-11-10 | [6 empty] | 2025-11-17 | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08 | [6 empty] | 2025-12-15 | [6 empty] | 2025-12-22 | [6 empty] | 2025-12-29 | [6 empty] | 2026-01-05 |  |  |  | 2026-01-09 | [6 empty] | 2026-01-16 | [6 empty] | 2026-01-23 | [6 empty] | 2026-01-30 | [6 empty] | 2026-02-06 | [6 empty] | 2026-02-13
Yellow | = Remark : Testing day | time axis 2025-08-04 to 2026-02-16
WBS | TASK | PIC | START | END | DAYS | % DONE | WORK DAYS | time axis 2025-08-04 to 2026-02-16
1 | Internal Testing Plan |  | 2025-08-13 | 2025-09-27 | 46 | 60% | 33
1.1 | Packaging inbound | Tomas | 2025-08-21 | 2025-08-21 | 1 | 100% | 1 | bar: 2025-08-21
1.1.1 | Purchase order plan preparation ( PO) | [5 empty] | - | bar: 2025-08-21
1.1.2 | Packaging Receiving Inbound | [5 empty] | -
1.2 | Production outbound after Retort | Tomas | 2025-08-21 | 2025-08-28 | 8 | 100% | 6
1.2.1 | Production plan preparation ( PD) | [5 empty] | - | bar: 2025-08-21
1.2.2 | Semi Before Retord | [5 empty] | -
1.2.2 | Semi Receiving Inbound After Retord | [5 empty] | - | bar: 2025-08-28
1.3 | FG Inbound | Tomas | 2025-08-28 | 2025-09-04 | 8 | 100% | 6
1.3.1 | Loading Plan preparation (Planload Delivery ) | bar: 2025-08-29
1.3.2 | FG Receive Inbound
1.4 | FG Outbound Delivery | Tomas | 2025-09-11 | 2025-09-18 | 8 | 0% | 6
1.1.10 | Loading Plan preparation ( PO) | [5 empty] | - | bar: 2025-09-11
1.1.11 | FG Picking Outbound ( Transfer FG) | [5 empty] | -
1.5 | Packing process | Tomas | 2025-09-04 | 2025-09-18 | 15 | 30% | 11
1.5.1 | Loading Plan preparation ( PO) | [5 empty] | - | bar: 2025-09-04; 2025-09-11; 2025-09-18
1.5.2 | Packing Plan preparation ( PP) | [5 empty] | -
1.5.3 | Semi Picking Outbound TO Packing Process | [5 empty] | -
1.6 | Transfer / Return | Tomas | 2025-09-18 | 2025-09-24 | 7 | 0% | 5
1.6.1 | Transfer Preparation | [5 empty] | - | bar: 2025-09-18
1.6.2 | Transfer Process | [5 empty] | -
1.6.3 | Return Process | [5 empty] | -
1.7 | QC Process | Tomas | 2025-09-18 | 2025-09-24 | 7 | 0% | 5
1.7.1 | Lab-QC Inspection | [5 empty] | - | bar: 2025-09-18
1.7.2 | Qc Semi Inspection
1.7.3 | QC Checking
1.7.4 | FG-QC Inspection
1.7.5 | Re-checking plan preparation
1.8 | AS/RS intrigration development | Tomas | 2025-09-03 | 2025-09-27 | 25 | 20% | 18
1.8.1 | Storage Plan | Tomas | bar: 2025-09-03; 2025-09-10; 2025-09-17; 2025-09-24
1.8.2 | Storage Plan response | AS/RS
1.8.3 | Retrieval Paln | Tomas
1.8.4 | Retrieval Paln response | AS/RS
1.9 | Simple Inbound | Tomas | 2025-09-18 | 2025-09-24 | 7 | 0% | 5
1.9.1 | Simple Outbound | bar: 2025-09-18
1.9.2 | Stock Counting (Semi /FG)
1.9.3 | Change location
2 | UAT Testing Plan | Inaba/Tomas | 2025-09-13 | 2025-11-01 | 50 | 0% | 35
2.1 | Packaging Process | Inaba/Tomas | 2025-09-13 | 2025-09-22 | 10 | 0% | 6
Purchase order plan preparation ( PO)
Packaging Receiving Inbound
2.2 | Production Befor/After Retort | Inaba/Tomas | 2025-09-23 | 2025-10-02 | 10 | 0% | 8
Production plan preparation ( PD)
Semi Receiving Inbound
Lab-QC Inspection
Qc Semi Inspection
QC Checking
2.3 | Packing plan process | Inaba/Tomas | 2025-10-03 | 2025-10-12 | 10 | 0% | 6
Loading Plan preparation ( PO)
Packing Plan preparation ( PP)
Semi Picking Outbound TO Packing Process
2.4 | FG Inbound Process | Inaba/Tomas | 2025-10-13 | 2025-10-22 | 10 | 0% | 8
FG Receive Inbound
Re-checking plan preparation
FG-QC Inspection
2.5 | Tranfer Process | Inaba/Tomas | 2025-10-23 | 2025-11-01 | 10 | 0% | 7
Transfer Preparation
Transfer Process
Return Process
2.6 | Delivery Process | Inaba/Tomas | 2025-10-23 | 2025-11-01 | 10 | 0% | 7
Loading Plan preparation (Planload Delivery )
FG Picking Outbound ( Transfer FG)
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on E7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on F7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on G7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on H7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.