## GanttChart
[WMS Phase2 for YAMATO] Project Schedule | [8 empty] | Copyright© TOMAS TECH CORPORATION. All rights reserved.
[Yamato Co., Ltd.]
| Project Start Date | 2025-05-09 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20
| Project Lead | [7 empty] | 2025-05-05 | [6 empty] | 2025-05-12 | [6 empty] | 2025-05-19 | [6 empty] | 2025-05-26 | [6 empty] | 2025-06-02 | [6 empty] | 2025-06-09 | [6 empty] | 2025-06-16 | [6 empty] | 2025-06-23 | [6 empty] | 2025-06-30 | [6 empty] | 2025-07-07 | [6 empty] | 2025-07-14 | [6 empty] | 2025-07-21 | [6 empty] | 2025-07-28 | [6 empty] | 2025-08-04 | [6 empty] | 2025-08-11 | [6 empty] | 2025-08-18 | [6 empty] | 2025-08-25 | [6 empty] | 2025-09-01 | [6 empty] | 2025-09-08 | [6 empty] | 2025-09-15
 | time axis 2025-05-05 to 2025-09-21
WBS | TASK | PIC | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2025-05-05 to 2025-09-21
1 | Kick-off meeting |  |  |  | - |  |  | -
1.1 | Kick-off meeting | /Tomas |  |  | - |  |  | -
1.2 |  |  |  |  | - |  |  | -
1.3 |  |  |  |  | - |  |  | -
1.4 |  |  |  |  | - |  |  | -
2 | Software schedule |  |  |  | - |  |  | -
2.1 | Requirements confirmation | /Tomas |  | 2025-05-09 | 2025-06-30 | 53 | 100% | 37
2.2 | System Design | /Tomas |  | 2025-05-12 | 2025-06-30 | 50 | 100% | 36
2.3 | Software development (Handy) | Soraya
| -Inbound Material - WH |  |  | 2025-07-16 | 2025-07-18 | 3 | 100% | 3
| -Confirm material before production |  |  | 2025-08-18 | 2025-08-20 | 3 | 100% | 5
| -Inbound FG - Assy |  |  | 2025-08-25 | 2025-08-29 | 5 | 100% | 5
| -Mix material |  |  | 2025-09-02 | 2025-09-03 | 2 | 100% | 2
| -Inbound WIP - Inj & Press |  |  | 2025-09-04 | 2025-09-08 | 5 | 100% | 5
| -Outbound Purge material L3 - Assy & Inj & Press |  |  | 2025-09-09 | 2025-09-10 | 2 | 100% | 2
| -Return parts to WH |  |  | 2025-09-11 | 2025-09-13 | 3 | 100% | 2
| -Create label template for QC Type & Modify label template |  |  | 2025-09-15 | 2025-09-16 | 2 | 100% | 2
2.4 | Software development (Web) | Ronnagon
| -Import schedule production (assy, press, inj) and delivery for 1 months to 4 months |  |  | 2025-05-12 | 2025-05-14 | 3 | 100% | 3
| -Search by part_name on page (stock inventory report) Search By part_name page stock_inquiry_report |  |  | 2025-05-15 | 2025-05-15 | 1 | 100% | 1
| -Add new master data page (line) |  |  | 2025-07-11 | 2025-07-11 | 1 | 100% | 1
| -Add new master data page (machine) |  |  | 2025-07-18 | 2025-07-18 | 1 | 100% | 1
| -Add new page Report delivery (weekly delivery report) Page |  |  | 2025-07-21 | 2025-07-21 | 1 | 100% | 1
| -Add new page Report warehouse (monthly inventory report) Page |  |  | 2025-07-22 | 2025-07-22 | 1 | 100% | 1
| -Implement QC process for purchase orders (Po, Pr) |  |  | 2025-07-25 | 2025-07-26 | 2 | 100% | 2
| -Add new page Schedule QC material |  |  | 2025-08-01 | 2025-08-01 | 1 | 100% | 1
| -Add new page master data ng detail |  |  | 2025-08-07 | 2025-08-07 | 1 | 100% | 1
| - Modify generate production schedule |  |  | 2025-08-11 | 2025-08-12 | 2 | 100% | 2
| -Add new page & Implement QC process for production (WH, Assy, Inj, Press) |  |  | 2025-08-14 | 2025-08-29 | 16 | 100% | 12
| -Gen pdf Assembly Order Sheet Report (Assy,Press,Inj) |  |  | 2025-09-29 | 2025-10-06 | 8 | 100% | 6
| -Add new page Report delivery (monthly delivery report) Page |  |  | 2025-09-07 | 2025-09-07 | 1 | 100% | 0
| -Add new Report stockcard (open,rec,issue,stock) Page |  |  | 2025-09-08 | 2025-09-08 | 1 | 100% | 1
| -Purchase instructions 3 months change to 4 months |  |  | 2025-09-10 | 2025-09-13 | 4 | 100% | 3
| -Add new page Report QC Page |  |  | 2025-09-15 | 2025-09-15 | 1 | 100% | 1
| -Add Setting hide show column (Stock Inquiry/Report, Stock Inventory Report) |  |  | 2025-09-16 | 2025-09-17 | 2 | 100% | 2
| -Add Language menu english to japanese |  |  | 2025-09-18 | 2025-09-19 | 2 | 0% | 2
3 | Hardware schedule
3.1 | Requirements confirmation | /Tomas |  |  | - |  |  | -
3.2 | System Design | /Tomas |  |  | - |  |  | -
3.3 | Hardware procurement | /Tomas |  |  | - |  |  | -
3.4 | Hardware pre-shipment confirmation | /Tomas |  |  | - |  |  | -
3.5 |  |  |  |  | - |  |  | -
3.6 |  |  |  |  | - |  |  | -
3.7 |  |  |  |  | - |  |  | -
4 | Installation |  |  |  | - |  |  | -
4.1 | Software installation | Tomas |  | 2025-09-22 | 2025-09-22 | 1 | 100% | 1
4.2 | Hardware installation | Tomas |  |  | - |  |  | -
4.3 | Teaching for UT | /Tomas |  | 2025-09-23 | 2025-09-24 | 2 | 100% | 2
4.4 | trainning User WH/Assy | /Tomas |  | 2025-09-25 | 2025-09-25 | 1 | 100% | 1
4.5 | trainning User Inj/Press | /Tomas |  | 2025-09-26 | 2025-09-26 | 1 | 100% | 1
4.6 | User Testing & Trial | /Tomas |  | 2025-09-29 | 2025-09-30 | 2 | 100% | 2
4.7 | Supports user feedback | /Tomas |  | 2025-09-29 | 2025-09-30 | 2 | 100% | 2
4.8 | Teaching for Go live | /Tomas |  | 2025-10-01 | 2025-10-01 | 1 | 100% | 1
4.9 | Go live | /Tomas |  | 2025-10-01 | 2025-10-01 | 1 | 100% | 1
4.10 |  |  |  |  | - |  |  | -
4.11 | [7 empty] | -
TEMPLATE ROWS
See the Help worksheet to learn how to use these rows. You can hide these rows before printing.
1 | [ Level 1 Task or Phase ] |  |  |  | - |  |  | -
1.1 | . [ Level 2 Task ] |  |  |  | - |  |  | -
1.1.1 | . . [ Level 3 Task ] |  |  |  | - |  |  | -
1.1.1.1 | . . . [ Level 4 Task ] |  |  |  | - |  |  | -
► Watch How to Create a Gantt Chart in Excel
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.