## Slide 1: Project management rules

## Slide 2
Project management rules

## Slide 3: Project management rules

## Slide 4: Overview
This document summarizes the rules related to project management. It outlines the key items that all project stakeholders must strictly adhere to,
in accordance with their respective areas of responsibility.

## Slide 5: Organization Chart
The organizational structure and corresponding roles as of August 2025 are outlined below.
IoT Engineer Dept.
Administration Dept.
Sales & Consulting Dept.
Application Engineer Dept.
Shareholders
Ryo Nozaki
CEO
Nongnut Tophimai
Accounting
Anek Sanohkham
Sales & Consulting Dept. Manager
Project Leader
Arunwit Isarapongporn
Software Engineer
Chanmnan Thaithani
Driver
Soraya Norasing
Software Engineer
Project Leader
Surasak Atchanawat
Software Engineer
Konlawat Saechee
IoT Engineer
Nichapa Bhichaiangkul
Sales Engineer
Panupong Raksakit
IoT Engineer
Phatthadon Inthachot
IoT Engineer
Wuttipong Jindam
Administration
Ronnagon Kongsuwan
Software Engineer
Project Leader
Thanthima Phaengkham
Software Engineer
Surat Duangchiaw
IoT Engineer
Watcharin Arnnok
Software Engineer
Thiraporn Amornsirinukorh
Software Engineer
Panthita Roekdee
Software Engineer
Yuki Osawa
System Engineer
Nattapol Poeam
IoT Engineer Dept.
Manager
Project Leader
Yukihiko Yaguchi
Software Engineer
Aug.2025-
Nattaporn Chaiya
Software Engineer
Project Leader
Purinat Thongbaiyai
IoT Engineer
Sermsak Prowee
IoT Engineer
Khanittha Dithakarn
Accounting
Phongphan Suwanteamee
Software Engineer
Karnthida Wannasiwaporn
Administrator Dept..
Manager
Nattikorn Srisadet
Software Engineer
Nattapong Sukcharoen
IoT Engineer
Yutthapong Sricha
Software Engineer
Project Leader
Pornpimon Jinawan
Inside sales & Admin
Ryosuke Hiroki
Sales Engineer & System Engineer
Pattanasak Chaonchom
Software Engineer
Phattarapong Kammee
Software Engineer
Suphawat Tinaso
Software Engineer
Kittisak​ Isarapongporn
CTO
Taweesak Prumvised
Software Engineer
Project Leader
Pairoj Neamjarn
Software Engineer
Project Leader
Kittisak​ Isarapongporn
Software Engineer
Project Leader
Shinnapat Phunsriphatchalakul
Software Engineer
Tanong Amnuaypornsri
Software Engineer
Nattawat Hannok
Mechanical Engineering
Warit Chunlaka
Mechanical Engineering Manager
Siriporn Nimitmuenwai
Engineering and Administrator
Project Leader
Schedule Manager

## Slide 6: Roles and Responsibilities
Project Leader
Responsible for project quality control, schedule planning and execution, and communication with the client.
Schedule Manager
Manages schedules for all projects.
In charge of entering data into Redmine and overseeing the management of project-related documents.
Japanese PIC
Responsible for project quality control and schedule management.
Acts as the primary point of contact for the client.
Sales person
Serves as the point of contact for clients in matters related to the project.
Accounting
In charge of accounting and financial matters.
CEO / CTO
Grants approvals for documents and applications. Holds overall responsibility for the project.

## Slide 7: New Project Kick-off Process
New Project Kick-off Process (N+0)
Project order received
N+0
Add to order list
N+0
Assign PJ code
N+1
④ Register PJ information in REDMINE
N+1
Appoint Project Leader
and Assign
N+1
Assign Project members
N+2
Explanation of Overview
and Usage
Project Leader to Project Member
N+2
Explanation of Overview and Usage
PIC to Project Leader
N+2
① Calculation of Development Man-hours
N+3
Confirmation of Development Man-hours by the Project Leader
N+3
CTO Confirmation and Approval of Development Man-hours
N+4
② Creation of Development Schedule
N+5
③ Project Schedule Preparation For Regular Customer Reporting
N+5
Approval of Development Man-hours
N+4
④ Register Development Schedule in REDMINE
N+5
Schedule Approval
N+5
Send Schedule to Customer
Customer / Event
Accounting
CEO
Sales & Japanese PIC
Project Leader
Project Member
CTO
Schedule Manager
① Development Man-hour Calculation Template :
② Development Schedule Template : https://node25444-tom-demo-01.proen.app.ruk-com.cloud/redmine/news/6
③ PJ Schedule Template : https://node25444-tom-demo-01.proen.app.ruk-com.cloud/redmine/news/7
YES
NO
YES
NO
④ REDMINE Data Entry Manual: https://node25444-tom-demo-01.proen.app.ruk-com.cloud/redmine/news/3
④ REDMINE Entry
Register Tasks for Each Responsible Person
N+5
④ Update REDMINE
Each Member Updates Progress and Comments
N+**

## Slide 8: Project Schedule Change
Project Schedule Change : Customer-Initiated (N+0)
Schedule Change Request Occurs
N+0
③ Project Schedule Adjustment For Regular Customer Reporting
N+1
④ Register Updated Development Schedule in REDMINE
N+1
Schedule Approval
N+2
Send Schedule to Customer
Customer / Event
Accounting
CEO
Sales & Japanese PIC
Project Leader
Project Member
CTO
Schedule Manager
YES
NO
Internal Schedule Confirmation and Notification
N+0
Assessment and Notification of Effects on Other Projects
N+1
Verification of Effects on Other Projects
N+1
② Adjustment/Modification of Development Schedule
N+1
Decision on Schedule Change
N+1
④ REDMINE Entry
Update of Each PIC’s Schedule
N+5
④ REDMINE Update
Progress and Comment Updates by Each Member
N+**
② Development Schedule Template : https://node25444-tom-demo-01.proen.app.ruk-com.cloud/redmine/news/6
③ PJ Schedule Template : https://node25444-tom-demo-01.proen.app.ruk-com.cloud/redmine/news/7
④ REDMINE Data Entry Manual: https://node25444-tom-demo-01.proen.app.ruk-com.cloud/redmine/news/3

## Slide 9: Project Schedule Change
Project Schedule Change : Internal Cause (N+0)
Send Schedule to Customer
N+2
Customer / Event
Accounting
CEO
Sales & Japanese PIC
Project Leader
Project Member
CTO
Schedule Manager
YES
NO
Schedule Change Request Occurs
N+0
Customer Confirmation
N+2
NO
YES
Report
N+1
Report
N+1
② Development Schedule Template : https://node25444-tom-demo-01.proen.app.ruk-com.cloud/redmine/news/6
③ PJ Schedule Template : https://node25444-tom-demo-01.proen.app.ruk-com.cloud/redmine/news/7
④ REDMINE Data Entry Manual: https://node25444-tom-demo-01.proen.app.ruk-com.cloud/redmine/news/3
Assessment and Notification of Effects on Other Projects
N+1
Verification of Effects on Other Projects
N+1
Decision on Schedule Change
N+1
② Adjustment/Modification of Development Schedule
N+1
④ Register Updated Development Schedule in REDMINE
N+1
③ Project Schedule Adjustment For Regular Customer Reporting
N+1
Schedule Approval
N+2

## Slide 10: Project Issue Occurrence
Project Issue Occurrence : Level 1 (N+0)
Level 1 : No disruption to customer operations. Operations can continue with a temporary workaround. No data loss
Change to Level 1 or Higher Handling
Send Punch List to Customer
N+0
Customer / Event
Accounting
CEO
Sales & Japanese PIC
Project Leader
Project Member
CTO
Schedule Manager
① Punch List Template : https://node25444-tom-demo-01.proen.app.ruk-com.cloud/redmine/news/8
YES
NO
④ REDMINE Data Entry Manual : https://node25444-tom-demo-01.proen.app.ruk-com.cloud/redmine/news/3
Receive Notification and Apology
Effect Scope Confirmation
N+0
Effect Scope Confirmation
N+0
Decision on Handling Policy and Plan Formulation
Correction Request
N+0
Level 1 Evaluation
N+0
Issue Occurrence
N+0
Receive Notification and Apology
Request for Effect Scope
N+0
④ REDMINE Entry
Issue Handling Data Entry
N+0
Issue Fix
N+**
① Creation and Update of Punch List
N+0
Report
N+0
Report
N+0
Report
N+0
Report Again After Completion of Corrections
N+**
Level 1 Evaluation
④ Register Updated Development Schedule in REDMINE
N+1

## Slide 11: Project Issue Occurrence
Project Issue Occurrence : Level 2 (N+0)
Level 2 : Customer operations have stopped. Temporary workaround allows continuation of work. Data is lost.
Customer / Event
Accounting
CEO
Sales & Japanese PIC
Project Leader
Project Member
CTO
Schedule Manager
YES
NO
Report
N+0
① Punch List Template : https://node25444-tom-demo-01.proen.app.ruk-com.cloud/redmine/news/8
④ REDMINE Data Entry Manual : https://node25444-tom-demo-01.proen.app.ruk-com.cloud/redmine/news/3
Issue Occurrence
N+0
Receive Notification and Apology
Request for Effect Scope
N+0
Receive Notification and Apology
Effect Scope Confirmation
N+0
Effect Scope Confirmation
N+0
Level 2 Evaluation
N+0
Change to Level 2 or Higher Handling
Decision on Handling Policy and Plan Formulation
Correction Request
N+0
④ Register Updated Development Schedule in REDMINE
N+1
④ REDMINE Entry
Issue Handling Data Entry
N+0
① Creation and Update of Punch List
N+0
Send Punch List to Customer
N+0
Issue Fix
N+**
Report
N+0
Report
N+0
Report
N+0
Report Again After Completion of Corrections
N+**

## Slide 12: Project Issue Occurrence
Project Issue Occurrence : Level 3 (N+0)
Level 3 : Customer operations are halted. Temporary measures cannot enable continued operations. Data is lost.
Customer / Event
Accounting
CEO
Sales & Japanese PIC
Project Leader
Project Member
CTO
Schedule Manager
Apology Visit
N+**
Preparation of Incident Report
N+0
Review of Incident Report
N+0
① Punch List Template : https://node25444-tom-demo-01.proen.app.ruk-com.cloud/redmine/news/8
④ REDMINE Data Entry Manual : https://node25444-tom-demo-01.proen.app.ruk-com.cloud/redmine/news/3
Issue Occurrence
N+0
Receive Notification and Apology
Request for Effect Scope
N+0
Report
N+0
Receive Notification and Apology
Effect Scope Confirmation
N+0
Effect Scope Confirmation
N+0
Decision on Handling Policy and Plan Formulation
Correction Request
N+0
④ Register Updated Development Schedule in REDMINE
N+1
④ REDMINE Entry
Issue Handling Data Entry
N+0
① Creation and Update of Punch List
N+0
Issue Fix
N+**
Report Again After Completion of Corrections
N+**
Send Punch List and Report to Customer
N+0

## Slide 13: Project Status Report (Weekly)
Regular Progress Report for the Project
Customer / Event
Accounting
CEO
Sales & Japanese PIC
Project Leader
Project Member
CTO
Schedule Manager
Every Monday, 08:30-11:00
N+0
Project Regular Meeting
Attendance
N+0
Project Regular Meeting
Attendance
N+0
Project Regular Meeting
Attendance
N+0
Project Regular Meeting
Attendance
N+0
③ Project Schedule Update For Regular Customer Reporting
N+0
② Development Schedule Update
N+0
Completion of Review and Update
N+0
Report
Every Monday, until 17:00
N+0
④ Register Updated Development Schedule in REDMINE
N+1
② Development Schedule Template : https://node25444-tom-demo-01.proen.app.ruk-com.cloud/redmine/news/6
③ PJ Schedule Template : https://node25444-tom-demo-01.proen.app.ruk-com.cloud/redmine/news/7
④ REDMINE Data Entry Manual: https://node25444-tom-demo-01.proen.app.ruk-com.cloud/redmine/news/3

## Slide 14: Project Status Report (Weekly)
Regular Project Progress Report (Weekly)
Objective :
Prevent delays and setbacks in the project.
Resolve technical issues faced by project members.
Visualize project progress and share updates with other team members.
Procedure :
Each participant gets 10 minutes to present the development and project Gantt charts.
The meeting starts every Monday at 08:30. Participants (as of 2025/08/01):
Report Contents :
Sharing weekly updated versions of [① Development Schedule]、[② PJ Schedule]
Sharing of issues (technical challenges, project progress, customer-related troubles, additional requests, etc.)
Anek Sanohkham
Sales & Consulting Dept. Manager
Project Leader
Soraya Norasing
Software Engineer
Project Leader
Ronnagon Kongsuwan
Software Engineer
Project Leader
Nattapol Poeam
IoT Engineer Dept.
Manager
Project Leader
Nattaporn Chaiya
Software Engineer
Project Leader
Yutthapong Sricha
Software Engineer
Project Leader
Taweesak Prumvised
Software Engineer
Project Leader
Pairoj Neamjarn
Software Engineer
Project Leader
Kittisak​ Isarapongporn
Software Engineer
Project Leader
08:30
08:40
08:50
09:00
09:10
09:20
09:30
09:40
09:50
② Development Schedule Template : https://node25444-tom-demo-01.proen.app.ruk-com.cloud/redmine/news/6
③ PJ Schedule Template : https://node25444-tom-demo-01.proen.app.ruk-com.cloud/redmine/news/7