## Scheudle
Development support schedule
| Customer : |  |  | Nippn Co., Ltd.
| Vender : |  |  | Tomas Tech Co.,Ltd.
OUT OF SCHEDULE | Project / Module : |  |  |  |  | Production management system
| No. | Description | [9 empty] | Progress (%) | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
[10 empty] | Main | Support | time axis 2025-08-17 to 2026-01-17
|  |  |  | 1 | 2 | 2 |  | Progress ahead of schedule | (Input Number "1")
[5 empty] | 2 | 2 |  | Progress as planned | (Input Number "2")
[5 empty] | 2 | 2 | 3 | Progress with scheduled delay | (Input Number "3")
[5 empty] | 2 | 4 |  | Progress finished job | (Input Number "4")
[10 empty] | Overall |  | 63.06%
| 1 | Schedule
| 1.1 |  | Kick off meeting and receive PO | [6 empty] | Tomas |  | 0%
|  |  |  | - Greeting and kick off meeting and receive PO | [7 empty] | 0% | 2025-08-17: 4
| 1.2 |  | - Development support phase | [6 empty] | Tomas |  | 0%
[5 empty] | Requirements confirmation from SA | [6 empty] | 0%
[5 empty] | System Design | [6 empty] | 0%
[5 empty] | Software development | [6 empty] | 0%
Schedule/Non-Schedule
[6 empty] | PO Customer |  |  |  | AT |  | 100% | 2025-09-08: 1; 2025-09-09: 2; 2025-09-10: 2; 2025-09-11: 2; 2025-09-12: 2; 2025-09-15: 2; 2025-09-16: 3; 2025-10-16: 2; 2025-10-17: 3; 2025-10-18: 3; 2025-10-20: 2; 2025-10-21: 2; 2025-10-22: 2; 2025-10-24: 4
[6 empty] | PD planing |  |  |  | AT |  | 100% | 2025-09-15: 2; 2025-09-16: 2; 2025-09-17: 2; 2025-09-18: 2; 2025-09-19: 2; 2025-09-20: 2; 2025-09-22: 4
[6 empty] | Outbound schedule |  |  |  | AT |  | 100% | 2025-09-23: 2; 2025-09-24: 2; 2025-09-25: 2; 2025-09-26: 2; 2025-09-29: 4
[6 empty] | Outbound |  |  |  | AT |  | 100% | 2025-09-26: 2; 2025-09-27: 4
[6 empty] | Picking/FG/Delivery Schedule Generate |  |  |  | AT |  | 100% | 2025-10-01: 2; 2025-10-02: 3; 2025-10-03: 3; 2025-10-15: 3; 2025-10-16: 3; 2025-10-17: 3; 2025-10-18: 3; 2025-10-20: 4
[6 empty] | RM Requistion sheet &schedule |  |  |  | AT |  | 100% | 2025-10-03: 1; 2025-10-04: 2; 2025-10-06: 2; 2025-10-14: 3; 2025-10-15: 3; 2025-10-16: 3; 2025-10-17: 3; 2025-10-18: 3; 2025-10-20: 4
[6 empty] | Issues Blending formula sheet |  |  |  | AT |  | 100% | 2025-10-07: 1; 2025-10-08: 2; 2025-10-09: 4
[6 empty] | Dashboard UI |  |  |  | AT |  | 100% | 2025-10-17: 1; 2025-10-18: 2; 2025-10-20: 3; 2025-10-21: 4
[6 empty] | Dashboard Backend |  |  |  | AT |  | 10% | bar: 2025-10-17 to 2025-10-18; 2025-10-27 to 2025-10-28
[6 empty] | Monthly Inventory report |  |  |  | AT |  | 10% | bar: 2025-10-27 to 2025-10-28
[6 empty] | Delivery planning |  |  |  | AT |  | 100% | 2025-10-14: 4
[6 empty] | Inbound schedule RM |  |  |  | Natto |  | 100% | 2025-10-20: 4
[6 empty] | Inbound schedule Production |  |  |  | Natto |  | 0% | bar: 2025-10-24
[6 empty] | Inbound schedule FG |  |  |  | Natto |  | 80% | 2025-10-21: 1; 2025-10-22: 2; 2025-10-24: 3
[6 empty] | Inbound History |  |  |  | Natto |  | 100% | 2025-10-20: 2; 2025-10-21: 4
[6 empty] | Incoming Plan |  |  |  | Natto |  | 100% | 2025-10-06: 1; 2025-10-07: 2; 2025-10-08: 3; 2025-10-09: 3; 2025-10-10: 3; 2025-10-14: 3; 2025-10-15: 4
[6 empty] | Return |  |  |  | Natto |  | 0% | 2025-10-09: 1; 2025-10-10: 2
[6 empty] | FG - Print label FG |  |  |  | Natto |  | 100% | 2025-10-10: 1; 2025-10-18: 4
[6 empty] | Packaging & Labeling Condition Inspection Record |  |  |  | Natto |  | 20% | 2025-10-22: 1; 2025-10-24: 2
Stock Management
[6 empty] | Stock inquiy/report |  |  |  | Natto |  | 100% | 2025-09-04: 4
[6 empty] | Stock Maintenance |  |  |  | Natto |  | 100% | 2025-09-01: 4
[6 empty] | Stocktaking |  |  |  | Natto |  | 100% | 2025-08-29: 4
[6 empty] | Puchase Instructions |  |  |  | Natto |  | 100% | 2025-09-17: 1; 2025-09-18: 2; 2025-09-19: 2; 2025-09-20: 2; 2025-09-21: 2; 2025-09-22: 2; 2025-09-23: 2; 2025-09-24: 3; 2025-09-25: 3; 2025-09-26: 3; 2025-09-27: 3; 2025-09-28: 3; 2025-09-29: 3; 2025-09-30: 3; 2025-10-01: 3; 2025-10-02: 3; 2025-10-03: 3; 2025-10-04: 3; 2025-10-05: 3; 2025-10-06: 3; 2025-10-07: 3; 2025-10-08: 3; 2025-10-09: 4
[6 empty] | PO Meterial |  |  |  | Natto |  | 100% | 2025-09-24: 1; 2025-09-25: 2; 2025-09-26: 2; 2025-09-27: 2; 2025-09-28: 2; 2025-09-29: 2; 2025-09-30: 2; 2025-10-01: 2; 2025-10-02: 3; 2025-10-03: 3; 2025-10-04: 3; 2025-10-05: 3; 2025-10-06: 3; 2025-10-07: 3; 2025-10-08: 3; 2025-10-09: 3; 2025-10-10: 3; 2025-10-14: 4
[6 empty] | MRP - PO Meterial request |  |  |  | Natto |  | 60% | 2025-10-01: 1; 2025-10-02: 2; 2025-10-03: 2; 2025-10-04: 2; 2025-10-05: 3; 2025-10-06: 3; 2025-10-07: 3; 2025-10-08: 3; 2025-10-09: 3
Master data
[6 empty] | Supplier name information |  |  |  | Natto |  | 100% | 2025-09-11: 1; 2025-09-12: 4
[6 empty] | Customer master |  |  |  | Natto |  | 100% | 2025-09-15: 1; 2025-09-16: 4
[6 empty] | Item master |  |  |  | Natto |  | 100% | 2025-09-02: 4
[6 empty] | Supplier map |  |  |  | Natto |  | 80% | 2025-09-03: 4
[6 empty] | Standard Packing Master |  |  |  | Natto |  | 100% | 2025-08-21: 4
[6 empty] | Location master |  |  |  | Natto |  | 100% | 2025-08-22: 4
[6 empty] | User master |  |  |  | Natto |  | 100% | 2025-08-25: 4
[6 empty] | User Credential master |  |  |  | Natto |  | 100% | 2025-08-26: 4
[6 empty] | Authority Master |  |  |  | Natto |  | 100% | 2025-08-27: 4
[6 empty] | Bill of Materials |  |  |  | Natto |  | 100% | 2025-09-08: 1; 2025-09-09: 2; 2025-09-10: 2; 2025-09-11: 3; 2025-09-12: 3; 2025-09-13: 3; 2025-09-14: 3; 2025-09-15: 3; 2025-09-16: 3; 2025-09-17: 3; 2025-09-18: 3; 2025-09-19: 3; 2025-09-20: 3; 2025-09-21: 3; 2025-09-22: 3; 2025-09-23: 3; 2025-09-24: 3; 2025-09-25: 3; 2025-09-26: 3; 2025-09-27: 3; 2025-09-28: 3; 2025-09-29: 3; 2025-09-30: 3; 2025-10-01: 3; 2025-10-02: 3; 2025-10-03: 3; 2025-10-04: 3; 2025-10-05: 3; 2025-10-06: 3; 2025-10-07: 3; 2025-10-08: 4
[6 empty] | NFT Product |  |  |  | Natto |  | 100% | 2025-08-18: 1; 2025-08-19: 4
[6 empty] | Pending Reason |  |  |  | Natto |  | 100% | 2025-08-20: 4
[6 empty] | TippingPlace |  |  |  | Natto |  | 100% | 2025-10-21: 4
[6 empty] | Timing of tipping |  |  |  | Natto |  | 100% | 2025-10-21: 4
[6 empty] | Blending |  |  |  | Natto |  | 100% | 2025-10-21: 4
[6 empty] | Warehouse master |  |  |  | Natto |  | 100% | 2025-10-21: 4
[6 empty] | Email notifications |  |  |  | At |  | 100% | 2025-10-10: 1; 2025-10-14: 4
Handy development | bar: 2025-10-14
[6 empty] | Login |  |  |  | Bally |  | 100% | 2025-10-08: 2
[6 empty] | Incoming Plan |  |  |  | Bally |  | 100% | 2025-10-08: 2; 2025-10-09: 2; 2025-10-10: 4
[6 empty] | Picking Plan (Full Bag) |  |  |  | Bally |  | 100% | 2025-10-14: 1; 2025-10-15: 4
[6 empty] | Picking Plan (Weighing) |  |  |  | Bally |  | 100% | 2025-10-16: 1; 2025-10-17: 4
[6 empty] | Weighing Receiving |  |  |  | Bally |  | 100% | 2025-10-18: 4
[6 empty] | Weighing Out |  |  |  | Bally |  | 100% | 2025-10-18: 4
[6 empty] | Production[3F] |  |  |  | Bally |  | 80% | 2025-10-22: 1; 2025-10-24: 2; 2025-10-27: 2
[6 empty] | Production[2F] |  |  |  | Bally |  | 0% | bar: 2025-10-25 to 2025-10-27
[6 empty] | Delivery |  |  |  | Bally |  | 0% | bar: 2025-10-28 to 2025-10-30
[6 empty] | StockManagement |  |  |  | Bally |  | 100% | 2025-10-10: 4
Unit test
Schedule/Non-Schedule
[6 empty] | PO Customer |  |  |  | AT |  | 70% | 2025-10-21: 1; 2025-10-22: 2; 2025-10-23: 2; 2025-10-24: 2
[6 empty] | PD planing |  |  |  | AT |  | 70% | 2025-10-21: 1; 2025-10-22: 2; 2025-10-23: 2; 2025-10-24: 2
[6 empty] | Outbound schedule |  |  |  | AT |  | 70% | 2025-10-21: 1; 2025-10-22: 2; 2025-10-23: 2; 2025-10-24: 2
[6 empty] | Outbound |  |  |  | AT |  | 70% | 2025-10-21: 1; 2025-10-22: 2; 2025-10-23: 2; 2025-10-24: 2
[6 empty] | Picking/FG/Delivery Schedule Generate |  |  |  | AT |  | 70% | 2025-10-21: 1; 2025-10-22: 2; 2025-10-23: 2; 2025-10-24: 2
[6 empty] | RM Requistion sheet &schedule |  |  |  | AT |  | 70% | 2025-10-21: 1; 2025-10-22: 2; 2025-10-23: 2; 2025-10-24: 2
[6 empty] | Issues Blending formula sheet |  |  |  | AT |  | 70% | 2025-10-21: 1; 2025-10-22: 2; 2025-10-23: 2; 2025-10-24: 2
[6 empty] | Dashboard UI |  |  |  | Nack |  | 100%
[6 empty] | Dashboard Backend |  |  |  | Nack |  | 100%
[6 empty] | Monthly Inventory report |  |  |  | Nack |  | 100%
[6 empty] | Delivery planning |  |  |  | Nack |  | 100% | bar: 2025-10-14
[6 empty] | Inbound shcedule |  |  |  | Nack |  | 100%
[6 empty] | Inbound |  |  |  | Nack |  | 100%
[6 empty] | Incoming Plan |  |  |  | Nack |  | 100%
[6 empty] | Return |  |  |  | Nack |  | 100%
[6 empty] | FG - Print label FG |  |  |  | Nack |  | 100%
[6 empty] | QC FG Release Product |  |  |  | Nack |  | 100%
Stock Management
[6 empty] | Stock inquiy/report |  |  |  | Nack |  | 100% | 2025-10-14: 4
[6 empty] | Stock Maintenance |  |  |  | Nack |  | 100% | 2025-10-14: 4
[6 empty] | Stocktaking |  |  |  | Nack |  | 100% | 2025-10-14: 4
[6 empty] | Puchase Instructions |  |  |  | Nack |  | 100% | 2025-10-14: 4
[6 empty] | PO Meterial |  |  |  | Nack |  | 100%
[6 empty] | MRP - PO Meterial request |  |  |  | Nack |  | 100%
Master data
[6 empty] | Supplier name information |  |  |  | Nack |  | 100% | 2025-10-14: 4
[6 empty] | Customer master |  |  |  | Nack |  | 100% | 2025-10-14: 4
[6 empty] | Item master |  |  |  | Nack |  | 100% | 2025-10-14: 4
[6 empty] | Supplier map |  |  |  | Nack |  | 0%
[6 empty] | Standard Packing Master |  |  |  | Nack |  | 100% | 2025-10-14: 4
[6 empty] | Location master |  |  |  | Nack |  | 100% | 2025-10-14: 4
[6 empty] | User master |  |  |  | Nack |  | 100% | 2025-10-14: 4
[6 empty] | User Credential master |  |  |  | Nack |  | 100% | 2025-10-14: 4
[6 empty] | Authority Master |  |  |  | Nack |  | 100% | 2025-10-14: 4
[6 empty] | Bill of Materials |  |  |  | Nack |  | 100% | 2025-10-14: 4
[6 empty] | NFT Product |  |  |  | Nack |  | 100% | 2025-08-18: 1; 2025-10-14: 4
[6 empty] | Pending Reason |  |  |  | Nack |  | 100% | 2025-10-14: 4
[6 empty] | TippingPlace |  |  |  | Nack |  | 0%
[6 empty] | Timing of tipping |  |  |  | Nack |  | 0%
[6 empty] | Blending |  |  |  | Nack |  | 0%
[6 empty] | Warehouse master |  |  |  | Nack |  | 0%
[6 empty] | Email notifications |  |  |  | Nack |  | 0%
Handy test
[6 empty] | Login |  |  |  | Bally |  | 0% | bar: 2025-10-21
[6 empty] | Incoming Plan |  |  |  | Bally |  | 0% | bar: 2025-10-21
[6 empty] | Picking Plan (Full Bag) |  |  |  | Bally |  | 0% | bar: 2025-10-21
[6 empty] | Picking Plan (Weighing) |  |  |  | Bally |  | 0% | bar: 2025-10-21
[6 empty] | Weighing Receiving |  |  |  | Bally |  | 0% | bar: 2025-10-21
[6 empty] | Weighing Out |  |  |  | Bally |  | 0% | bar: 2025-10-21
[6 empty] | Production[3F] |  |  |  | Bally |  | 0%
[6 empty] | Production[2F] |  |  |  | Bally |  | 0%
[6 empty] | Delivery |  |  |  | Bally |  | 0%
[6 empty] | StockManagement |  |  |  | Bally |  | 0%
0%
0%
[5 empty] | System intregrate Test |  |  |  |  | Film |  | 0% | bar: 2025-10-22 to 2025-10-31
[5 empty] | Internal Test | [6 empty] | 0%
[5 empty] | Comprehensive test | [6 empty] | 0%
[5 empty] | Document creation | [6 empty] | 0%
| 1.3 |  | - Installation | [6 empty] | Tomas |  | 0%
[5 empty] | Software installation | [6 empty] | 0% | bar: 2025-08-19
[5 empty] | Hardware installation | [6 empty] | 0% | bar: 2025-08-31
[5 empty] | Teaching for UT | [6 empty] | 0%
[5 empty] | User Testing & Trial | [6 empty] | 0%
[5 empty] | Supports user feedback | [6 empty] | 0%
[5 empty] | Go live | [6 empty] | 0%
DD / MM / YYYY Schedule 1st planning
DD / MM / YYYY Schedule 2nd planning
DD / MM / YYYY Schedule 3rd planning