## Phase1
[ANI CO.,LTD] Project Schedule | [8 empty] | Copyright© TOMAS TECH CORPORATION. All rights reserved.
[ANI Logistics CO.,LTD]
| Project Start Date | 2025-04-01 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Week 22 | [6 empty] | Week 23 | [6 empty] | Week 24 | [6 empty] | Week 25 | [6 empty] | Week 26 | [6 empty] | Week 27 | [6 empty] | Week 28 | [6 empty] | Week 29 | [6 empty] | Week 30 | [6 empty] | Week 31 | [6 empty] | Week 32 | [6 empty] | Week 33 | [6 empty] | Week 34 | [6 empty] | Week 35 | [6 empty] | Week 36 | [6 empty] | Week 37 | [6 empty] | Week 38 | [6 empty] | Week 39 | [6 empty] | Week 40 | [6 empty] | Week 41 | [6 empty] | Week 42 | [6 empty] | Week 43
| Project Lead | 2025-11-30 | [6 empty] | 2025-03-31 | [6 empty] | 2025-04-07 | [6 empty] | 2025-04-14 | [6 empty] | 2025-04-21 | [6 empty] | 2025-04-28 | [6 empty] | 2025-05-05 | [6 empty] | 2025-05-12 | [6 empty] | 2025-05-19 | [6 empty] | 2025-05-26 | [6 empty] | 2025-06-02 | [6 empty] | 2025-06-09 | [6 empty] | 2025-06-16 | [6 empty] | 2025-06-23 | [6 empty] | 2025-06-30 | [6 empty] | 2025-07-07 | [6 empty] | 2025-07-14 | [6 empty] | 2025-07-21 | [6 empty] | 2025-07-28 | [6 empty] | 2025-08-04 | [6 empty] | 2025-08-11 | [6 empty] | 2025-08-18 | [6 empty] | 2025-08-25 | [6 empty] | 2025-09-01 | [6 empty] | 2025-09-08 | [6 empty] | 2025-09-15 | [6 empty] | 2025-09-22 | [6 empty] | 2025-09-29 | [6 empty] | 2025-10-06 | [6 empty] | 2025-10-13 | [6 empty] | 2025-10-20 | [6 empty] | 2025-10-27 | [6 empty] | 2025-11-03 | [6 empty] | 2025-11-10 | [6 empty] | 2025-11-17 | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08 | [6 empty] | 2025-12-15 | [6 empty] | 2025-12-22 | [6 empty] | 2025-12-29 | [6 empty] | 2026-01-05 | [6 empty] | 2026-01-12 | [6 empty] | 2026-01-19
 | time axis 2025-03-31 to 2026-01-25
WBS | TASK | PIC | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2025-03-31 to 2026-01-25
1 | Kick-off meeting |  |  |  | - |  |  | -
1.1 | Kick-off meeting after PO | ANI/Tomas |  | 2024-10-01 | 2024-10-01 | 1 | 100% | 1
1.2 |  |  |  |  | - |  |  | -
1.3 |  |  |  |  | - |  |  | -
1.4 |  |  |  |  | - |  |  | -
2 | Software schedule |  |  |  | - |  |  | -
2.1 | Requirements confirmation | ANI/Tomas |  | 2024-10-01 | 2024-12-19 | 80 | 100% | 58 | bar: 2025-04-16; 2025-04-30; 2025-05-16; 2025-05-29; 2025-06-12
2.2 | Data organization/confirmation | ANI |  | 2024-10-01 | 2024-12-19 | 80 | 100% | 58
2.3 | System Design | Nack |  | 2025-04-18 | 2025-07-11 | 85 | 100% | 61
2.4 | Software development | Tomas |  | 2025-06-26 | 2025-09-30 | 97 | 98.97% | 69
2.4.1 | Handheld UI frontend | Tanong |  | 2025-06-26 | 2025-09-30 | 97 | 100% | 69
2.4.2 | SDK migrate to A1000 | Tanong |  | 2025-10-01 | 2025-10-01 | 1 | 100% | 1
2.4.3 | Handy UI Script | Tanong |  | 2025-06-26 | 2025-10-04 | 15 | 100% | 13
2.4.3.1 | Receive cont./Receive container | Tanong |  | 2025-10-01 | 2025-10-01 | 1 | 100% | 1
2.4.3.2 | Receive cont./Move case in stock | Tanong |  | 2025-10-01 | 2025-10-01 | 1 | 100% | 1
2.4.3.3 | CaseTransfer/CASE_MOVING CASE_MOVING | Tanong |  | 2025-10-02 | 2025-10-02 | 1 | 100% | 1
2.4.3.4 | CaseTransfer/CASE_LOADING CASE_LOADING | Tanong |  | 2025-10-02 | 2025-10-02 | 1 | 100% | 1
2.4.3.5 | CaseTransfer/TRANSFER_RECEIVE | Tanong |  | 2025-10-02 | 2025-10-02 | 1 | 100% | 1
2.4.3.6 | CasePicking/SET_ORDER CASE_PICKING | Tanong |  | 2025-10-02 | 2025-10-02 | 1 | 100% | 1
2.4.3.7 | CasePicking/SP_MOVE_TO_UNPACK | Tanong |  | 2025-10-02 | 2025-10-02 | 1 | 100% | 1
2.4.3.8 | Stagging/MS_RECEIVE MS_RECEIVE | Tanong |  | 2025-10-03 | 2025-10-03 | 1 | 100% | 1
2.4.3.9 | Staging/SCAN_PARTS SCAN_PARTS | Tanong |  | 2025-10-03 | 2025-10-03 | 1 | 100% | 1
2.4.3.10 | Staging/LOADING_PARTS LOADING_PARTS | Tanong |  | 2025-10-03 | 2025-10-03 | 1 | 100% | 1
2.4.3.11 | Box unpack/ROBBING CASE_ROBBING | Tanong |  | 2025-10-03 | 2025-10-03 | 1 | 100% | 1
2.4.3.12 | Box unpack/SPECIAL SP_BOX_UNPACK | Tanong |  | 2025-10-03 | 2025-10-03 | 1 | 100% | 1
2.4.3.13 | CasePicking/SPECIAL CASE_SPECIAL | Tanong |  | 2025-10-03 | 2025-10-03 | 1 | 100% | 1
2.4.3.14 | RackTransfer/RETURN_RACK RETURN_RACK | Tanong |  | 2025-10-04 | 2025-10-04 | 1 | 100% | 0
2.4.3.15 | RackTransfer/RECEIVE_RACK RECEIVE_RACK | Tanong |  | 2025-10-04 | 2025-10-04 | 1 | 100% | 0
2.4.3.16 | Manual Inbound | Tanong |  | 2025-12-01 | 2025-12-01 | 1 | 100% | 1
2.4.3.17 | Manual Outbound | Tanong |  | 2025-12-02 | 2025-12-02 | 1 | 100% | 1
2.4.4 | WS api and frontend script fixing | Kittisak, Tanong |  | 2025-06-26 | 2025-10-20 | 97 | 100% | 83
2.4.4.1 | Receive cont./Receive container | Kittisak, Tanong |  | 2025-10-01 | 2025-10-01 | 1 | 100% | 1 | 2025-10-07: 4
2.4.4.2 | Receive cont./Move case in stock | Kittisak, Tanong |  | 2025-10-01 | 2025-10-01 | 1 | 100% |  | 2025-10-08: 4
2.4.5 | CaseTransfer/CASE_MOVING CASE_MOVING | Kittisak, Tanong |  | 2025-10-02 | 2025-10-02 | 1 | 100% |  | 2025-10-09: 4
2.4.5.1 | CaseTransfer/CASE_LOADING CASE_LOADING | Kittisak, Tanong |  | 2025-10-02 | 2025-10-02 | 1 | 100% |  | 2025-10-10: 4
2.4.5.2 | CaseTransfer/TRANSFER_RECEIVE | Kittisak, Tanong |  | 2025-10-02 | 2025-10-02 | 1 | 100% |  | 2025-10-11: 4
2.4.5.3 | Box unpack/ROBBING CASE_ROBBING | Kittisak, Tanong |  | 2025-10-15 | 2025-10-15 | 1 | 100% |  | 2025-10-15: 4
2.4.5.4 | Box unpack/SET_ORDER | Kittisak, Tanong |  | 2025-10-15 | 2025-10-15 | 1 | 100% |  | 2025-10-16: 4; 2025-11-28: 2
2.4.5.5 | Box unpack/SPECIAL CASE_SPECIAL | Kittisak, Tanong |  | 2025-10-16 | 2025-10-16 | 1 | 100% |  | 2025-10-17: 4
2.4.5.6 | CasePicking/ROBBING_CASE | Kittisak, Tanong |  | 2025-10-09 | 2025-10-09 | 1 | 100% |  | 2025-10-14: 4
2.4.5.7 | CasePicking/ROBBING_PICKING_PARTS | Kittisak, Tanong |  | 2025-10-10 | 2025-10-10 | 1 | 100% |  | 2025-10-20: 4
2.4.5.8 | CasePicking/ROBBING_RETURN | Kittisak, Tanong |  | 2025-10-10 | 2025-10-10 | 1 | 100% |  | 2025-10-21: 4
2.4.5.9 | CasePicking/SET_ORDER | Kittisak, Tanong |  | 2025-10-13 | 2025-10-13 | 1 | 100% |  | 2025-10-24: 4
2.4.5.10 | Stagging/MS_RECEIVE | Kittisak, Tanong |  | 2025-10-14 | 2025-10-14 | 1 | 100% |  | 2025-11-08: 4
2.4.5.11 | Staging/SCAN_PARTS SCAN_PARTS | Kittisak, Tanong |  | 2025-10-14 | 2025-10-14 | 1 | 100% |  | 2025-10-29: 3; 2025-11-03: 3; 2025-11-04: 3; 2025-11-05: 3; 2025-11-06: 4
2.4.5.12 | Staging/LOADING_PARTS | Kittisak, Tanong |  | 2025-10-14 | 2025-10-14 | 1 | 100% |  | 2025-10-30: 3; 2025-11-06: 3; 2025-11-07: 4
2.4.5.13 | RackTransfer/RETURN_RACK RETURN_RACK | Kittisak, Tanong |  | 2025-10-17 | 2025-10-17 | 1 | 100% |  | 2025-11-10: 4
2.4.5.14 | RackTransfer/RECEIVE_RACK RECEIVE_RACK | Kittisak, Tanong |  | 2025-10-17 | 2025-10-17 | 1 | 100% |  | 2025-11-10: 4
2.4.5.15 | Trouble Report | Kittisak, Tanong |  | 2025-10-18 | 2025-10-20 | 1 | 100% | 1 | 2025-10-20: 4
2.4.5.16 | Manual Inbound | Kittisak, Tanong |  | 2025-12-02 | 2025-12-02 | 1 | 0% | 1
2.4.5.17 | Manual Outbound | Kittisak, Tanong |  | 2025-12-03 | 2025-12-03 | 1 | 0% | 1
2.4.6 | Labeling | Tanong |  | 2025-10-02 | 2025-10-02 | 1 | 100% | 1
2.4.6.1 | Issue ANI Label | Tanong |  | 2025-10-05 | 2025-10-05 | 1 | 100% | 0 | 2025-11-14: 1; 2025-11-17: 2; 2025-11-18: 2; 2025-11-19: 4
2.4.6.2 | Issue Shipping Note | Yut |  | 2025-10-05 | 2025-10-05 | 1 | 100% | 0
2.4.6.3 | Issue Truck Delivery | Tanong |  | 2025-11-22 | 2025-11-22 | 1 | 100% | 0 | 2025-11-22: 1; 2025-11-24: 2; 2025-11-26: 4
2.4.6.4 | Trouble Report | Tanong |  | 2025-09-25 | 2025-09-29 | 3 | 100% | 3
2.4.7 | Tablet Development | Tanong |  | 2025-10-21 | 2025-11-10 | 15 | 100% | 15
2.4.7.1 | Result Report | Tanong |  | 2025-10-21 | 2025-10-22 | 2 | 100% | 2 | 2025-10-23: 4; 2025-11-14: 4
2.4.7.2 | Meiji card display | Tanong |  | 2025-10-31 | 2025-10-31 | 1 | 100% | 1 | 2025-11-01: 4; 2025-11-14: 4
2.4.7.3 | Report Detail | Tanong |  | 2025-11-10 | 2025-11-10 | 1 | 100% | 1 | 2025-11-14: 4
2.4.8 | Web Development | Yut |  | 2025-06-26 | 2025-09-30 | 97 | 91.79% | 69
2.4.8.1 | Setting - Manage Menus | Yut |  | 2025-06-26 | 2025-06-27 | 2 | 100% | 2 | 2025-06-27: 4
2.4.8.2 | Location Master | Yut |  | 2025-06-28 | 2025-07-01 | 2 | 100% | 2 | 2025-07-01: 4
2.4.8.3 | Calendar Master | Yut |  | 2025-07-02 | 2025-07-03 | 2 | 100% | 2 | 2025-07-03: 4
2.4.8.4 | Line Master | Yut |  | 2025-07-04 | 2025-07-07 | 2 | 100% | 2 | 2025-07-07: 4
2.4.8.5 | Department Master | Yut |  | 2025-07-08 | 2025-07-09 | 2 | 100% | 2 | 2025-07-09: 4
2.4.8.6 | Packing Standard | Yut |  | 2025-07-10 | 2025-07-11 | 2 | 100% | 2 | 2025-07-11: 4
2.4.8.7 | User Master | Yut |  | 2025-07-12 | 2025-07-15 | 2 | 100% | 2 | 2025-07-15: 4
2.4.8.8 | User Credential Master | Yut |  | 2025-07-16 | 2025-07-17 | 2 | 100% | 2 | 2025-07-17: 4
2.4.8.9 | Warehouse Master | Yut |  | 2025-07-18 | 2025-07-21 | 2 | 100% | 2 | 2025-07-21: 4
2.4.8.10 | Rack Master | Yut |  | 2025-07-22 | 2025-07-23 | 2 | 100% | 2 | 2025-07-23: 4
2.4.8.11 | Pending Reason Master | Yut |  | 2025-07-24 | 2025-07-25 | 2 | 100% | 2 | 2025-07-25: 4
2.4.8.12 | Q.Point Check Master | Yut |  | 2025-07-26 | 2025-07-29 | 2 | 100% | 2 | 2025-07-29: 4
2.4.8.13 | Item Master | Yut |  | 2025-07-30 | 2025-07-31 | 2 | 100% | 2 | 2025-07-31: 4
2.4.8.14 | Import Transaction/Mnf Raw Data AS400 | Yut |  | 2025-08-01 | 2025-08-04 | 2 | 100% | 2 | 2025-08-04: 4
2.4.8.15 | Import Transaction/Mnf Received Email | Yut |  | 2025-08-05 | 2025-08-06 | 2 | 100% | 2 | 2025-08-06: 4
2.4.8.16 | Import Transaction/Product Plan Prority | Yut |  | 2025-08-07 | 2025-08-08 | 2 | 100% | 2 | 2025-08-08: 4
2.4.8.17 | Import Transaction/ Rotation Parts Order Transfer | Yut |  | 2025-08-09 | 2025-08-12 | 2 | 100% | 2 | 2025-08-12: 4
2.4.8.18 | Import Transaction/ Plan Weekly | Yut |  | 2025-08-13 | 2025-08-14 | 2 | 100% | 2 | 2025-08-14: 4
2.4.8.19 | Import Transaction/ Part List | Yut |  | 2025-08-15 | 2025-08-18 | 2 | 100% | 2 | 2025-08-18: 4
2.4.8.20 | Import Transaction/ Match Lot and Special | Yut |  | 2025-08-19 | 2025-08-20 | 2 | 100% | 2 | 2025-08-20: 4
2.4.8.21 | Inbound/Inbound Inquiry Report | Yut |  | 2025-08-21 | 2025-08-22 | 2 | 100% | 2 | 2025-08-22: 4
2.4.8.22 | Outbound/Outbound Inquiry Report | Yut |  | 2025-08-23 | 2025-08-26 | 2 | 100% | 2 | 2025-08-26: 4
2.4.8.23 | Menu Stock Management/stock maintenance | Yut |  | 2025-08-27 | 2025-08-28 | 2 | 100% | 2 | 2025-08-28: 4
2.4.8.24 | Menu Stock Management/stocktaking | Yut |  | 2025-08-29 | 2025-09-01 | 2 | 100% | 2 | 2025-09-01: 4
2.4.8.25 | Menu Stock Management/stock inquiry report | Yut |  | 2025-09-02 | 2025-09-03 | 2 | 100% | 2 | 2025-09-03: 4
2.4.8.26 | Schedule/Receive Container | Yut |  | 2025-09-04 | 2025-09-05 | 2 | 100% | 2 | 2025-09-05: 4; 2025-10-24: 4
2.4.8.27 | Schedule/Production | Yut |  | 2025-09-22 | 2025-09-26 | 5 | 100% | 5 | 2025-10-27: 4; 2025-11-22: 4
2.4.8.28 | Schedule/Robbing Parts/Return | Yut |  | 2025-09-27 | 2025-09-30 | 2 | 100% | 2 | 2025-10-29: 3; 2025-10-30: 3; 2025-10-31: 3; 2025-11-01: 3; 2025-11-03: 3; 2025-11-04: 3; 2025-11-05: 3; 2025-11-06: 3; 2025-11-07: 3; 2025-11-10: 3; 2025-11-11: 4
2.4.8.29 | Schedule/Case Transfer | Yut |  | 2025-10-07 | 2025-10-08 | 2 | 100% | 2 | 2025-10-27: 4
2.4.8.30 | Schedule/Special Parts | Yut |  | 2025-10-09 | 2025-10-10 | 2 | 100% | 2 | 2025-10-22: 3; 2025-10-24: 3; 2025-10-27: 3; 2025-10-28: 3; 2025-10-29: 3; 2025-10-30: 3; 2025-10-31: 3; 2025-11-03: 3; 2025-11-04: 3; 2025-11-05: 3; 2025-11-06: 3; 2025-11-07: 3; 2025-11-10: 4; 2025-11-26: 3
2.4.8.31 | Export NET file | Yut |  | 2025-10-01 | 2025-10-02 | 2 | 100% | 2 | 2025-11-21: 1; 2025-11-26: 3; 2025-11-27: 3; 2025-11-28: 3; 2025-12-01: 4
2.4.8.32 | Export ANI weekly plan | Yut |  | 2025-10-03 | 2025-10-06 | 2 | 100% | 2 | 2025-10-06: 4
2.4.8.33 | Reprint Exporter content label | Yut |  | 2025-10-11 | 2025-10-11 | 1 | 100% | 0 | 2025-11-12: 4
2.4.8.34 | Reprint Case mark document | Yut |  | 2025-12-04 | 2025-12-04 | 1 | 0% | 1
2.4.8.35 | Shipping Note | Yut |  | 2025-10-12 | 2025-10-12 | 1 | 100% | 0 | 2025-11-18: 1; 2025-11-19: 2; 2025-11-20: 4
2.4.8.36 | Setting list | Yut |  | 2025-10-13 | 2025-10-13 | 1 | 100% | 1 | 2025-11-26: 1; 2025-11-27: 2; 2025-11-28: 3; 2025-12-01: 4
2.4.8.37 | Trouble Report | Yut |  | 2025-12-02 | 2025-12-04 | 1 | 80% | 3 | 2025-12-02: 1; 2025-12-03: 2
2.4.8.38 | Picking List | Yut |  | 2025-12-05 | 2025-12-05 | 1 | 0% | 1 | bar: 2025-12-04
2.4.8.39 | Dashboard | Yut |  | 2025-11-24 | 2025-11-25 | 2 | 0% |  | 2025-11-28: 3
2.5 | SIT | Tomas |  | 2025-08-18 | 2025-10-06 | 50 | 90% | 36
2.6 | [7 empty] | -
3 | Hardware schedule |  |  |  | - |  |  | -
3.1 | Requirements confirmation | ANI/Tomas |  | 2025-06-02 | 2025-07-01 | 30 | 100% | 22
3.2 | System Design | Tomas |  | 2025-06-16 | 2025-07-25 | 40 | 100% | 30
3.3 | Hardware procurement | Tomas |  | 2025-07-14 | 2025-09-06 | 55 | 100% | 40
3.4 | Hardware pre-shipment confirmation | Tomas |  | 2025-08-01 | 2025-08-02 | 2 | 100% | 1
3.5 |  |  |  |  | - |  |  | -
3.6 |  |  |  |  | - |  |  | -
3.7 |  |  |  |  | - |  |  | -
4 | Installation |  |  |  | - |  |  | -
4.1 | Software installation | Tomas |  | 2025-10-01 | 2025-10-07 | 7 | 100% | 5
4.2 | Hardware installation | Tomas |  | 2025-09-16 | 2025-10-01 | 12 | 100% | 12
4.3 | Teaching/Correction check for Web | ANI/Tomas |  | 2025-11-10 | 2025-11-11 | 2 | 0% | 2 | bar: 2025-11-10
4.4 | Teaching/Correction check for Handy | ANI/Tomas |  | 2025-11-10 | 2025-11-11 | 2 | 0% | 2 | bar: 2025-11-10
4.5 | UAT | ANI/Tomas |  | 2025-11-10 | 2025-11-21 | 10 | 84.41% | 10 | bar: 2025-11-10
4.5.1 | Handy functions | ANI/Tomas |  | 2025-11-10 | 2025-11-17 | 6 | 100% | 6 | 2025-11-10: 0
4.5.1.1 | Receive cont./Receive container | ANI/Tomas |  | 2025-11-10 | 2025-11-12 | 3 | 100% | 3 | 2025-11-10: 0; 2025-11-11: 4; 2025-11-20: 4
4.5.1.2 | Receive cont./Move case in stock | ANI/Tomas |  | 2025-11-10 | 2025-11-12 | 3 | 100% | 3 | 2025-11-10: 0; 2025-11-11: 4; 2025-11-20: 4
4.5.1.3 | CaseTransfer/CASE_MOVING CASE_MOVING | ANI/Tomas |  | 2025-11-10 | 2025-11-12 | 3 | 100% | 3 | 2025-11-10: 0; 2025-11-11: 4
4.5.1.4 | CaseTransfer/CASE_LOADING CASE_LOADING | ANI/Tomas |  | 2025-11-10 | 2025-11-12 | 3 | 100% | 3 | 2025-11-10: 0; 2025-11-11: 4
4.5.1.5 | CaseTransfer/TRANSFER_RECEIVE | ANI/Tomas |  | 2025-11-10 | 2025-11-12 | 3 | 100% | 3 | 2025-11-10: 0; 2025-11-11: 4
4.5.1.6 | CasePicking/ROBBING_CASE | ANI/Tomas |  | 2025-11-12 | 2025-11-14 | 3 | 100% | 3 | 2025-11-12: 1; 2025-11-13: 3; 2025-11-14: 3; 2025-11-17: 3; 2025-11-18: 3; 2025-11-19: 4
4.5.1.7 | CasePicking/ROBBING_PICKING_PARTS | ANI/Tomas |  | 2025-11-12 | 2025-11-14 | 3 | 100% | 3 | 2025-11-12: 1; 2025-11-13: 3; 2025-11-14: 3; 2025-11-17: 3; 2025-11-18: 3; 2025-11-19: 4; 2025-11-26: 4
4.5.1.8 | CasePicking/ROBBING_RETURN | ANI/Tomas |  | 2025-11-12 | 2025-11-14 | 3 | 100% | 3 | 2025-11-12: 1; 2025-11-13: 3; 2025-11-14: 3; 2025-11-17: 3; 2025-11-18: 3; 2025-11-19: 4
4.5.1.9 | CasePicking/SET_ORDER | ANI/Tomas |  | 2025-11-12 | 2025-11-14 | 3 | 100% | 3 | 2025-11-12: 1; 2025-11-13: 3; 2025-11-14: 3; 2025-11-17: 3; 2025-11-18: 4
4.5.1.10 | Box unpack/ROBBING CASE_ROBBING | ANI/Tomas |  | 2025-11-12 | 2025-11-14 | 3 | 100% | 3 | 2025-11-12: 1; 2025-11-13: 3; 2025-11-14: 3; 2025-11-17: 3; 2025-11-18: 3; 2025-11-19: 3; 2025-11-20: 3; 2025-11-21: 3; 2025-11-24: 3; 2025-11-25: 4
4.5.1.11 | Box unpack/SPECIAL SP_BOX_UNPACK | ANI/Tomas |  | 2025-11-12 | 2025-11-14 | 3 | 100% | 3 | 2025-11-12: 1; 2025-11-13: 3; 2025-11-14: 3; 2025-11-17: 3; 2025-11-18: 3; 2025-11-19: 3; 2025-11-20: 3; 2025-11-21: 4
4.5.1.12 | Box unpack/SET_ORDER | ANI/Tomas |  | 2025-11-12 | 2025-11-14 | 3 | 100% | 3 | 2025-11-12: 1; 2025-11-13: 3; 2025-11-14: 3; 2025-11-17: 3; 2025-11-18: 3; 2025-11-19: 3; 2025-11-20: 4
4.5.1.13 | Staging/SCAN_PARTS SCAN_PARTS | ANI/Tomas |  | 2025-11-13 | 2025-11-17 | 3 | 100% | 3 | 2025-11-17: 1; 2025-11-18: 3; 2025-11-19: 3; 2025-11-20: 3; 2025-11-24: 3; 2025-11-25: 4
4.5.1.14 | Delivery/MS_RECEIVE | ANI/Tomas |  | 2025-11-13 | 2025-11-17 | 3 | 100% | 3 | 2025-11-17: 1; 2025-11-18: 3; 2025-11-19: 3; 2025-11-20: 3; 2025-11-24: 3; 2025-11-25: 4
4.5.1.15 | Staging/LOADING_PARTS | ANI/Tomas |  | 2025-11-13 | 2025-11-17 | 3 | 100% | 3 | 2025-11-17: 1; 2025-11-18: 3; 2025-11-19: 3; 2025-11-20: 3; 2025-11-24: 3; 2025-11-25: 4
4.5.1.16 | Delivery/MS_RECEIVE | ANI/Tomas |  | 2025-11-13 | 2025-11-17 | 3 | 100% | 3 | 2025-11-17: 1; 2025-11-18: 3; 2025-11-19: 3; 2025-11-20: 3; 2025-11-24: 3; 2025-11-25: 4
4.5.1.17 | RackTransfer/RETURN_RACK RETURN_RACK | ANI/Tomas |  | 2025-11-13 | 2025-11-17 | 3 | 100% | 3 | 2025-11-17: 1; 2025-11-18: 3; 2025-11-19: 3; 2025-11-20: 3; 2025-11-24: 3; 2025-11-25: 4
4.5.1.18 | RackTransfer/RECEIVE_RACK RECEIVE_RACK | ANI/Tomas |  | 2025-11-13 | 2025-11-17 | 3 | 100% | 3 | 2025-11-17: 1; 2025-11-18: 3; 2025-11-19: 3; 2025-11-20: 3; 2025-11-24: 3; 2025-11-25: 4
4.5.1.19 | Trouble Report | ANI/Tomas |  | 2025-12-01 | 2025-12-01 | 1 | 100% | 1 | 2025-11-24: 3; 2025-11-25: 3; 2025-12-01: 4
4.5.2 | Tablet functions | ANI/Tomas |  | 2025-11-24 | 2025-11-24 | 1 | 33.33% | 1
4.5.2.1 | Result Report | ANI/Tomas |  | 2025-11-24 | 2025-11-24 | 1 | 0% | 1 | 2025-11-24: 2; 2025-11-25: 3
4.5.2.2 | Meiji card display | ANI/Tomas |  | 2025-11-24 | 2025-11-24 | 1 | 100% | 1 | 2025-11-24: 4
4.5.2.3 | Report Detail | ANI/Tomas |  | 2025-11-24 | 2025-11-24 | 1 | 0% | 1 | 2025-11-24: 2; 2025-11-25: 3
4.5.3 | Web functions | ANI/Tomas |  | 2025-11-10 | 2025-11-17 | 6 | 68.82% | 6
4.5.3.1 | Setting - Manage Menus | ANI/Tomas |  | 2025-11-10 | 2025-11-10 | 1 | 100% | 1 | 2025-11-10: 1; 2025-11-11: 4
4.5.3.2 | Location Master | ANI/Tomas |  | 2025-11-10 | 2025-11-10 | 1 | 100% | 1 | 2025-11-10: 1; 2025-11-11: 4
4.5.3.3 | Calendar Master | ANI/Tomas |  | 2025-11-10 | 2025-11-10 | 1 | 100% | 1 | 2025-11-10: 1; 2025-11-11: 4
4.5.3.4 | Line Master | ANI/Tomas |  | 2025-11-10 | 2025-11-10 | 1 | 100% | 1 | 2025-11-10: 1; 2025-11-11: 4
4.5.3.5 | Department Master | ANI/Tomas |  | 2025-11-10 | 2025-11-10 | 1 | 100% | 1 | 2025-11-10: 1; 2025-11-11: 4
4.5.3.6 | Packing Standard | ANI/Tomas |  | 2025-11-10 | 2025-11-10 | 1 | 100% | 1 | 2025-11-10: 1; 2025-11-11: 4
4.5.3.7 | User Master | ANI/Tomas |  | 2025-11-10 | 2025-11-10 | 1 | 100% | 1 | 2025-11-10: 1; 2025-11-11: 4
4.5.3.8 | User Credential Master | ANI/Tomas |  | 2025-11-10 | 2025-11-10 | 1 | 100% | 1 | 2025-11-10: 1; 2025-11-11: 4
4.5.3.9 | Warehouse Master | ANI/Tomas |  | 2025-11-10 | 2025-11-10 | 1 | 100% | 1 | 2025-11-10: 1; 2025-11-11: 4
4.5.3.10 | Rack Master | ANI/Tomas |  | 2025-11-10 | 2025-11-10 | 1 | 100% | 1 | 2025-11-10: 1; 2025-11-11: 4
4.5.3.11 | Pending Reason Master | ANI/Tomas |  | 2025-11-10 | 2025-11-10 | 1 | 100% | 1 | 2025-11-10: 1; 2025-11-11: 4
4.5.3.12 | Q.Point Check Master | ANI/Tomas |  | 2025-11-10 | 2025-11-10 | 1 | 100% | 1 | 2025-11-10: 1; 2025-11-11: 4
4.5.3.13 | Item Master | ANI/Tomas |  | 2025-11-10 | 2025-11-10 | 1 | 100% | 1 | 2025-11-10: 1; 2025-11-11: 4
4.5.3.14 | Import Transaction/Mnf Raw Data AS400 | ANI/Tomas |  | 2025-11-10 | 2025-11-11 | 2 | 100% | 2 | 2025-11-10: 1; 2025-11-11: 2; 2025-11-12: 4
4.5.3.15 | Import Transaction/Mnf Received Email | ANI/Tomas |  | 2025-11-10 | 2025-11-11 | 2 | 100% | 2 | 2025-11-10: 1; 2025-11-11: 2; 2025-11-12: 4
4.5.3.16 | Import Transaction/Product Plan Prority | ANI/Tomas |  | 2025-11-10 | 2025-11-11 | 2 | 100% | 2 | 2025-11-10: 1; 2025-11-11: 2; 2025-11-12: 4
4.5.3.17 | Import Transaction/ Rotation Parts Order Transfer | ANI/Tomas |  | 2025-11-10 | 2025-11-11 | 2 | 100% | 2 | 2025-11-10: 1; 2025-11-11: 2; 2025-11-12: 4
4.5.3.18 | Import Transaction/ Plan Weekly | ANI/Tomas |  | 2025-11-10 | 2025-11-11 | 2 | 100% | 2 | 2025-11-10: 1; 2025-11-11: 2; 2025-11-12: 4
4.5.3.19 | Import Transaction/ Part List | ANI/Tomas |  | 2025-11-10 | 2025-11-11 | 2 | 100% | 2 | 2025-11-10: 1; 2025-11-11: 2; 2025-11-12: 4
4.5.3.20 | Import Transaction/ Match Lot and Special | ANI/Tomas |  | 2025-11-10 | 2025-11-11 | 2 | 100% | 2 | 2025-11-10: 1; 2025-11-11: 2; 2025-11-12: 4
4.5.3.21 | Inbound/Inbound Inquiry Report | ANI/Tomas |  | 2025-11-11 | 2025-11-12 | 2 | 0% | 2 | 2025-11-14: 3; 2025-11-17: 3
4.5.3.22 | Outbound/Outbound Inquiry Report | ANI/Tomas |  | 2025-11-11 | 2025-11-12 | 2 | 0% | 2 | 2025-11-14: 3; 2025-11-17: 3
4.5.3.23 | Menu Stock Management/stock maintenance | ANI/Tomas |  | 2025-11-11 | 2025-11-12 | 2 | 0% | 2 | 2025-11-14: 3; 2025-11-17: 3
4.5.3.24 | Menu Stock Management/stock inquiry report | ANI/Tomas |  | 2025-11-11 | 2025-11-12 | 2 | 0% | 2 | 2025-11-14: 3; 2025-11-17: 3
4.5.3.25 | Schedule/Receive Container | ANI/Tomas |  | 2025-11-11 | 2025-11-12 | 2 | 100% | 2 | 2025-11-14: 3; 2025-11-17: 4
4.5.3.26 | Schedule/Production | ANI/Tomas |  | 2025-11-11 | 2025-11-12 | 2 | 80% | 2 | 2025-11-14: 3; 2025-11-17: 3; 2025-12-01: 3; 2025-12-02: 3; 2025-12-03: 3
4.5.3.27 | Schedule/Robbing Parts/Return | ANI/Tomas |  | 2025-11-11 | 2025-11-12 | 2 | 95% | 2 | 2025-11-14: 3; 2025-11-17: 3; 2025-11-25: 3; 2025-11-26: 3; 2025-11-27: 3; 2025-11-28: 2; 2025-12-02: 3; 2025-12-03: 3
4.5.3.28 | Schedule/Case Transfer | ANI/Tomas |  | 2025-11-13 | 2025-11-14 | 2 | 0% | 2 | 2025-11-14: 3; 2025-11-17: 3; 2025-11-25: 3; 2025-11-26: 3; 2025-11-27: 3; 2025-11-28: 3; 2025-12-01: 3; 2025-12-02: 3; 2025-12-03: 3
4.5.3.29 | Schedule/Special Parts | ANI/Tomas |  | 2025-11-13 | 2025-11-14 | 2 | 50% | 2 | 2025-11-14: 3; 2025-11-17: 3; 2025-11-25: 3; 2025-11-26: 3; 2025-11-27: 3; 2025-11-28: 3; 2025-12-01: 3; 2025-12-02: 3; 2025-12-03: 3
4.5.3.30 | Export NET file | ANI/Tomas |  | 2025-11-13 | 2025-11-14 | 2 | 0% | 2 | 2025-11-14: 3; 2025-11-17: 3; 2025-11-26: 3
4.5.3.31 | Export ANI weekly plan | ANI/Tomas |  | 2025-11-13 | 2025-11-14 | 2 | 0% | 2 | 2025-11-14: 3; 2025-11-17: 3; 2025-11-26: 3
4.5.3.32 | Reprint Exporter content label | ANI/Tomas |  | 2025-11-17 | 2025-11-17 | 1 | 100% | 1 | 2025-11-26: 3; 2025-11-27: 4
4.5.3.33 | Shipping Note | ANI/Tomas |  | 2025-11-17 | 2025-11-17 | 1 | 0% | 1 | 2025-11-26: 3
4.5.3.34 | Robbing and Return | ANI/Tomas |  | 2025-11-17 | 2025-11-17 | 1 | 95% | 1 | 2025-11-26: 3; 2025-11-27: 2; 2025-11-28: 3
4.5.3.35 | Setting List | ANI/Tomas |  | 2025-12-04 | 2025-12-04 | 1 | 95% | 1 | bar: 2025-12-02 to 2025-12-03
4.5.3.36 | Trouble Report | ANI/Tomas |  | 2025-12-05 | 2025-12-05 | 1 | 0% | 1 | bar: 2025-12-03 to 2025-12-04
4.5.3.37 | Picking List | ANI/Tomas |  | 2025-12-05 | 2025-12-05 | 1 | 0% | 1 | bar: 2025-12-04
4.5.3.38 | Dashboard | ANI/Tomas |  | 2025-11-17 | 2025-11-17 | 1 | 0%
4.6 | User Testing & Trial | ANI/Tomas |  | 2025-11-10 | 2025-11-29 | 20 | 84.41% | 15
4.7 | Supports user feedback | ANI/Tomas |  | 2025-11-10 | 2025-12-19 | 40 | 0% | 30
4.8 | Teaching for Go live | ANI/Tomas |  | 2025-11-17 | 2025-11-30 | 14 | 0% | 10
4.9 | Go live | ANI/Tomas |  | 2025-12-01 | 2025-12-01 | 1 | 0% | 1
4.10 | [7 empty] | -
TEMPLATE ROWS
See the Help worksheet to learn how to use these rows. You can hide these rows before printing.
1 | [ Level 1 Task or Phase ] |  |  |  | - |  |  | -
1.1 | . [ Level 2 Task ] |  |  |  | - |  |  | -
1.1.1 | . . [ Level 3 Task ] |  |  |  | - |  |  | -
1.1.1.1 | . . . [ Level 4 Task ] |  |  |  | - |  |  | -
► Watch How to Create a Gantt Chart in Excel
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.
Note on HF39: User: Traning HT all day.
Note on HF40: User: Traning HT all day.
Note on HF41: User: Traning HT all day.
Note on HF42: User: Traning HT all day.
Note on HF43: User: Traning HT all day.
Note on HF44: User: Traning HT all day.
Note on HF45: User: Traning HT all day.
Note on IS45: Kittisak: Found some issues that doesn't match to actual operation (modify 2 days) 1. Adding auto print ANI label 2. Show SP/RB/BLANK
Note on HF46: User: Traning HT all day.
Note on HF47: User: Traning HT all day.
Note on HF49: User: Traning HT all day.
Note on HF50: User: Traning HT all day.
Note on HF51: User: Traning HT all day.
Note on HF52: User: Traning HT all day.
Note on HF53: User: Traning HT all day.
Note on HF54: User: Traning HT all day.
Note on HF55: User: Traning HT all day.
Note on IM60: User: Retest
Note on GV94: User: Training/Test Receive Container function
Note on GZ95: User: Preview/Check plan production schedule at the afternoon 2pm
Note on HD95: User: Receive container: 95% Case Transfer: Robbing: - DB 100% - Case picking - Part picking - Case return Set order: - Case picking Staging - 100% Delivery: - 100% MS - 100%
Note on IM95: User: 80%
Note on HF97: User: Check plan case transfer
Note on HG98: User: Check plan special part at the afternoon 2pm.
Note on IQ98: User: Fixing, will be finished within today
Note on HB99: User: Preview/Check plan robbing schedule at the morning 10am
Note on HC99: User: Compare NET file with an old system AS400 at the afternoon 3pm.
Note on IK125: User: Actual test with the real data หน้างาน
Note on IQ131: User: Test actual print ANI label
Note on IP133: User: Need to manual choose the location on step3
Note on IV143: Kittisak: Need to retest (imported NG Reason)
Note on IW174: User: 1. Part list unsuccessful imported. (wait for reimport) 2. Weekly plan unsuccessful imported (missing format - need user to fix it) (p'Yut will fix and import then confirm to user again) 3. Plan priority (wait for reimport)
Note on IW175: User: 2Dec - may finish 2Dec 3Dec - Found new problems(old bugs) - 100% fixed (testing in progress) - Must finished the testing within 3Dec 4Dec - Able to test
Note on IS176: User: ไก่
Note on IW176: User: Will test today. 3Dec - Change the testing to 4Dec
Note on IS177: User: ใบเตย
Note on IV177: User: Bug found, Fixed and will retest with user 2Dec.
Note on IY177: User: 3Dec - Will able to test on 4Dec
Note on IW179: User: Will UAT 2Dec.
Note on IR180: User: ทดสอบพี่ขวัญชัย
Note on IY183: User: 3Dec - Waiting for special schedule above - Able to test on 4Dec