## Summary
Project punch list
Customer : SKT
Project name : Handy terminal stock management system | [19 empty] | Create:19-Jun-2025
[9 empty] | Cause of a problem T/L |  | Problem solving T/L |  |  |  |  | Custumer Confirmation |  |  |  | Update:19-Jun-2025
No. | Issuing Date | Issue Category | Function/Root | Picture/Screen shot | Description ENG | Cause of a problem ENG | Solve problems ENG | In charge | Plan | Actual | Plan |  | Actual |  | Status | Date | PIC | Status | Note | PIC
[9 empty] | End | End | Start | End | Start | End
1 | 2025-07-29 | Problem | Kanban Status Not Resuse |  | Kanban status Normal : Not using , Inbound Complete Status Kanban change to : using , Outbound Complete Kanban status change to : Not using | Outbound Completed Kanban Status Not change | Check Function and modify | Tomas Tech Yutthapong | 2025-08-07 |  | 2025-08-01 | 2025-08-07 | 2025-08-01 | 2025-08-05 | 100%
2 | 2025-07-29 | Request | Log Data Error |  | User Scan Error on Handy , customer want show Error on Pegasus | User Scan Kanban Status "NG" user don't delete | create new page show list Error and delete on Pegasus | Tomas Tech Yutthapong | 2025-08-07 |  | 2025-07-31 | 2025-08-07 | 2025-08-06 | 2025-08-07 | 100%
3 | 2025-07-29 | Problem | repair database |  | Kanban status it using, it don't reuse Kanban | Kanban QR code Don't use | use statement query repair status By compare inbound, outbound | Tomas Tech Yutthapong | 2025-08-07 |  | 2025-07-31 | 2025-08-07 | 2025-07-31 | 2025-07-31 | 100%
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23