## Spiral Project
[Thai nippon food co.,ltd] Project Schedule | [8 empty] | Copyright© TOMAS TECH CORPORATION. All rights reserved.
[Thai Nippon foods Co.,Ltd]
| Project Start Date | 2023-09-20 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Week 22 | [6 empty] | Week 23 | [6 empty] | Week 24 | [6 empty] | Week 25 | [6 empty] | Week 26 | [6 empty] | Week 27 | [6 empty] | Week 28 | [6 empty] | Week 29 | [6 empty] | Week 30 | [6 empty] | Week 31 | [6 empty] | Week 32 | [6 empty] | Week 33 | [6 empty] | Week 34 | [6 empty] | Week 35 | [6 empty] | Week 36 | [6 empty] | Week 37 | [6 empty] | Week 38 | [6 empty] | Week 39 | [6 empty] | Week 40 | [6 empty] | Week 41 | [6 empty] | Week 42 | [6 empty] | Week 43
| Project Lead | 2024-03-30 | [6 empty] | 2023-09-18 | [6 empty] | 2023-09-25 | [6 empty] | 2023-10-02 | [6 empty] | 2023-10-09 | [6 empty] | 2023-10-16 | [6 empty] | 2023-10-23 | [6 empty] | 2023-10-30 | [6 empty] | 2023-11-06 | [6 empty] | 2023-11-13 | [6 empty] | 2023-11-20 | [6 empty] | 2023-11-27 | [6 empty] | 2023-12-04 | [6 empty] | 2023-12-11 | [6 empty] | 2023-12-18 | [6 empty] | 2023-12-25 | [6 empty] | 2024-01-01 | [6 empty] | 2024-01-08 | [6 empty] | 2024-01-15 | [6 empty] | 2024-01-22 | [6 empty] | 2024-01-29 | [6 empty] | 2024-02-05 | [6 empty] | 2024-02-12 | [6 empty] | 2024-02-19 | [6 empty] | 2024-02-26 | [6 empty] | 2024-03-04 | [6 empty] | 2024-03-11 | [6 empty] | 2024-03-18 | [6 empty] | 2024-03-25 | [6 empty] | 2024-04-01 | [6 empty] | 2024-04-08 | [6 empty] | 2024-04-15 | [6 empty] | 2024-04-22 | [6 empty] | 2024-04-29 | [6 empty] | 2024-05-06 | [6 empty] | 2024-05-13 | [6 empty] | 2024-05-20 | [6 empty] | 2024-05-27 | [6 empty] | 2024-06-03 | [6 empty] | 2024-06-10 | [6 empty] | 2024-06-17 | [6 empty] | 2024-06-24 | [6 empty] | 2024-07-01 | [6 empty] | 2024-07-08
 | time axis 2023-09-18 to 2024-07-14
WBS | TASK | PIC | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2023-09-18 to 2024-07-14
1 | Kick-off meeting |  |  |  | - |  |  | -
1.1 | Kick-off meeting after PO | TNF/Tomas |  | 2023-09-18 | 2023-09-18 | 1 | 0% | 1
1.2 |  |  |  |  | - |  |  | -
1.3 |  |  |  |  | - |  |  | -
1.4 |  |  |  |  | - |  |  | -
2 | Software schedule |  |  |  | - |  |  | -
2.1 | Requirements confirmation | TNF/Tomas |  | 2023-09-18 | 2023-10-07 | 20 | 0% | 15
2.2 | Data organization/confirmation | TNF/Tomas |  | 2023-09-18 | 2023-10-07 | 20 | 0% | 15
2.3 | System Design | Tomas |  | 2023-09-18 | 2023-10-27 | 40 | 0% | 30
2.4 | Software development | Tomas |  | 2023-10-01 | 2023-11-10 | 41 | 0% | 30
2.5 | Software test | Tomas |  | 2023-11-01 | 2023-11-21 | 21 | 0% | 15
2.6 | [7 empty] | -
3 | Hardware schedule |  |  |  | - |  |  | -
3.1 | Requirements and site survey confirmation | TNF/Tomas |  | 2023-09-18 | 2023-10-07 | 20 | 0% | 15
3.2 | System Design | Tomas |  | 2023-09-18 | 2023-10-07 | 20 | 0% | 15
3.3 | Drawing Desgin | Tomas |  | 2023-09-18 | 2023-10-13 | 26 | 0% | 20
3.4 | Hardware procurement | Tomas |  | 2023-10-09 | 2023-10-15 | 7 | 0% | 5
3.5 | Hardware pre-shipment confirmation | Tomas |  | 2023-10-16 | 2024-02-12 | 120 | 0% | 86
3.6 | Hardware Assembly | Tomas |  | 2023-10-30 | 2023-12-03 | 35 | 0% | 25
3.7 |  |  |  |  | - |  |  | -
3.8 |  |  |  |  | - |  |  | -
4 | Installation |  |  |  | - |  |  | -
4.1 | Software installation | Tomas |  | 2023-12-05 | 2024-01-13 | 40 | 0% | 29
4.2 | Hardware installation | Tomas |  | 2023-12-05 | 2024-01-13 | 40 | 0% | 29
4.3 | Wiring and Connect to machine | Tomas |  | 2024-01-04 | 2024-02-15 | 43 | 0% | 31
4.4 | Teaching for UT | TNF/Tomas |  | 2024-02-16 | 2024-03-16 | 30 | 0% | 21
4.5 | User Testing & Trial | TNF/Tomas |  | 2024-02-16 | 2024-03-16 | 30 | 0% | 21
4.6 | Supports user feedback | TNF/Tomas |  | 2024-02-16 | 2024-03-16 | 30 | 0% | 21
4.7 | Teaching for Go live | TNF/Tomas |  | 2024-02-16 | 2024-03-16 | 30 | 0% | 21
4.8 | Go live | TNF/Tomas |  | 2024-02-16 | 2024-03-16 | 30 | 0% | 21
4.9 |  |  |  |  | - |  |  | -
4.10 | [7 empty] | -
TEMPLATE ROWS
See the Help worksheet to learn how to use these rows. You can hide these rows before printing.
1 | [ Level 1 Task or Phase ] |  |  |  | - |  |  | -
1.1 | . [ Level 2 Task ] |  |  |  | - |  |  | -
1.1.1 | . . [ Level 3 Task ] |  |  |  | - |  |  | -
1.1.1.1 | . . . [ Level 4 Task ] |  |  |  | - |  |  | -
► Watch How to Create a Gantt Chart in Excel
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.

## Schedule install plant A
OUT OF SCHEDULE | Schedule Hardware Install | [46 empty] | *Partially omitted
| No. | Description | [8 empty] | PIC |  | Progress (%) | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
[11 empty] | Main | Support |  | 2023-09-18 | 2023-09-19 | 2023-09-20 | 2023-09-21 | 2023-09-22 | 2023-09-23 | 2023-09-24 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-30 | 2023-10-01 | 2023-10-02 | 2023-10-03 | 2023-10-04 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 | 2023-10-14 | 2023-10-15 | 2023-10-16 | 2023-10-17 | 2023-10-18 | 2023-10-19 | 2023-10-20 | 2023-10-21 | 2023-10-22
|  |  |  | 1 | 2 | 2 |  | Progress ahead of schedule |  | (Input Number "1")
[5 empty] | 2 | 2 |  | Progress as planned |  | (Input Number "2")
[5 empty] | 2 | 2 | 3 | Progress with scheduled delay |  | (Input Number "3")
[5 empty] | 2 | 4 |  | Progress finished job |  | (Input Number "4")
[11 empty] | Overall |  | 0%
| 1 | Installation on site plant A
| 1.1 |  | - Install main box master | [7 empty] | Tomas | TNF
|  |  |  | - Install Box master | [8 empty] | 0%
|  |  |  | - Check Communication PLC | [8 empty] | 0%
|  |  |  | - Install program for I/O Check | [8 empty] | 0%
| 1.2 |  | - Install cabinet for collection signal from Machine Plant A ( 14 Machine ) | [7 empty] | Tomas | TNF
|  |  |  | - Install box for collect signal and data Fry fry room ( 7 Machine ) | [8 empty] | 0%
[5 empty] | - Install Box main 2 ( Prepare for fry room ) | [7 empty] | 0%
[5 empty] | - Install slave Box 2-1 ( Collect signal steam cook machine ) | [7 empty] | 0%
[5 empty] | - Install slave Box 2-2 ( Collect signal Koppen fryer machine ) | [7 empty] | 0%
|  |  |  | - Install Box main 3 ( Collect signal and data Spiral room ) ( 4 Machine ) | [8 empty] | 0%
[5 empty] | - Install Box main 3 | [7 empty] | 0%
|  |  |  | - Install Box main 4 ( Polystar Clean room ) ( 3 Machine ) | [8 empty] | 0%
[5 empty] | - Install Box main 4 | [7 empty] | 0%
| 1.2 |  | - Install Power cable,Lan Cable,I/O Signal Cable ( Plant A Zone 1 ) | [7 empty] | TNF | Tomas
[5 empty] | - Install Power cable,Lan Cable from server (hub) to Box Main 2 | [7 empty] | 0%
[5 empty] | - Install Lan Cable from Box Main2 to Box Main 2-1,Box Main 2-2, Highcook 1-2,New High cook 1-2,Sunmax | [7 empty] | 0%
[5 empty] | - Install Power cable to Box Main 2-1 | [7 empty] | 0%
[5 empty] | - Install Power cable to Box Main 2-2 | [7 empty] | 0%
[5 empty] | - Install wiring I/O signal cable between Box Main 2-1 ⇆ Koppen Fryer | [7 empty] | 0%
[5 empty] | - Install wiring I/O signal cable between Box Main 2-2 ⇆ Steam cook | [7 empty] | 0%
| 1.3 |  | - Install Power cable,Lan Cable,I/O Signal Cable ( Plant A Zone 2 ) | [7 empty] | TNF | Tomas
[5 empty] | - Install Power cable,Lan Cable from server (hub) to Box Main 3 | [7 empty] | 0%
[5 empty] | - Install Lan Cable from Box Main 3 to Spiral No.6,No.7 | [7 empty] | 0%
[5 empty] | - Install wiring I/O signal cable between Box Main 2-1 ⇆ Koppen Fryer | [7 empty] | 0%
[5 empty] | - Install wiring I/O signal cable between Box Main 2-2 ⇆ Steam cook | [7 empty] | 0%
| 1.4 |  | - Install Power cable,Lan Cable,I/O Signal Cable ( Plant A Zone 3 ) | [7 empty] | TNF | Tomas
[5 empty] | - Install Power cable,Lan Cable from server (hub) to Box Main 4 | [7 empty] | 0%
[5 empty] | - Install Lan Cable from Box Main 4 to Polystar 1,2,3 | [7 empty] | 0%
| 1.5 |  | - Wiring and Config parameter setting Machine plant A (Prepare for Fry room 7 Machine) | [7 empty] | Tomas | TNF
[5 empty] | - Install and Config module ethernet FX3U to High-Cook New 1 Machine | [7 empty] | 0%
[5 empty] | - Install and Config module ethernet FX3U to High-Cook New 2 Machine | [7 empty] | 0%
[5 empty] | - Install and Config module ethernet FX3U to High-Cook 1 Machine | [7 empty] | 0%
[5 empty] | - Install and Config module ethernet FX3U to High-Cook 2 Machine | [7 empty] | 0%
[5 empty] | - Install and Config module ethernet FX3U to Sun Max Machine | [7 empty] | 0%
[5 empty] | - Wiring and connect to machine KOPPEN FRYER | [7 empty] | 0%
[5 empty] | - Wiring and connect to machine STEAM COOK | [7 empty] | 0%
[5 empty] | - Test communication data between PLC Master ⇆ Machine | [7 empty] | 0%
| 1.6 |  | - Wiring and Config parameter setting Machine plant A (Spiral room 4 Machine) | [7 empty] | Tomas | TNF
[5 empty] | - Install and Config module ethernet QJ71EN71 to Spiral No.6 Machine | [7 empty] | 0%
[5 empty] | - Install and Config module ethernet QJ71EN71 to Spiral No.7 Machine | [7 empty] | 0%
[5 empty] | - Wiring and connect to machine Spiral No.2 | [7 empty] | 0%
[5 empty] | - Wiring and connect to machine Spiral No.3 | [7 empty] | 0%
[5 empty] | - Test communication data between PLC Master ⇆ Machine | [7 empty] | 0%
| 1.7 |  | - Wiring and Config parameter setting Machine plant A (Polystar room 3 Machine) | [7 empty] | Tomas | TNF
[5 empty] | - Setting parameter for collect data polystar 1 | [7 empty] | 0%
[5 empty] | - Setting parameter for collect data polystar 2 | [7 empty] | 0%
[5 empty] | - Setting parameter for collect data polystar 3 | [7 empty] | 0%
[5 empty] | - Test communication data between PLC Master ⇆ Machine | [7 empty] | 0%
Completed
In progress (on schedule)
In progress (Risk out of schedule)
Out of schedule

## Schedule install plant B
OUT OF SCHEDULE | Schedule Hardware Install | [46 empty] | *Partially omitted
| No. | Description | [8 empty] | PIC |  | Progress (%) | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
[11 empty] | Main | Support |  | 2023-09-18 | 2023-09-19 | 2023-09-20 | 2023-09-21 | 2023-09-22 | 2023-09-23 | 2023-09-24 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-30 | 2023-10-01 | 2023-10-02 | 2023-10-03 | 2023-10-04 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 | 2023-10-14 | 2023-10-15 | 2023-10-16 | 2023-10-17 | 2023-10-18 | 2023-10-19 | 2023-10-20 | 2023-10-21 | 2023-10-22
|  |  |  | 1 | 2 | 2 |  | Progress ahead of schedule |  | (Input Number "1")
[5 empty] | 2 | 2 |  | Progress as planned |  | (Input Number "2")
[5 empty] | 2 | 2 | 3 | Progress with scheduled delay |  | (Input Number "3")
[5 empty] | 2 | 4 |  | Progress finished job |  | (Input Number "4")
[11 empty] | Overall |  | 0%
| 1 | Installation on site plant B
| 1.1 |  | - Install cabinet for collection signal from Machine Plant B ( 10 Machine ) | [7 empty] | Tomas | TNF
|  |  |  | - Install box for collect signal and data Fry fry room | [8 empty] | 0%
[5 empty] | - Install Box main 2 ( Fry fry room ) | [7 empty] | 0%
|  |  |  | - Install Box main 3 ( Collect signal and data Spiral room ) | [8 empty] | 0%
[5 empty] | - Install Box main 3 | [7 empty] | 0%
|  |  |  | - Install Box main 4 ( Clean room ) | [8 empty] | 0%
[5 empty] | - Install Box main 4 | [7 empty] | 0%
|  |  | - Install Power cable,Lan Cable,I/O Signal Cable ( Plant B Zone 1 ) | [7 empty] | TNF | Tomas
[5 empty] | - Install Power cable,Lan Cable from server (hub) to Box Main 2 | [7 empty] | 0%
[5 empty] | - Install Lan Cable from Box Main2 to Fryer 1,Fryer2,Steam Oven 4 | [7 empty] | 0%
[5 empty] | - Install wiring I/O signal cable between Box Main 2 ⇆ Koppen Fryer | [7 empty] | 0%
|  |  | - Install Power cable,Lan Cable,I/O Signal Cable ( Plant B Zone 2 ) | [7 empty] | TNF | Tomas
[5 empty] | - Install Power cable,Lan Cable from server (hub) to Box Main 3 | [7 empty] | 0%
[5 empty] | - Install Lan Cable from Box Main2 to Spiral No.4,Spiral No.5 | [7 empty] | 0%
|  |  | - Install Power cable,Lan Cable,I/O Signal Cable ( Plant B Zone 3 ) | [7 empty] | TNF | Tomas
[5 empty] | - Install Power cable,Lan Cable from server (hub) to Box Main 4 | [7 empty] | 0%
[5 empty] | - Install wiring I/O signal cable between Box Main 2 ⇆ Vertical packing No.1 | [7 empty] | 0%
[5 empty] | - Install wiring I/O signal cable between Box Main 2 ⇆ Vertical packing No.2 | [7 empty] | 0%
[5 empty] | - Install wiring I/O signal cable between Box Main 2 ⇆ Generral Packer No.1 | [7 empty] | 0%
[5 empty] | - Install wiring I/O signal cable between Box Main 2 ⇆ Generral Packer No.2 | [7 empty] | 0%
| 1.3 |  | - Install cabinet for collection signal from Machine Plant B ( 10 Machine ) | [7 empty] | TNF | Tomas
|  |  |  | - Install box for collect signal and data Fry fry room ( 4 Machine ) | [8 empty] | 0%
[5 empty] | - Install Box main 2 ( for fry room ) | [7 empty] | 0%
|  |  |  | - Install box for collect signal and data Clean room ( 6 Machine ) | [8 empty] | 0%
[5 empty] | - Install Box main 3 ( for Spiral room ) | [7 empty] | 0%
[5 empty] | - Install Box main 4 ( for packing room ) | [7 empty] | 0%
| 1.4 |  | - Wiring and Config parameter setting Machine plant A (Fry Fry room 4 Machine) | [7 empty] | Tomas | TNF
[5 empty] | - Install and Config module ethernet FX3U to Fryer1 Machine | [7 empty] | 0%
[5 empty] | - Install and Config module ethernet FX3U to Fryer2 Machine | [7 empty] | 0%
[5 empty] | - Install and Config module ethernet FX3U to Steam Oven4 Machine | [7 empty] | 0%
[5 empty] | - Wiring and connect to machine KOPPEN FRYER | [7 empty] | 0%
[5 empty] | - Test communication data between PLC Master ⇆ Machine | [7 empty] | 0%
|  |  | - Wiring and Config parameter setting Machine plant A (Spiral room 2 Machine) | [7 empty] | Tomas | TNF
[5 empty] | - Install and Config module ethernet FX3U to Spiral No.4 Machine | [7 empty] | 0%
[5 empty] | - Install and Config module ethernet FX3U to Spiral No.5 Machine | [7 empty] | 0%
[5 empty] | - Test communication data between PLC Master ⇆ Machine | [7 empty] | 0%
|  |  | - Wiring and Config parameter setting Machine plant A (Clean room 4 Machine) | [7 empty] | Tomas | TNF
[5 empty] | - Wiring and connect to machine Vertical packing 1 | [7 empty] | 0%
[5 empty] | - Wiring and connect to machine Vertical packing 2 | [7 empty] | 0%
[5 empty] | - Wiring and connect to machine General packer 1 | [7 empty] | 0%
[5 empty] | - Wiring and connect to machine General packer 2 | [7 empty] | 0%
- Test communication data between PLC Master ⇆ Machine
Completed
In progress (on schedule)
In progress (Risk out of schedule)
Out of schedule