## GanttChart
[WMS] Project Schedule | [8 empty] | Copyright© TOMAS TECH CORPORATION. All rights reserved.
[Mitsui Precision Thai Co.,Ltd.]
| Project Start Date | 2025-10-01 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20
| Project Lead | 2025-10-01 | [6 empty] | 2025-09-29 | [6 empty] | 2025-10-06 | [6 empty] | 2025-10-13 | [6 empty] | 2025-10-20 | [6 empty] | 2025-10-27 | [6 empty] | 2025-11-03 | [6 empty] | 2025-11-10 | [6 empty] | 2025-11-17 | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08 | [6 empty] | 2025-12-15 | [6 empty] | 2025-12-22 | [6 empty] | 2025-12-29 | [6 empty] | 2026-01-05 | [6 empty] | 2026-01-12 | [6 empty] | 2026-01-19 | [6 empty] | 2026-01-26 | [6 empty] | 2026-02-02 | [6 empty] | 2026-02-09
 | time axis 2025-09-29 to 2026-02-15
WBS | TASK | PIC | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2025-09-29 to 2026-02-15
1 | Kick-off meeting |  |  |  | - |  |  | -
1.1 | Kick-off meeting | /Tomas |  | 2025-04-08 | 2025-04-17 | 10 | 0% | 8
1.2 |  |  |  |  | - |  |  | -
1.3 |  |  |  |  | - |  |  | -
1.4 |  |  |  |  | - |  |  | -
2 | Software schedule |  |  |  | - |  |  | -
2.1 | Requirements confirmation | Tomas |  | 2025-04-22 | 2025-06-08 | 48 | 100% | 34
2.2 | System Design | Tomas |  | 2025-08-05 | 2025-11-12 | 100 | 70% | 72
2.3 | Software development (Handy) | Tomas |  | 2025-11-10 | 2026-01-23 | 75 | 0% | 50
| Inbound Material -WH |  |  | 2025-11-10 | 2025-11-17 | 8 | 0% | 6
| IQC Material-WH |  |  | 2025-11-18 | 2025-11-24 | 7 | 0% | 5
| Outbound Material to Production -WH |  |  | 2025-11-25 | 2025-12-02 | 8 | 0% | 6
| Transfer Receive Material -PD |  |  | 2025-12-03 | 2025-12-09 | 7 | 0% | 5
| Outbound Material Usage -PD |  |  | 2025-12-10 | 2025-12-19 | 10 | 0% | 8
| Inbound FG -PD |  |  | 2025-12-22 | 2025-12-26 | 5 | 0% | 5
| IQC FG -PD |  |  | 2026-01-05 | 2026-01-08 | 4 | 0% | 4
| WH Receive FG -WH |  |  | 2026-01-09 | 2026-01-13 | 5 | 0% | 3
| Outbound Delivery -WH |  |  | 2026-01-14 | 2026-01-16 | 3 | 0% | 3
| Template Label & Label Print Controller |  |  | 2026-01-19 | 2026-01-21 | 3 | 0% | 3
| Stock Management |  |  | 2026-01-22 | 2026-01-23 | 2 | 0% | 2
2.4 | Software development (Web) | Tomas |  | 2025-10-09 | 2026-01-13 | 97 | 0% | 49
| Master Data -WH,PD |  |  | 2025-10-09 | 2025-10-14 | 6 | 80% | 4
| Inbound - Outbound Inquiery, Tracking, Tag Label Page -WH |  |  | 2025-10-15 | 2025-10-19 | 5 | 50% | 3
| Import Purchase Order -WH |  |  | 2025-10-20 | 2025-10-20 | 1 | 100% | 1
| Import Schedule Raw Material Receiving (Plan) -WH |  |  | 2025-10-21 | 2025-10-21 | 1 | 100% | 1
| Inbound Material Page -WH |  |  | 2025-10-22 | 2025-10-26 | 5 | 100% | 3
| Purchase Order Page -WH |  |  | 2025-10-27 | 2025-10-28 | 2 | 100% | 2
| -Print Purchase Order Domistic -WH |  |  | 2025-10-29 | 2025-10-31 | 3 | 100% | 3
| -Print Purchase Order International -WH |  |  | 2025-11-01 | 2025-11-04 | 4 | 0% | 2
| IQC Material Page -WH |  |  | 2025-11-05 | 2025-11-06 | 2 | 0% | 2
| Import Schedule Raw Material Request (Plan) -WH,PD |  |  | 2025-11-07 | 2025-11-07 | 1 | 0% | 1
| Raw Material Request Page -WH,PD |  |  | 2025-11-08 | 2025-11-11 | 4 | 0% | 2
| -Print Raw Material Request -WH,PD |  |  | 2025-11-12 | 2025-11-13 | 2 | 0% | 2
| Import Schedule FG Production (Plan) -PD |  |  | 2025-11-14 | 2025-11-14 | 1 | 0% | 1
| Inbound Production Page -PD |  |  | 2025-11-15 | 2025-11-21 | 7 | 0% | 5
| Outbound Material Usage Page -PD |  |  | 2025-11-22 | 2025-11-26 | 5 | 0% | 3
| IQC FG Page -PD |  |  | 2025-11-27 | 2025-11-30 | 4 | 0% | 2
| Outbound FG (Production) To WH Page -WH,PD |  |  | 2025-12-22 | 2025-12-26 | 5 | 0% | 5
| -Print Finished Goods Pay In Stock Sheet -PD |  |  | 2026-01-05 | 2026-01-06 | 2 | 0% | 2
| Outbound Delivery Page -WH |  |  | 2026-01-07 | 2026-01-10 | 4 | 0% | 3
| Stock Management -WH |  |  | 2026-01-11 | 2026-01-13 | 3 | 0% | 2
2.5 | Software test & Internal final test |  |  | 2026-01-26 | 2026-01-30 | 5 | 0% | 5
3 | Hardware schedule | [6 empty] | #VALUE!
3.1 |  |  |  |  | - |  |  | -
3.2 |  |  |  |  | - |  |  | -
3.3 |  |  |  |  | - |  |  | -
3.4 |  |  |  |  | - |  |  | -
3.5 |  |  |  |  | - |  |  | -
3.6 |  |  |  |  | - |  |  | -
3.7 |  |  |  |  | - |  |  | -
4 | Installation |  |  |  | - |  |  | -
4.1 | Hardware installation |  |  | 2026-02-02 | 2026-02-03 | 2 | 0% | 2
4.2 | Software installation |  |  | 2026-02-02 | 2026-02-03 | 2 | 0% | 2
4.3 | Teaching for UT |  |  | 2026-02-04 | 2026-02-06 | 3 | 0% | 3
4.4 | User Testing & Trial |  |  | 2026-02-07 | 2026-03-01 | 23 | 0% | 15
4.5 | Supports user feedback |  |  | 2026-02-07 | 2026-03-01 | 23 | 0% | 15
4.6 | Teaching for Go live |  |  | 2026-03-02 | 2026-03-02 | 1 | 0% | 1
4.7 | Go live |  |  | 2026-03-02 | 2026-03-03 | 2 | 0% | 2
4.8 | [7 empty] | -
TEMPLATE ROWS
See the Help worksheet to learn how to use these rows. You can hide these rows before printing.
1 | [ Level 1 Task or Phase ] |  |  |  | - |  |  | -
1.1 | . [ Level 2 Task ] |  |  |  | - |  |  | -
1.1.1 | . . [ Level 3 Task ] |  |  |  | - |  |  | -
1.1.1.1 | . . . [ Level 4 Task ] |  |  |  | - |  |  | -
► Watch How to Create a Gantt Chart in Excel
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.